## May-23 Plan- Completed (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 |  |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 10 | 12 | 12 | 12 | 18 | 25 | 23 |  |  | Track beam with nose |  | 1140 | 95 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 36 | 240 | 60 | 108 | 125 | 355 | 924 |  | Track beam without nose |  | 960 | 80
Part A | Nos. | 6 | 6 | 6 | 6 | 6 | 14 | 14 |  |  | h-section beam |  | 336 | 28
| Qty |  | 18 | 120 | 30 | 36 | 70 | 140 | 414 |  | U-section beam |  | 336 | 28
Part B | Nos. | 4 | 6 | 6 | 6 | 6 | 2 |  |  |  | Pre-cast Slab |  | 38 | 76
| Qty |  | 18 | 120 | 30 | 36 | 10 | 0 | 214 |  | Total: |  | 2810 | 307
Part H | Nos. | [6 empty] | 4 | [9 empty] | Month Plan | Interim
| Qty |  | 0 | 0 | 0 | 0 | 0 | 115 | 115 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 36 | 17.4514
Part C | Nos. |  |  |  |  | 6 | 9 | 5 |  |  |  |  | A | 414 | 255.4545 | 669.4545 | RCC Foundation | 240 | 116.3428
| Qty |  | 0 | 0 | 0 | 36 | 45 | 100 | 181 |  |  |  | B | 214 | 255.4545 | 469.4545 | Step Footing | 60 | 29.0857
Part I | Nos. | [11 empty] | C | 181 | 255.4545 | 436.4545 | Pier 1900 mm | 132 | 63.9885
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | D | 0 | 255.4545 | 255.4545 | Pier 1600 mm | 500 | 242.3809
Part D | Nos. | [11 empty] | E | 15 | 255.4545 | 270.4545 | Pier Cap | 355 | 172.0904
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 150 | 255.4545 | 405.4545 | Track Beam with Nose | 1140 | 552.6284
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 4 | 75 | 0 |  |  |  |  | G | 150 | 255.4545 | 405.4545 | Track Beam without Nose | 960 | 465.3713
| Qty | 0 | 0 | 0 | 0 | 24 | 375 | 0 | 399 |  |  |  | H | 115 | 255.4545 | 370.4545 | H - Section Beam | 336 | 162.8799
Part E | Nos. | [5 empty] | 3 | [5 empty] | I | 0 | 255.4545 | 255.4545 | U - Section Beam | 336 | 162.8799
| Qty |  | 0 | 0 | 0 | 0 | 15 | 0 | 15 |  |  |  | J | 60 | 255.4545 | 315.4545 | Pre-cast Slab | 38 | 18.4209
Part F | Nos. | [5 empty] | 30 | [5 empty] | K | 24 | 255.4545 | 279.4545
| Qty |  | 0 | 0 | 0 | 0 | 150 | 0 | 150 |  |  |  |  | 1323 | 2810 | 4133
Part G | Nos. | [5 empty] | 30
| Qty |  | 0 | 0 | 0 | 0 | 150 | 0 | 150
Part J | Nos. | [5 empty] | 12
| Qty |  | 0 | 0 | 0 | 0 | 60 | 0 | 60
Part K | Nos. |  |  |  |  | 4 |  |  |  | Clearence to be given by 10th Feb 2023 from JSW.
| Qty |  | 0 | 0 | 0 | 24 | 0 | 0 | 24
Total | Nos. | 10 | 12 | 12 | 12 | 22 | 100 | 23
| Qty | 0 | 36 | 240 | 60 | 132 | 500 | 355 | 1323
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 673.1397 | 23.96%
[10 empty] | Week 2 (9 to 16) | 703.2161 | 25.03%
[10 empty] | Week 3 (17 to 24) | 703.2161 | 25.03%
[10 empty] | Week 4 (25 to 31) | 730.4281 | 25.99%
[10 empty] | Total | 2810
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 277.6971 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 356.9687 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 356.9687 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 331.3655 | 25.05% | 25.52%
[10 empty] | Total | 1323
[10 empty] | Monthly Concreting Target | 4133 | cum
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 27 | 78 | 16 | 13 | 27 | 161 | [10 empty] | Month Plan | Interim
| Qty | 27 | 78 | 16 | 13 | 27 | 161 | [9 empty] | Track beam with nose | 27 | 8.1
Part A | Nos. | [12 empty] | A | 0 |  | Track beam without nose | 78 | 23.4
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | B | 0 |  | h-section beam | 16 | 4.8
Part B | Nos. | [5 empty] | 0 | [6 empty] | C | 0 |  | U-section beam | 13 | 3.9
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 27 | 8.1
Part H | Nos. | 27 | 78 | 16 | 13 | 27 | 161 | [6 empty] | E | 0
| Qty | 27 | 78 | 16 | 13 | 27 | 161 | [6 empty] | F | 0
Part C | Nos. | [12 empty] | G | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | H | 161
Part I | Nos. | [5 empty] | 0 | [6 empty] | I | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | J | 0
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 161
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 16.1 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 32.2 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 56.35 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 56.35 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 161
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 27 | 78 | 16 | 13 | 27 | 161
| Qty | 27 | 78 | 16 | 13 | 27 | 161
FTM
Track Linking
A |  | 0
B |  | 0
C |  | 0
D |  | 100
E |  | 0
F |  | 0
G |  | 0
H |  | 0
I |  | 0
J |  | 0
K |  | 0

## Jul-23 Plan - Old (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 | 35 |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Track beam with nose |  | 720 | 60 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Track beam without nose |  | 720 | 60
Part A | Nos. | [9 empty] | h-section beam |  | 300 | 25
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | U-section beam |  | 300 | 25
Part B | Nos. | [9 empty] | Pre-cast Slab |  | 30 | 60
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total: |  | 2070 | 230 | [5 empty] | Pre-cast |  |  | Cast Insitu | Total | UOM | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Part H | Nos. | [16 empty] | Month Plan | Interim |  | Qty | Cum | Cum | Cum | Nos. | 60 | 60 | 20 | 20 | 60 | 220
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 159 | 77.0771 | A | 0 | 0 | 0 | 0 | Qty | 720 | 720 | 240 | 240 | 30 | 1950
Part C | Nos. | [11 empty] | A | 0 | 188.1818 | 188.1818 | RCC Foundation | 740 | 358.7237 | B | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | B | 0 | 188.1818 | 188.1818 | Step Footing | 185 | 89.6809 | C | 16 | 192 | 0 | 192
Part I | Nos. | [11 empty] | C | 0 | 188.1818 | 188.1818 | Pier 1900 mm | 120 | 58.1714 | D | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | D | 0 | 188.1818 | 188.1818 | Pier 1600 mm | 850 | 412.0475 | E | 0 | 0 | 476 | 476
Part D | Nos. | [11 empty] | E | 476 | 188.1818 | 664.1818 | Pier Cap | 300 | 145.4285 | F | 0 | 0 | 225 | 225
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 225 | 188.1818 | 413.1818 | Track Beam with Nose | 720 | 349.0285 | G | 159 | 1218 | 328 | 1546
Priority Section-2 | Nos. | 53 | 53 | 37 | 37 | 20 | 170 | 20 |  |  |  |  | G | 328 | 188.1818 | 516.1818 | Track Beam without Nose | 720 | 349.0285 | H | 5 | 60 | 0 | 60
| Qty | 0 | 159 | 740 | 185 | 120 | 850 | 300 | 2354 |  |  |  | H | 0 | 188.1818 | 188.1818 | H - Section Beam | 300 | 145.4285 | I | 40 | 480 | 0 | 480
Part E | Nos. | 17 | 17 | 17 | 17 | [7 empty] | I | 0 | 188.1818 | 188.1818 | U - Section Beam | 300 | 145.4285 | J | 0 | 0 | 375 | 375
| Qty |  | 51 | 340 | 85 | 0 | 0 | 0 | 476 |  |  |  | J | 395 | 188.1818 | 583.1818 | Pre-cast Slab | 30 | 14.5429 | K | 0 | 0 | 930 | 930
Part F | Nos. | [5 empty] | 45 | [5 empty] | K | 930 | 188.1818 | 1118.1818 |  |  |  |  | 220 | 1950 | 2334 | 4284
| Qty |  | 0 | 0 | 0 | 0 | 225 | 0 | 225 |  |  |  |  | 2354 | 2070 | 4424
Part G | Nos. | 16 | 16 |  |  |  |  | 18
| Qty |  | 48 | 0 | 0 | 0 | 0 | 280 | 328
Part J | Nos. | [5 empty] | 75 | 2
| Qty |  | 0 | 0 | 0 | 0 | 375 | 20 | 395
Part K | Nos. | 20 | 20 | 20 | 20 | 20 | 50 |  |  | Clearence to be given by 10th Feb 2023 from JSW.
| Qty |  | 60 | 400 | 100 | 120 | 250 | 0 | 930
Total | Nos. | 53 | 53 | 37 | 37 | 20 | 170 | 20
| Qty | 0 | 159 | 740 | 185 | 120 | 850 | 300 | 2354
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 495.8716 | 23.96%
[10 empty] | Week 2 (9 to 16) | 518.0275 | 25.03%
[10 empty] | Week 3 (17 to 24) | 518.0275 | 25.03%
[10 empty] | Week 4 (25 to 31) | 538.0734 | 25.99%
[10 empty] | Total | 2070
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 494.1035 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 635.1507 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 635.1507 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 589.5951 | 25.05% | 25.52%
[10 empty] | Total | 2354
[10 empty] | Monthly Concreting Target | 4424 | cum
|  | 12 | 12 | 12 | 12 | 0.5
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 29 | 28 | 13 | 17 | 93 | 180 | [10 empty] | Month Plan | Interim
| Qty | 348 | 336 | 156 | 204 | 46.5 | 1090.5 | [9 empty] | Track beam with nose | 29 | 8.7
Part A | Nos. | 8 |  | 4 | 4 | 72 | 88 | [6 empty] | A | 88 |  | Track beam without nose | 28 | 8.4
| Qty | 96 | 0 | 48 | 48 | 36 | 228 | [6 empty] | B | 13 |  | h-section beam | 13 | 3.9
Part B | Nos. | 3 | 4 | 2 | 1 | 3 | 13 | [6 empty] | C | 0 |  | U-section beam | 17 | 5.1
| Qty | 36 | 48 | 24 | 12 | 1.5 | 121.5 | [6 empty] | D | 0 |  | Pre-cast Slab | 93 | 27.9
Part H | Nos. | 18 | 24 | 7 | 12 | 18 | 79 | [6 empty] | E | 0
| Qty | 216 | 288 | 84 | 144 | 9 | 741 | [6 empty] | F | 0
Part C | Nos. | [12 empty] | G | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | H | 79
Part I | Nos. | [5 empty] | 0 | [6 empty] | I | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | J | 0
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 180
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 18 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 36 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 63 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 63 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 180
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 29 | 28 | 13 | 17 | 93 | 180
| Qty | 348 | 336 | 156 | 204 | 46.5 | 1090.5
FTM
Track Linking
A |  | 0
B |  | 0
C |  | 0
D |  | 200
E |  | 0
F |  | 0
G |  | 0
H |  | 0
I |  | 0
J |  | 0
K |  | 0

## Aug-23 Plan -old (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 | 35 |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Track beam with nose |  | 720 | 60 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Track beam without nose |  | 720 | 60
Part A | Nos. | [9 empty] | h-section beam |  | 240 | 20
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | U-section beam |  | 240 | 20
Part B | Nos. | [9 empty] | Pre-cast Slab |  | 30 | 60
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total: |  | 1950 | 220 | [5 empty] | Pre-cast |  |  | Cast Insitu | Total | UOM | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Part H | Nos. | [16 empty] | Month Plan | Interim |  | Qty | Cum | Cum | Cum | Nos. | 60 | 60 | 20 | 20 | 60 | 220
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 0 | 0 | A | 0 | 0 | 204 | 204 | Qty | 720 | 720 | 240 | 240 | 30 | 1950
Part C | Nos. | [11 empty] | A | 0 | 0 | 0 | RCC Foundation | 0 | 0 | B | 0 | 0 | 358 | 358
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | B | 0 | 12 | 12 | Step Footing | 50 | 24.2381 | C | 16 | 192 | 0 | 192
Part I | Nos. | [11 empty] | C | 0 | 96 | 96 | Pier 1900 mm | 72 | 34.9028 | D | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | D | 0 | 0 | 0 | Pier 1600 mm | 600 | 290.857 | E | 0 | 0 | 0 | 0
Part D | Nos. | [11 empty] | E | 0 | 48 | 48 | Pier Cap | 604 | 292.7961 | F | 0 | 0 | 150 | 150
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 440 | 0 | 440 | Track Beam with Nose | 720 | 349.0285 | G | 159 | 1218 | 452 | 1670
Priority Section-2 | Nos. | 0 | 0 | 0 | 10 | 12 | 120 | 25 |  |  |  |  | G | 156 | 286 | 442 | Track Beam without Nose | 720 | 349.0285 | H | 5 | 60 | 68 | 128
| Qty | 0 | 0 | 0 | 50 | 72 | 600 | 604 | 1326 |  |  |  | H | 0 | 96 | 96 | H - Section Beam | 240 | 116.3428 | I | 40 | 480 | 0 | 480
Part E | Nos. | [11 empty] | I | 0 | 12 | 12 | U - Section Beam | 240 | 116.3428 | J | 0 | 0 | 278 | 278
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | J | 268 | 696 | 964 | Pre-cast Slab | 30 | 14.5429 | K | 0 | 0 | 594 | 594
Part F | Nos. | [5 empty] | 20 | 13 |  |  |  |  | K | 462 | 334 | 796 | Abutment wall- PART-A | 280 | 135.7333 | Abutment wall- PART-A |  |  | 84 | 84
| Qty |  | 0 | 0 | 0 | 0 | 100 | 340 | 440 |  |  |  | Abutment wall- PART-A | 280 |  | 280 | Abutment wall- PART-D |  |  | Abutment wall- PART-D |  |  |  | 0
Part G | Nos. | [6 empty] | 6 |  |  |  |  | Abutment wall- PART-D | 0 |  | 0 | Cast In-situ slab- 1- PART-G |  |  | Cast In-situ slab- 1- PART-G |  |  |  | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 156 | 156 |  |  |  | Cast In-situ slab- 1- PART-G | 0 |  | 0 | Cast In-situ slab- 2- PART-G |  |  | Cast In-situ slab- 2- PART-G |  |  |  | 0
Part J | Nos. | [5 empty] | 32 | 6 |  |  |  |  | Cast In-situ slab- 2- PART-G | 0 |  | 0 | Cast In-situ slab- PART-C |  |  | Cast In-situ slab- PART-C |  |  |  | 0
| Qty |  | 0 | 0 | 0 | 0 | 160 | 108 | 268 |  |  |  | Cast In-situ slab- PART-C | 0 |  | 0 |  |  |  |  | 220 | 1950 | 2188 | 4138
Part K | Nos. |  |  |  | 10 | 12 | 68 | [6 empty] | 1606 | 1580 | 3186
| Qty |  | 0 | 0 | 50 | 72 | 340 | 0 | 462
Total | Nos. | 0 | 0 | 0 | 10 | 12 | 120 | 25
| Qty | 0 | 0 | 0 | 50 | 72 | 600 | 604 | 1326
Abutment wall- PART-A |  |  | 25 | 255 |  |  |  |  | 280
Abutment wall- PART-D
Cast In-situ slab- 1- PART-G
Cast In-situ slab- 2- PART-G
Cast In-situ slab- PART-C
Cast Insitu | [8 empty] | 0
1606
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 467.1254 | 23.96%
[10 empty] | Week 2 (9 to 16) | 487.9969 | 25.03%
[10 empty] | Week 3 (17 to 24) | 487.9969 | 25.03%
[10 empty] | Week 4 (25 to 31) | 506.8807 | 25.99%
[10 empty] | Total | 1950
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 337.0986 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 433.3271 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 433.3271 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 402.2471 | 25.05% | 25.52%
[10 empty] | Total | 1606
[10 empty] | Monthly Concreting Target | 3556 | cum
|  | 12 | 12 | 12 | 12 | 0.5
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total | [10 empty] | Erection
Priority Section-1 | Nos. | 31 | 25 | 12 | 18 | 39 | 125 | [7 empty] | Erection |  |  | Month Plan | Interim
| Qty | 228 | 96 | 96 | 120 | 324 | 864 | [9 empty] | Track beam with nose | 31 | 9.3
Part A | Nos. | [5 empty] | 0 | [6 empty] | A | 0 |  | Track beam without nose | 25 | 7.5
| Qty | [5 empty] | 0 | [6 empty] | B | 0 |  | h-section beam | 12 | 3.6
Part B | Nos. | [5 empty] | 0 | [6 empty] | C | 72 |  | U-section beam | 18 | 5.4
| Qty | [5 empty] | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 39 | 11.7
Part H | Nos. | 12 | 17 | 4 | 8 | 12 | 53 | [6 empty] | E | 0
| Qty | [5 empty] | 0 | [6 empty] | F | 0
Part C | Nos. | 19 | 8 | 8 | 10 | 27 | 72 | [6 empty] | G | 0
| Qty | 228 | 96 | 96 | 120 | 324 | 864 | [6 empty] | H | 53
Part I | Nos. | [5 empty] | 0 | [6 empty] | I | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | J | 0
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 125
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 12.5 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 25 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 43.75 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 43.75 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 125
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 31 | 25 | 12 | 18 | 39 | 125
| Qty | 228 | 96 | 96 | 120 | 324 | 864
FTM
Track Linking
A |  | 150
B |  | 90
C |  | 0
D |  | 0
E |  | 0
F |  | 0
G |  | 0
H |  | 0
I |  | 0
J |  | 0
K |  | 0

## Sep-23 Plan-Old (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 | 35 |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 22 | 24 | 18 | 18 | 18 | 0 | 0 |  |  | Track beam with nose |  | 720 | 60 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 72 | 360 | 90 | 108 | 0 | 0 | 630 |  | Track beam without nose |  | 720 | 60
Part A | Nos. | 6 | 6 | 6 | 6 | 6 |  |  |  |  | h-section beam |  | 240 | 20
| Qty |  | 18 | 120 | 30 | 36 | 0 | 0 | 204 |  | U-section beam |  | 240 | 20
Part B | Nos. | 16 | 16 | 10 | 10 | 10 |  |  |  |  | Pre-cast Slab |  | 30 | 60
| Qty |  | 48 | 200 | 50 | 60 | 0 | 0 | 358 |  | Total: |  | 1950 | 220 | [5 empty] | Pre-cast |  |  | Cast Insitu | Total | UOM | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Part H | Nos. |  | 2 | 2 | 2 | 2 | [11 empty] | Month Plan | Interim |  | Qty | Cum | Cum | Cum | Nos. | 60 | 60 | 20 | 20 | 60 | 220
| Qty |  | 6 | 40 | 10 | 12 | 0 |  | 68 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 108 | 52.3543 | A | 0 | 0 | 204 | 204 | Qty | 720 | 720 | 240 | 240 | 30 | 1950
Part C | Nos. | [11 empty] | A | 204 | 0 | 204 | RCC Foundation | 600 | 290.857 | B | 0 | 0 | 358 | 358
| Qty |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | B | 358 | 12 | 370 | Step Footing | 150 | 72.7143 | C | 16 | 192 | 0 | 192
Part I | Nos. | [11 empty] | C | 0 | 96 | 96 | Pier 1900 mm | 240 | 116.3428 | D | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | D | 0 | 0 | 0 | Pier 1600 mm | 500 | 242.3809 | E | 0 | 0 | 0 | 0
Part D | Nos. | [11 empty] | E | 0 | 48 | 48 | Pier Cap | 506 | 245.2894 | F | 0 | 0 | 150 | 150
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 150 | 0 | 150 | Track Beam with Nose | 720 | 349.0285 | G | 159 | 1218 | 452 | 1670
Priority Section-2 | Nos. | 0 | 12 | 12 | 12 | 22 | 100 | 20 |  |  |  |  | G | 452 | 286 | 738 | Track Beam without Nose | 720 | 349.0285 | H | 5 | 60 | 68 | 128
| Qty | 0 | 36 | 240 | 60 | 132 | 500 | 506 | 1474 |  |  |  | H | 68 | 96 | 164 | H - Section Beam | 240 | 116.3428 | I | 40 | 480 | 0 | 480
Part E | Nos. | [11 empty] | I | 0 | 12 | 12 | U - Section Beam | 240 | 116.3428 | J | 0 | 0 | 278 | 278
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | J | 278 | 696 | 974 | Pre-cast Slab | 30 | 14.5429 | K | 0 | 0 | 594 | 594
Part F | Nos. | [6 empty] | 5 |  |  |  |  | K | 594 | 334 | 928 | Abutment wall- PART-A | 84 | 40.72 | Abutment wall- PART-A |  |  | 84 | 84
| Qty |  | 0 | 0 | 0 | 0 | 0 | 150 | 150 |  |  |  | Abutment wall- PART-A | 84 |  | 84 | Abutment wall- PART-D | 500 |  | Abutment wall- PART-D |  |  | 500 | 500
Part G | Nos. |  | 6 | 6 | 6 | 6 |  | 12 |  |  |  |  | Abutment wall- PART-D | 500 |  | 500 | Cast In-situ slab- 1- PART-G |  |  | Cast In-situ slab- 1- PART-G |  |  |  | 0
| Qty |  | 18 | 120 | 30 | 36 | 0 | 248 | 452 |  |  |  | Cast In-situ slab- 1- PART-G | 0 |  | 0 | Cast In-situ slab- 2- PART-G |  |  | Cast In-situ slab- 2- PART-G |  |  |  | 0
Part J | Nos. | [5 empty] | 34 | 3 |  |  |  |  | Cast In-situ slab- 2- PART-G | 0 |  | 0 | Cast In-situ slab- PART-C |  |  | Cast In-situ slab- PART-C |  |  |  | 0
| Qty |  | 0 | 0 | 0 | 0 | 170 | 108 | 278 |  |  |  | Cast In-situ slab- PART-C | 0 |  | 0 |  |  |  |  | 220 | 1950 | 2688 | 4638
Part K | Nos. |  | 6 | 6 | 6 | 16 | 66 | [6 empty] | 2688 | 1580 | 4268
| Qty |  | 18 | 120 | 30 | 96 | 330 | 0 | 594
Total | Nos. | 22 | 36 | 30 | 30 | 40 | 100 | 20
| Qty | 0 | 108 | 600 | 150 | 240 | 500 | 506 | 2104
Abutment wall- PART-A |  |  |  | 84 |  |  |  |  | 84
Abutment wall- PART-D |  |  |  | 500 |  |  |  |  | 500
Cast In-situ slab- 1- PART-G | [8 empty] | 0
Cast In-situ slab- 2- PART-G | [8 empty] | 0
Cast In-situ slab- PART-C | [8 empty] | 0
Cast Insitu | [8 empty] | 0
2688
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 467.1254 | 23.96%
[10 empty] | Week 2 (9 to 16) | 487.9969 | 25.03%
[10 empty] | Week 3 (17 to 24) | 487.9969 | 25.03%
[10 empty] | Week 4 (25 to 31) | 506.8807 | 25.99%
[10 empty] | Total | 1950
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 564.2099 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 725.2698 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 725.2698 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 673.2505 | 25.05% | 25.52%
[10 empty] | Total | 2688
[10 empty] | Monthly Concreting Target | 4638 | cum
|  | 12 | 12 | 12 | 12 | 0.5
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total | [10 empty] | Erection
Priority Section-1 | Nos. | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | Erection |  |  | Month Plan | Interim
| Qty | [5 empty] | 0 | [9 empty] | Track beam with nose | 28 | 8.4
Part A | Nos. | [5 empty] | 0 | [6 empty] | A | 0 |  | Track beam without nose | 41 | 12.3
| Qty | [5 empty] | 0 | [6 empty] | B | 0 |  | h-section beam | 8 | 2.4
Part B | Nos. | [5 empty] | 0 | [6 empty] | C | 0 |  | U-section beam | 9 | 2.7
| Qty | [5 empty] | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 24 | 7.2
Part H | Nos. | [5 empty] | 0 | [6 empty] | E | 0
| Qty | [5 empty] | 0 | [6 empty] | F | 73
Part C | Nos. | [12 empty] | G | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | H | 0
Part I | Nos. | [5 empty] | 0 | [6 empty] | I | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | J | 37
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 110
Priority Section-2 | Nos. | 28 | 41 | 8 | 9 | 24 | 110
| Qty | 336 | 492 | 96 | 108 | 288 | 1320
Part E | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | 20 | 24 | 5 | 6 | 18 | 73 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 240 | 288 | 60 | 72 | 216 | 876 |  |  | Week 1 (1 to 8) | 11 | 10% | 30%
Part G | Nos. | [8 empty] | Week 2 (9 to 16) | 22 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 38.5 | 35%
Part J | Nos. | 8 | 17 | 3 | 3 | 6 | 37 |  |  | Week 4 (25 to 31) | 38.5 | 35%
| Qty | 96 | 204 | 36 | 36 | 72 | 444 |  |  | Total | 110
Part K | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 28 | 41 | 8 | 9 | 24 | 110
| Qty | 336 | 492 | 96 | 108 | 288 | 1320
FTM
Track Linking
A |  | 0
B |  | 100
C |  | 0
D |  | 0
E |  | 0
F |  | 0
G |  | 0
H |  | 200
I |  | 0
J |  | 0
K |  | 0

## Nov-23 Plan (2) (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 | 35 |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 8 | 8 | 8 | 8 | 10 | 26 | 8 |  |  | Track beam with nose |  | 996 | 83 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 24 | 160 | 40 | 60 | 130 | 160 | 574 |  | Track beam without nose |  | 408 | 34
Part A | Nos. | [9 empty] | h-section beam |  | 420 | 35
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | U-section beam |  | 276 | 23
Part B | Nos. | 2 | 2 | 2 | 2 | 4 | 14 | 8 |  |  | Pre-cast Slab |  | 20 | 40
| Qty |  | 6 | 40 | 10 | 24 | 70 | 160 | 310 |  | Total: |  | 2120 | 215 | [5 empty] | Pre-cast |  |  | Cast Insitu | Total | UOM | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Part H | Nos. | 2 | 2 | 2 | 2 | 2 | 4 | [10 empty] | Month Plan | Interim |  | Qty | Cum | Cum | Cum | Nos. | 60 | 60 | 20 | 20 | 60 | 220
| Qty |  | 6 | 40 | 10 | 12 | 20 |  | 88 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 69 | 33.4486 | A | 0 | 0 | 204 | 204 | Qty | 720 | 720 | 240 | 240 | 30 | 1950
Part C | Nos. | 4 | 4 | 4 | 4 | 4 | 8 | [5 empty] | A | 0 | 0 | 0 | RCC Foundation | 460 | 222.9904 | B | 0 | 0 | 358 | 358
| Qty |  | 12 | 80 | 20 | 24 | 40 |  | 176 |  |  |  | B | 310 | 13.5 | 323.5 | Step Footing | 115 | 55.7476 | C | 16 | 192 | 0 | 192
Part I | Nos. | [11 empty] | C | 176 | 542.5 | 718.5 | Pier 1900 mm | 222 | 107.6171 | D | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | D | 0 | 0 | 0 | Pier 1600 mm | 500 | 242.3809 | E | 0 | 0 | 0 | 0
Part D | Nos. | [11 empty] | E | 0 | 0 | 0 | Pier Cap | 560 | 271.4666 | F | 0 | 0 | 150 | 150
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 0 | 6.5 | 6.5 | Track Beam with Nose | 996 | 482.8227 | G | 159 | 1218 | 452 | 1670
Priority Section-2 | Nos. | 10 | 15 | 15 | 15 | 27 | 74 | 8 |  |  |  |  | G | 510 | 12 | 522 | Track Beam without Nose | 408 | 197.7828 | H | 5 | 60 | 68 | 128
| Qty | 0 | 45 | 300 | 75 | 162 | 370 | 400 | 1352 |  |  |  | H | 88 | 264 | 352 | H - Section Beam | 420 | 203.5999 | I | 40 | 480 | 0 | 480
Part E | Nos. | [11 empty] | I | 0 | 261.5 | 261.5 | U - Section Beam | 276 | 133.7942 | J | 0 | 0 | 278 | 278
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | J | 300 | 324 | 624 | Pre-cast Slab | 20 | 9.6952 | K | 0 | 0 | 594 | 594
Part F | Nos. | [11 empty] | K | 542 | 696 | 1238 | Abutment wall- PART-A | 90 | 43.6286 | Abutment wall- PART-A |  |  | 84 | 84
| Qty |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | Abutment wall- PART-A | 90 |  | 90 | Abutment wall- PART-D | 120 | 58.1714 | Abutment wall- PART-D |  |  | 500 | 500
Part G | Nos. | 10 | 15 | 15 | 15 | 15 | [6 empty] | Abutment wall- PART-D | 120 |  | 120 | Cast In-situ slab- 1- PART-G | 0 | 0 | Cast In-situ slab- 1- PART-G |  |  |  | 0
| Qty |  | 45 | 300 | 75 | 90 | 0 |  | 510 |  |  |  | Cast In-situ slab- 1- PART-G | 0 |  | 0 | Cast In-situ slab- 2- PART-G | 529 | 256.439 | Cast In-situ slab- 2- PART-G |  |  |  | 0
Part J | Nos. | [6 empty] | 6 |  |  |  |  | Cast In-situ slab- 2- PART-G | 529 |  | 529 | Cast In-situ slab- PART-C | 0 | 0 | Cast In-situ slab- PART-C |  |  |  | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 300 | 300 |  |  |  | Cast In-situ slab- PART-C | 0 |  | 0 |  | 4785 | 2319.5849 |  | 220 | 1950 | 2688 | 4638
Part K | Nos. |  |  |  |  | 12 | 74 | 2 | [5 empty] | 2665 | 2120 | 4785
| Qty |  | 0 | 0 | 0 | 72 | 370 | 100 | 542
Total | Nos. |  | 0 | 0 | 0 | 432 | 1850 | 4000 | 6282
| Qty | 0 | 69 | 460 | 115 | 222 | 500 | 560 | 1926
Abutment wall- PART-A |  |  | 10 | 80 |  |  |  |  | 90
Abutment wall- PART-D |  |  |  | 120 |  |  |  |  | 120
Cast In-situ slab- 1- PART-G | [8 empty] | 0
Cast In-situ slab- 2- PART-G |  |  |  | 529 |  |  |  |  | 529
Cast In-situ slab- PART-C
Cast Insitu | [8 empty] | 0
2665
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 507.8491 | 23.96%
[10 empty] | Week 2 (9 to 16) | 530.5403 | 25.03%
[10 empty] | Week 3 (17 to 24) | 530.5403 | 25.03%
[10 empty] | Week 4 (25 to 31) | 551.0703 | 25.99%
[10 empty] | Total | 2120
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 559.3822 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 719.064 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 719.064 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 667.4898 | 25.05% | 25.52%
[10 empty] | Total | 2665
[10 empty] | Monthly Concreting Target | 4785 | cum
|  | 12 | 12 | 12 | 12 | 0.5
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total | [10 empty] | Erection
Priority Section-1 | Nos. | 35 | 16 | 19 | 19 | 51 | 140 | [7 empty] | Erection |  |  | Month Plan | Interim
| Qty | [5 empty] | 0 | [9 empty] | Track beam with nose | 42 | 12.6
Part A | Nos. | 12 |  | 6 | 6 | 18 | 42 | [6 empty] | A | 42 |  | Track beam without nose | 58 | 17.4
| Qty | [5 empty] | 0 | [6 empty] | B | 0 |  | h-section beam | 24 | 7.2
Part B | Nos. | [5 empty] | 0 | [6 empty] | C | 74 |  | U-section beam | 22 | 6.6
| Qty | [5 empty] | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 54 | 16.2
Part H | Nos. | 4 | 8 | 3 | 3 | 6 | 24 | [6 empty] | E | 0
| Qty | [5 empty] | 0 | [6 empty] | F | 0
Part C | Nos. | 19 | 8 | 10 | 10 | 27 | 74 | [6 empty] | G | 0
| Qty | 228 | 96 | 120 | 120 | 324 | 888 | [6 empty] | H | 24
Part I | Nos. | [5 empty] | 0 | [6 empty] | I | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | J | 0
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 140
Priority Section-2 | Nos. | 7 | 42 | 5 | 3 | 3 | 60
| Qty | 84 | 504 | 60 | 36 | 36 | 720
Part E | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [7 empty] | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 20 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 40 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 70 | 35%
Part J | Nos. | [8 empty] | Week 4 (25 to 31) | 70 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 200
Part K | Nos. | 7 | 42 | 5 | 3 | 3
| Qty | 84 | 504 | 60 | 36 | 36 | 720
Total | Nos. | 42 | 58 | 24 | 22 | 54 | 200
| Qty | 84 | 504 | 60 | 36 | 36 | 720
FTM
Track Linking
A |  | 0
B |  | 100
C |  | 0
D |  | 0
E |  | 0
F |  | 0
G |  | 0
H |  | 200
I |  | 0
J |  | 0
K |  | 0

## Top Sheet
Project: 5 MTPA Integrated Steel Plant at Vijayanagar
ELEVATED HOT METAL TRACK
Client Name: JVML |  |  |  |  | REPORT DATE | 2023-12-18 | WEATHER : | Sunny
PMC: KPMG | [21 empty] | Engineering Progress
Contractor: Rohan Builder India Pvt Ltd |  |  |  |  | REPORTING DATE | 2023-12-19 | WORKING : | Full day
OVERALL PHYSICAL PROGRESS
| Month | 2023-12-01 | [27 empty] | Actuals for the month
[18 empty] | 2023-12-31 | 2023-12-01 | 2023-12-18 | 13 | [7 empty] | Areas | PCC | RCC Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Track Beam with Nose | Track Beam without Nose | h - Section Beam | U - Section Beam | Pre-cast Slab | Erection-Track Beam with Nose | Erection-Track Beam without Nose | Erection-h - Section Beam | Erection-U - Section Beam | Erection-Pre-cast Slab | Track Laying
[18 empty] | Month | 2023-12-01 |  |  | Item Description | UOM | Scope (cum) | Completed Till date (cum) | % Complete | Scope (nos.) | Completed Till date (nos.) | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | Daily Actual | Month Actual | Item Description | Month Plan | Month Actual | Plan in Nos | PCC | CuM | 2033.9804 | 1840 | 90.46% | 581.1373 | 525.7143 | B | 10 | 0 | 0 | 0 | 0 | 64 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 28 | 109 | PCC | 0 | 109 | 0 | RCC Foundation | CuM | 13947.2941 | 11022.75 | 79.03% | 581.1373 | 459.2812 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 40 | 476 | RCC Foundation | 0 | 476 | 0 | Step Footing | CuM | 3196.2549 | 2606 | 81.53% | 581.1373 | 473.8182 | D | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 5 | 80 | Step Footing | 0 | 80 | 0 | Pier 1900 mm | CuM | 3486.8235 | 3344.3 | 95.91% | 581.1373 | 557.3833 | E | 44 | 160 | 35 | 12 | 0 | 67 | 72 | 24 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 12 | 68 | Pier 1900 mm | 0 | 68 | 0 | Pier 1600 mm | CuM | 3486.8235 | 4672 | 134% | 581.1373 | 778.6667 | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 10 | 172 | Pier 1600 mm | 0 | 172 | 0 | Pier Cap | CuM | 5230.2353 | 5660 | 108.2% | 581.1373 | 628.8889 | G | 30 | 266 | 33 | 44 | 5 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 35 | 196 | Pier Cap | 0 | 196 | 0 | Track Beam with Nose | CuM | 6973.6471 | 7728 | 110.8% | 581.1373 | 644 | H | 7 | 50 | 12 | 12 | 0 | 0 | 0 | 0 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 24 | 264 | Track Beam with Nose | 0 | 264 | 0 | Track Beam without Nose | CuM | 6973.6471 | 9105 | 130.6% | 581.1373 | 758.75 | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[14 empty] | 82.2917 |  | 12 | 204 | Track Beam without Nose | 0 | 204 | 0 | h - Section Beam | CuM | 6973.6471 | 2887.5 | 41.41% | 581.1373 | 240.625 | J | 0 | 0 | 0 | 0 | 0 | 65 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 24 | 288 | h - Section Beam | 0 | 288 | 0 | U - Section Beam | CuM | 6973.6471 | 2896.5 | 41.53% | 581.1373 | 241.375 | K | 0 | 0 | 0 | 0 | 167 | 0 | 168 | 180 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | 36 | U - Section Beam | 0 | 36 | 0 | Pre-cast Slab | CuM | 0 | 196.5 | #DIV/0! |  |  |  | 109 | 476 | 80 | 68 | 172 | 196 | 264 | 204 | 288 | 36 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[16 empty] | 0 | 2.5 | Pre-cast Slab | 0 | 2.5 | 0 | Erection-Track Beam with Nose | CuM | 0 | 388 | 0%
[16 empty] | 0 | 24 | Erection-Track Beam with Nose | 0 | 24 | 0 | Erection-Track Beam without Nose | CuM | 0 | 451 | 0%
CIVIL (RCC) PROGRESS | [15 empty] | 0 | 12 | Erection-Track Beam without Nose | 0 | 12 | 0 | Erection-h - Section Beam | CuM | 0 | 164 | 0%
Total Scope: | 69550 | cum | Month Plan: | 4037 | cum | Engineering Progress: | Scope: | 69550 | cum | [6 empty] | 0 | 10 | Erection-h - Section Beam | 0 | 10 | 0 | Erection-U - Section Beam | CuM | 0 | 173 | 0%
Actual till date: | 54088.55 | cum | Month Actual: | 1975 | cum |  | Achieved: | 69550 | cum | 48.92% | 77.77% | 15461.45 | 3865.3625 |  |  | 2 | 13 | Erection-U - Section Beam | 0 | 13 | 0 | Erection-Pre-cast Slab | CuM | 0 | 333 | 0%
Balance till date: | 15461.45 | cum | Balance FTM: | 2062 | cum |  | Balance: | 0 | cum | [6 empty] | 0 | 0 | Erection-Pre-cast Slab | 0 | 0 | 0 | Track Laying | Km | 0 | 0 | 0%
PRECAST SEGMENT ERECTION PROGRESS | [15 empty] | 0 |  | Track Laying | 0 | 0 | 0 | Abutment wall- PART-A | CuM |  | 673
Total Scope: | 3004 | nos. | Month Plan: | 245 | nos. | Engineering Progress: | Scope: | 3004 | nos. | [8 empty] | Concreting | 0 | 1895.5 | 0 | Abutment wall- PART-D | CuM |  | 595
Actual till date: | 1509 | nos. | Month Actual: | 59 | nos. |  | Achieved: | 3004 | nos. | 24.08% | 50.23% | [6 empty] | Erection | 0 | 59 | 0 | Cast In-situ slab- 1- PART-G | CuM |  | 0
Balance till date: | 1495 | nos. | Balance FTM: | 186 | nos. |  | Balance: | 0 | nos. | [12 empty] | Cast In-situ slab- 2- PART-G | CuM |  | 0
TRACK LINKING
Total Scope: | 5152 | RM | Month Plan: | 560 | RM | Engineering Progress: | Scope: | 5152 | RM
Actual till date: | 1378 | RM | Month Actual: | 470 | RM |  | Achieved: | 5152 | RM
Balance till date: | 3774 | RM | Balance FTM: | 90 | RM |  | Balance: | 0 | RM
TODAY'S PROGRESS | [15 empty] | 0 | 82 | Abutment wall- PART-A |  | 0 |  | Cast In-situ slab- PART-C | CuM |  | 862
Item Description | UOM | Today's Progress | Asking Rate | [12 empty] | 0 | 0 | Abutment wall- PART-D |  | 0
PCC | Cum | 28 | -8 | [12 empty] | 0 | 0 | Cast In-situ slab- 1- PART-G |  | 0
RCC Foundation | Cum | 40 | -37 | [12 empty] | 0 | 0 | Cast In-situ slab- 2- PART-G |  | 0
Step Footing | Cum | 5 | -6 | [12 empty] | 0 | 0 | Cast In-situ slab- PART-C |  | 0
Pier 1900 mm | Cum | 12 | -5
Pier 1600 mm | Cum | 10 | -13 | [11 empty] | Concrete | 190 | 1975 | cum |  |  |  | Concreting till date |  |  | 54088.55 | cum
Pier Cap | Cum | 35 | -15 | [11 empty] | Erection | 2 | 59 | nos. |  |  |  | Erection till date |  |  | 1509 | nos.
Track Beam with Nose | Cum | 24 | -20
Track Beam without Nose | Cum | 12 | -16
h - Section Beam | Cum | 24 | -22 | [11 empty] | Track Laying |  | 470 | Monthly actual
U - Section Beam | Cum | 0 | -3 | [13 empty] | 0 | Daily Actual
Pre-cast Slab | Cum | 0 | 0 | [13 empty] | 1378 | Completed till date
Total Concrete for the Day |  | 190 | -145
Item Description | UOM | Today's Progress | Asking Rate
Erection-Track Beam with Nose | Nos. | 0 | 0
Erection-Track Beam without Nose | Nos. | 0 | 0
Erection-h - Section Beam | Nos. | 0 | 0
Erection-U - Section Beam | Nos. | 2 | 0
Erection-Pre-cast Slab | Nos. | 0 | 0
Total Erection for the Day |  | 2 | 0
REMARKS / ISSUES OF THE DAY | [19 empty] | 1895.5
1)
2)
3)
4)
Rain Status:

## Automated DPR (hidden)
|  |  |  | REPORT DATE | 2023-12-18 | WEATHER : | Sunny
|  |  |  | REPORTING DATE | 2023-12-19 | WORKING : | Full day
Total Scope: | 69550 | cum | Month Plan: | 4036 | cum | Engineering Progress: | Scope: | 69550 | cum
Actual till date: | 54088.55 | cum | Month Actual: | 1975 | cum |  | Achieved: | 69550 | cum
Balance till date: | 15461.45 | cum | Balance FTM: | 2061 | cum |  | Balance: | 0 | cum
|  | Day Actuals | 190

## Priority (hidden)
WORK PROGRESS STATUS - ELEVATED TRACK | [12 empty] | 2023-12-01 |  | 2023-12-18
BF#5 Route- Part A, B, H, C, I, D | [15 empty] | A | B | H | C | I | D
Sr. No. | Particulars | Unit | Start Date | Finish Date | Total Scope | As on date | Balance Qty | Target FTM | Achieved FTM | Manpower | [8 empty] | G | J | F | K
1 | Foundation | Nos | 2023-04-01 | 2023-06-20 | 248 | 243 | 5 | 10 | 2 | 70 | Manual Entry- Data Not Available | [7 empty] | E
2 | Pier Cap | Nos | 2023-04-01 | 2023-08-16 | 167 | 161 | 6 | 7 | 2 | [6 empty] | Cumulative progress
| A |  |  |  | 40 | 40 | 0 | 0 | 0 |  | 6 | -6 |  | -12 |  |  | A | B | H | C | I | D | G | J | F | K | E | Total
| B |  |  |  | 17 | 16 | 1 | 4 | 2 |  | 7 | -6 |  |  |  | RCC Foundation | 800 | 536.75 | 980 | 770 | 1098 | 1075 | 1750 | 810 | 596 | 2067 | 540 | 11022.75
| H |  |  |  | 20 | 18 | 2 | 0 | 0 |  | 1 | 1 |  |  |  | Pier 1900 mm | 243.7 | 155 | 340 | 202 | 312 | 320.6 | 553 | 253 | 179 | 660 | 126 | 3344.3
| C |  |  |  | 19 | 16 | 3 | 3 | 0 |  | 3 | 0 |  |  |  | Pier 1600 mm | 194.5 | 118.5 | 276 | 260 | 455 | 160 | 355 | 656.5 | 465.5 | 1589 | 142 | 4672
| I |  |  |  | 35 | 35 | 0 | 0 | 0 | [6 empty] | Pier Cap | 531 | 451 | 670 | 479 | 855 | 784 | 352 | 519 | 554 | 328 | 137 | 5660
| D |  |  |  | 36 | 36 | 0 | 0 | 0 | [6 empty] | Step Footing | 190 | 139 | 265 | 161 | 286 | 274 | 288 | 206 | 122 | 540 | 135 | 2606
3 | Total Erection | Nos | 2023-04-01 | 2023-09-30 | 1553 | 1177 | 376 | 208 | 55 | [6 empty] | Track Beam with Nose | 911 | 541 | 552 | 756 | 996 | 1008 | 418 | 516 | 444 | 1384 | 202 | 7728
| A |  |  |  | 266 | 62 | 204 | 42 | 0 | [6 empty] | Track Beam without Nose | 0 | 552 | 1258 | 360 | 1407 | 1008 | 623 | 660 | 864 | 1941 | 432 | 9105
| B |  |  |  | 190 | 188 | 2 | 40 | 0 | [6 empty] | h - Section Beam | 478 | 342 | 336 | 372 | 447.5 | 408 | 144 | 60 | 216 | 36 | 48 | 2887.5
| H |  |  |  | 252 | 207 | 45 | 6 | 0 | [6 empty] | U - Section Beam | 455 | 168 | 228 | 384 | 461.5 | 540 | 144 | 144 | 180 | 180 | 12 | 2896.5
| C |  |  |  | 184 | 65 | 119 | 80 | 5 | [6 empty] | Pre-cast Slab | 52 | 18.5 | 11.5 | 12 | 14 | 50 | 7 | 0 | 22 | 9.5 | 0 | 196.5
| I |  |  |  | 319 | 301 | 18 | 40 | 50 | [6 empty] | PCC | 129 | 100 | 182 | 125 | 177 | 199 | 295 | 126 | 94 | 322 | 91 | 1840
| D |  |  |  | 342 | 354 | -12 | 0 | 0 | [6 empty] | Total | 3984.2 | 3121.75 | 5098.5 | 3881 | 6509 | 5826.6 | 4929 | 3950.5 | 3736.5 | 9056.5 | 1865 | 51958.55
4 | RCC Qty ( Cast In-situ) | Cum | 2023-04-01 | 2023-09-30 | 13925 | 13382.05 | 542.95 | 558 | 138 | [6 empty] | Track Laying | 288 | 0 | 0 | 0 | 470 | 620 | 0 | 0 | 0 | 0 | 0 | 1378
| A |  |  |  | 2072 | 1959.2 | 112.8 | 0 | 0
| B |  |  |  | 1492 | 1400.25 | 91.75 | 158 | 64
| H |  |  |  | 2509 | 2531 | -22 | 88 | 74
| C |  |  |  | 2286 | 1872 | 414 | 312 | 0 | [6 empty] | Monthly progress
| I |  |  |  | 2805 | 3006 | -201 | 0 | 0 | [7 empty] | A | B | H | C | I | D | G | J | F | K | E | Total
| D |  |  |  | 2761 | 2613.6 | 147.4 | 0 | 0 | [6 empty] | RCC Foundation | 0 | 0 | 50 | 0 | 0 | 0 | 266 | 0 | 0 | 0 | 160 | 476
5 | RCC Qty ( Precast) | Cum | 2023-04-01 | 2023-09-30 | 13903 | 14127 | -224 | 156 | 194.5 | [6 empty] | Pier 1900 mm | 0 | 0 | 12 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 12 | 68
| A |  |  |  | 1831 | 1896 | -65 | 0 | 2.5 | [6 empty] | Pier 1600 mm | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 167 | 0 | 172
| B |  |  |  | 1633 | 1621.5 | 11.5 | 12 | 36 | [6 empty] | Pier Cap | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 65 | 0 | 0 | 67 | 196
| H |  |  |  | 2639 | 2385.5 | 253.5 | 96 | 72 | [6 empty] | Step Footing | 0 | 0 | 12 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 35 | 80
| C |  |  |  | 1771 | 1884 | -113 | 0 | 72 | [6 empty] | Track Beam with Nose | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 168 | 72 | 264
| I |  |  |  | 3086 | 3326 | -240 | 48 | 12 | [6 empty] | Track Beam without Nose | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 24 | 204
| D |  |  |  | 2943 | 3014 | -71 | 0 | 0 | [6 empty] | h - Section Beam | 0 | 36 | 72 | 72 | 12 | 0 | 12 | 0 | 0 | 36 | 48 | 288
5 | Track Laying | RM | 2023-04-01 | 2023-10-15 | 2748 | 1378 | 1370 | 360 | 470 | [6 empty] | U - Section Beam | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 36
| A |  |  |  | 360 | 288 | 72 | 0 | 0 | bar: Total
| B |  |  |  | 300 | 0 | 300 | 100 | 0 | bar: Total
| H |  |  |  | 454 | 0 | 454 | 200 | 0 | bar: Total
| C |  |  |  | 450 | 0 | 450 | 60 | 0 | bar: Total
| I |  |  |  | 564 | 470 | 94 | 0 | 470 | bar: Total
| D |  |  |  | 620 | 620 | 0 | 0 | 0 | bar: Total
SMS#4 Route - Part G, J, F, k | [15 empty] | Pre-cast Slab | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5
Sr. No. | Particulars | Unit | Start Date | Finish Date | Total Scope | As on date | Balance | Target FTM | Achieved FTM | Manpower | [5 empty] | PCC | 0 | 10 | 7 | 0 | 0 | 18 | 30 | 0 | 0 | 0 | 44 | 109
1 | Foundation | Nos | 2023-05-01 | 2023-08-31 | 209 | 205 | 4 | 14 | 6 |  | Manual Entry- Data Not Available |  |  |  |  | Total | 2.5 | 110 | 153 | 72 | 12 | 18 | 390 | 89 | 0 | 587 | 462 | 1895.5
2 | Pier Cap | Nos | 2023-06-01 | 2023-11-30 | 75 | 43 | 32 | 4 | 1 | [6 empty] | Track Laying | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 470
| G |  |  |  | 25 | 10 | 15 | 0 | 0
| J |  |  |  | 16 | 13 | 3 | 4 | 1
| F |  |  |  | 15 | 15 | 0 | 0 | 0
| K |  |  |  | 19 | 5 | 14 | 0 | 0
3 | Total Erection | Nos | 2022-08-01 | 2023-12-30 | 1261 | 338 | 923 | 37 | 0
| G |  |  |  | 245 | 83 | 162 | 0 | 0
| J |  |  |  | 234 | 37 | 197 | 37 | 0
| F |  |  |  | 172 | 187 | -15 | 0 | 0
| K |  |  |  | 610 | 31 | 579 | 0 | 0
4 | RCC Qty ( Cast In-situ) | Cum | 2023-05-01 | 2023-12-30 | 15126 | 12843 | 2283 | 844 | 580
| G |  |  |  | 3634 | 3298 | 336 | 304 | 348
| J |  |  |  | 2704 | 2444.5 | 259.5 | 200 | 65
| F |  |  |  | 1980 | 1916.5 | 63.5 | 0 | 0
| K |  |  |  | 6808 | 5184 | 1624 | 340 | 167
5 | RCC Qty ( Precast) | Cum | 2023-05-01 | 2023-12-30 | 11592 | 7992.5 | 3599.5 | 1316 | 456
| G |  |  |  | 2123 | 1336 | 787 | 286 | 12
| J |  |  |  | 2209 | 1380 | 829 | 696 | 24
| F |  |  |  | 1598 | 1726 | -128 | 0 | 0
| K |  |  |  | 5662 | 3550.5 | 2111.5 | 334 | 420
5 | Track Laying | RM | 2023-09-01 | 2024-01-31 | 2077 | 0 | 2077 | 200 | 0
| G |  |  |  | 450 | 0 | 450 | 0 | 0
| J |  |  |  | 357 | 0 | 357 | 0 | 0
| F |  |  |  | 279 | 0 | 279 | 200 | 0
| K |  |  |  | 991 | 0 | 991 | 0 | 0
Link Route/ Return Route- Part E
Sr. No. | Particulars | Unit | Start Date | Finish Date | Total Scope | As on date | Balance | Target FTM | Achieved FTM | Manpower
1 | Foundation | Nos | 2023-08-01 | 2023-08-31 | 36 | 27 | 9 | 0 | 8 |  | Manual Entry- Data Not Available
2 | Pier Cap | Nos | 2023-09-01 | 2023-10-15 | 18 | 4 | 14 | 4 | 2
3 | Total Erection | Nos | 2023-09-20 | 2023-12-30 | 190 | 0 | 190 | 0 | 0
4 | RCC Qty ( Cast In-situ) | Cum | 2023-08-01 | 2023-12-30 | 2256 | 1080 | 1176 | 346 | 274
5 | RCC Qty ( Precast) | Cum | 2023-08-01 | 2023-12-30 | 2165 | 785 | 1380 | 48 | 188
6 | Track Laying | RM | 2023-11-15 | 2024-01-31 | 325 | 0 | 325 | 0 | 0
Target Vs. Actual
SL No | Description | Scope | UoM | Daily |  | Monthly |  | Cumulative Till Date |  | Balance
|  |  |  | Target | Achieved | Target | Achieved | Target | Achieved
1 | Excavation for foundation | 495 | Nos. | 0 | 2 | 0 | 24 | 470 | 522 | -27
2 | Pier Cap | 259 | Nos. | 0 | 1 | 0 | 5 | 124 | 208 | 51
3 | RCC Cast-in-situ & Pre-cast | 61107 | Cum | 108.7333 | 162 | 4037 | 2659 | 74263.16 | 50118.55 | 10988.45
4 | Erection-For all Beams | 2946 | Nos. | 0 | 2 | 245 | 59 | 5584.5 | 1509 | -2638.5

## Details (hidden)
[8 empty] | 2023-12-18 |  | 2023-12-01
Summary
Sr. No. | Activity | Scope in Nos. | Clear Front | Tentative Scope (Cum) | Plan | Plan | Achieved | Achieved | Balance | Today's Progress | Today's Progress | Asking Rate/Day
Month: |  |  |  |  | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01 | 2023-12-01
UOM: |  |  |  |  | No's | Cum | No's | Cum | Cum | No's | Cum | Cum
1 | Excavation | 550 | 470 | 82500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Filling | 550 | 470 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0
3 | PCC | 550 | 470 | 2079 | 0 | 0 | 24 | 109 | -109 | 2 | 28 | -8
4 | RCC Foundation | 550 | 470 | 11636 | 0 | 0 | 16 | 476 | -476 | 2 | 40 | -37
5 | Step Footing | 550 | 470 | 3050 | 0 | 0 | 14 | 80 | -80 | 1 | 5 | -6
6 | Pier 1900 mm | 550 | 294 | 3530 | 0 | 0 | 12 | 68 | -68 | 2 | 12 | -5
7 | Pier 1600 mm | 550 | 294 | 5191 | 0 | 0 | 15 | 172 | -172 | 2 | 10 | -13
8 | Pier Cap | 454 | 137 | 12354 | 0 | 0 | 5 | 196 | -196 | 1 | 35 | -15
7 | Track Beam with Nose | 600 |  | 7192.8 | 0 | 0 | 22 | 264 | -264 | 2 | 24 | -20
8 | Track Beam without Nose | 600 |  | 6888 | 0 | 0 | 17 | 204 | -204 | 1 | 12 | -16
9 | h - Section Beam | 600 |  | 5610 | 0 | 0 | 24 | 288 | -288 | 2 | 24 | -22
10 | U - Section Beam | 600 |  | 5430 | 0 | 0 | 3 | 36 | -36 | 0 | 0 | -3
11 | Pre-cast Slab | 600 |  | 1200 | 0 | 0 | 5 | 2.5 | -2.5 | 0 | 0 | 0
12 | Erection-Track Beam with Nose | 600 |  | 7192.8 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0
13 | Erection-Track Beam without Nose | 600 |  | 6888 | 0 | 0 | 11 | 0 | 0 | 0 | 0 | 0
14 | Erection-h - Section Beam | 600 |  | 5610 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0
15 | Erection-U - Section Beam | 600 |  | 5430 | 0 | 0 | 12 | 0 | 0 | 2 | 2 | 0
16 | Erection-Pre-cast Slab | 600 |  | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Track Laying | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0
64160.8
TOTAL CONCRETE> | [5 empty] | 0 |  | 1895.5 | -1895.5 | 15 | 190 | -145
Work Done in Current Month Area Wise
Section | Initial Scope (Piers) | Actual Scope | No. of Pier as per Drawing Available | Length of piers | Clear Front (Nos.) | PCC (Nos.) | PCC (Cum) | Footings (Nos.) | Footings (cum) | Spread Footing (No's) | Spread Footing (Cum) | 1.9m dia lift (Nos.) | 1.9m dia lift (Cum) | 1.6m dia lift (Nos.) | 1.6m dia lift (Cum) | Pier Cap (No's) | Pier Cap (Cum)
A | 50 | 40 | 40 | 3mtr | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
B | 33 | 28 | 28 | 3mtr | 28 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 64 | 64
H | 61 | 50 | 50 | 5.8mtrs | 50 | 2 | 7 | 2 | 50 | 2 | 12 | 2 | 12 | 0 | 0 | 0 | 0 | 74
C | 18 | 40 | 40 | 5.8mtrs | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 43 | 55 | 55 | 8mtrs | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 90 | 54 | 54 | 8mtrs to 3mtrs | 54 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E | 28 | 36 | 36 | 8mtrs | 19 | 14 | 44 | 8 | 160 | 7 | 35 | 2 | 12 | 0 | 0 | 2 | 67 | 274
G | 45 | 66 | 66 | 5.8mtrs to 8mtrs | 27 | 6 | 30 | 6 | 266 | 5 | 33 | 8 | 44 | 0.5 | 5 | 0 | 0 | 343
J | 44 | 43 | 43 | 9mtrs | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 65 | 65
F | 122 | 30 | 30 | 11.4mtrs | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
K |  | 104 | 104 | 11.4mtrs | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.5 | 167 | 0 | 0 | 0
Total | 534 | 546 | 546 |  | 470 | 24 | 109 | 16 | 476 | 14 | 80 | 12 | 68 | 15 | 172 | 5 | 196
Work Done Till Date
Section | Initial Scope (Piers) | Actual Scope | No. of Pier as per Drawing Available | Length of piers | Clear Front (Nos.) | Excavation (Nos.) | PCC (Nos.) | PCC (Cum) | Footings (Nos.) | Footings (cum) | Step Footing (No's) | Step Footing (Cum) | 1.9m dia lift (Nos.) | 1.9m dia lift (Cum) | 1.6m dia lift (Nos.) | 1.6m dia lift (Cum) | Pier Cap (No's) | Pier Cap (Cum) | Issues and concern
A | 50 | 40 | 40 | 3mtr | 40 | 40 | 40 | 129 | 40 | 800 | 40 | 190 | 40 | 243 | 40 | 194.5 | 40 | 531 | Micro palletization plant affecting 20 footings | 1958.5 | 13381.35
B | 33 | 28 | 28 | 3mtr | 28 | 26 | 28 | 100 | 27 | 536.75 | 27 | 139 | 26 | 155 | 24.75 | 118.5 | 16 | 451 | Refractory bricks material affecting 18 footings | 1400.25
H | 61 | 52 | 50 | 5.8mtrs | 50 | 50 | 41 | 182 | 41 | 980 | 42 | 265 | 52 | 340 | 50 | 276 | 18 | 670 | Drawings not available | 2531
C | 18 | 40 | 40 | 5.8mtrs | 34 | 34 | 32 | 125 | 32 | 770 | 32 | 161 | 34 | 202 | 34 | 260 | 16 | 479 | Drawings not available | 1872
I | 43 | 55 | 55 | 8mtrs | 55 | 55 | 49 | 177 | 49 | 1098 | 49 | 286 | 55 | 312 | 55 | 455 | 35 | 855 | Refractory bricks material affecting 20 footings | 3006
D | 90 | 54 | 54 | 8mtrs to 3mtrs | 54 | 54 | 54 | 199 | 54 | 1075 | 54 | 274 | 54 | 320.6 | 54 | 160 | 36 | 784 | Refractory bricks material affecting 20 footings | 2613.6 |  |  | 21
E | 28 | 36 | 36 | 8mtrs | 19 | 24 | 33 | 91 | 27 | 540 | 26 | 135 | 21 | 126 | 19 | 142 | 4 | 137 | Drawings not available | 1080
G | 45 | 62 | 63 | 5.8mtrs to 8mtrs | 27 | 56 | 55 | 295 | 53 | 1750 | 48 | 288 | 56 | 553 | 41.5 | 355 | 10 | 352 | Drawings not available | 3298
J | 44 | 43 | 43 | 9mtrs | 43 | 43 | 37 | 126 | 37 | 810 | 37 | 206 | 43 | 253 | 43.25 | 656.5 | 13 | 519 | Front is clear but not in Priority | 2444.5 | 12843
F | 122 | 30 | 30 | 11.4mtrs | 30 | 30 | 30 | 94 | 30 | 596 | 30 | 122 | 30 | 179 | 30 | 465.5 | 15 | 554 | Front is clear but not in Priority | 1916.5 |  | 21644.35
K |  | 110 | 106 |  | 90 | 110 | 85 | 322 | 85 | 2067 | 85 | 540 | 110 | 660 | 103.5 | 1589 | 5 | 328 |  | 5184
Total | 534 | 550 | 545 |  | 470 | 522 | 484 | 1840 | 475 | 11022.75 | 470 | 2606 | 521 | 3343.6 | 495 | 4672 | 208 | 5660
[5 empty] | 2023-12-01: 600; 2023-12-01: 3.8017; 2023-12-01: 21.1569; 2023-12-01: 5.5447 | 6.4177 | 9.4384 |  |  | 27.2115 | 29144.35
27304.35
Section | Initial Scope (Piers) | Actual Scope | No. of Pier as per Drawing Available | Length of piers | Clear Front (Nos.) | Excavation (Nos.) | PCC (Nos.) | PCC (Cum) | Footings (Nos.) | Footings (cum) | 1.9m dia lift (Nos.) | 1.9m dia lift (Cum) | 1.6m dia lift (Nos.) | 1.6m dia lift (Cum) | Issues and concern |  | 297
A | 50 | 40 | 40 | 3mtr | 14 | 8 | 8 | 29 | 8 | 212 | 8 | 72 | 4 | 24 | Micro palletization plant affecting 20 footings
B | 33 | 28 | 28 | 3mtr | 10 | 10 | 10 | 36 | 10 | 205.75 | 10 | 24 | 0 | 0 | Refractory bricks material affecting 18 footings
H | 61 | 40 | 0 | 5.8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drawings not available
C | 18 | 18 | 0 | 5.8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drawings not available
I | 43 | 55 | 55 | 8mtrs | 23 | 6 | 3 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | Refractory bricks material affecting 20 footings
D | 90 | 69 | 69 | 8mtrs to 3mtrs | 33 | 33 | 33 | 99 | 31 | 819.9 | 21 | 153.6 | 11 | 24.75 | Refractory bricks material affecting 20 footings
E | 28 | 36 | 36 | 8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drawings not available
G | 45 | 33 | 0 | 5.8mtrs to 8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Drawings not available
J | 44 | 41 | 41 | 9mtrs | 41 | - | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Front is clear but not in Priority
F | 122 | 108 | 30 | 11.4mtrs | 30 | 30 | 30 | 94 | 30 | 694 | 30 | 161 | 1 | 10 | Front is clear but not in Priority
Total | 534 | 468 | 264 |  | 151 | 87* | 84 | 267 | 79 | 1931.7 | 69 | 410.6 | 16 | 58.75
In Progress
In Progress

## Weekly plan (hidden)
PLAN
Activity | UoM | Scope | Current Plan FTM Nov'23 (Cum) | Current Plan FTM Nov'23 (Nos) | WEEK-1 |  | WEEK-2 |  | WEEK-3 |  | WEEK-4
[5 empty] | Nos | Cum | Nos | Cum | Nos | Cum | Nos | Cum
Civil | cum | 62550 | 4795 |  | 105 | 986 | 119 | 1160 | 118 | 1104 | 95 | 1535 |  |  | 4785 | 332
PCC | cum | 1655 | 79 | 23 | 5 | 25 | 10 | 30 | 8 | 24 |  |  |  |  | 79 | 18
RCC Foundation | cum | 10211 | 460 | 23 | 5 | 100 | 10 | 200 | 8 | 100 |  | 60 |  |  | 460 | 18
Step Footing | cum | 2550 | 115 | 23 | 5 | 25 | 10 | 50 | 8 | 40 |  | 0 |  |  | 115 | 18
Pier 1900 mm | cum | 3270 | 222 | 37 | 10 | 60 | 10 | 60 | 10 | 60 | 7 | 42 |  |  | 222 | 27
Pier 1600 mm | cum | 5546 | 500 | 100 | 25 | 125 | 25 | 125 | 25 | 125 | 25 | 125 |  |  | 500 | 75
Pier Cap | cum | 8075 | 560 | 16 | 2 | 100 | 4 | 140 | 4 | 140 | 6 | 180 |  |  | 560 | 14
Track Beam with Nose | cum | 8981 | 996 | 83 | 20 | 240 | 20 | 240 | 20 | 240 | 23 | 276 |  |  | 996 | 63
Track Beam without Nose | cum | 9585 | 408 | 34 | 5 | 60 | 5 | 60 | 10 | 120 | 14 | 168 |  |  | 408 | 29
h - Section Beam | cum | 4483 | 420 | 35 | 10 | 120 | 10 | 120 | 10 | 120 | 5 | 60 |  |  | 420 | 25
U - Section Beam | cum | 4260 | 276 | 23 | 8 | 96 | 5 | 60 | 5 | 60 | 5 | 60 |  |  | 276 | 15
Pre-cast Slab | cum | 351 | 20 | 40 | 10 | 5 | 10 | 5 | 10 | 5 | 10 | 5 |  |  | 20 | 30
Abutment wall- PART-A | cum | 491 | 90 | 1 |  | 30 |  | 30 |  | 30 |  |  |  |  | 90 | 0
Abutment wall- PART-D | cum | 830 | 120 | 1 |  |  |  | 40 |  | 40 |  | 40 |  |  | 120 | 0
Cast In-situ slab- 1- PART-G | cum | 471 | 529 | [8 empty] | 519 |  |  | 519 | 0
Cast In-situ slab- 2- PART-G | cum | 1141 | [12 empty] | 0 | 0
Cast In-situ slab- PART-C | cum | 650 |  | 1 | [10 empty] | 0 | 0
Pre-cast Segment Erection | nos. | 3004 | 200 | 0 | 34 | 0 | 49 | 0 | 49 | 0 | 68 | 0
Track Beam with Nose | nos. | 783 | 42 |  | 8 |  | 10 |  | 10 |  | 14
Track Beam without Nose | nos. | 811 | 58 |  | 10 |  | 14 |  | 14 |  | 20
h-Section Beam | nos. | 369 | 24 |  | 4 |  | 6 |  | 6 |  | 8
U-Section Beam | nos. | 420 | 22 |  | 2 |  | 6 |  | 6 |  | 8
Pre-cast Slab | nos. | 621 | 54 |  | 10 |  | 13 |  | 13 |  | 18
Elevated HMT works | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 | 0 | 75 | 0
Track linking | RM | 5152 | 300 | 300 | 75 |  | 75 |  | 75 |  | 75
ACTUALS
Activity | UoM | Scope | Current Plan FTM Sep'23 (Cum) | Current Plan FTM Sep'23 (Nos) | WEEK-1 |  | WEEK-2 |  | WEEK-3 |  | WEEK-4 |  | Total Actuals ( Nos) | Total Actuals ( Cum) | Shortfall ( Nos) | Shortfall ( Cum)
[5 empty] | Nos | Cum | Nos | Cum | Nos | Cum | Nos | Cum
Civil | cum | 62550 | 4795 | 440 | 73 | 1654.5 | 59 | 585 | 101 | 953 | 53 | 875 | 286 | 4067.5 | 154 | 727.5
PCC | cum | 1655 | 79 | 23 | 0 | 0 | 0 | 0 | 7 | 39 | 0 | 0 | 7 | 39 | 16 | 40
RCC Foundation | cum | 10211 | 460 | 23 | 3 | 75 | 1 | 45 | 5 | 167 | 3 | 113 | 12 | 400 | 11 | 60
Step Footing | cum | 2550 | 115 | 23 | 2 | 15 | 1 | 5 | 2 | 10 | 2 | 20 | 7 | 50 | 16 | 65
Pier 1900 mm | cum | 3270 | 222 | 37 | 10 | 60 | 2 | 12 | 5 | 30 | 1 | 6 | 18 | 108 | 19 | 114 | Achieved | Shortfall
Pier 1600 mm | cum | 5546 | 500 | 100 | 12 | 57 | 25 | 121 | 45 | 157 | 19 | 110 | 101 | 445 | -1 | 55 | 101 | -1 | 1600mm pier casting
Pier Cap | cum | 8075 | 560 | 16 | 1 | 65 | 1 | 66 | 2 | 130 | 5 | 208 | 9 | 469 | 7 | 91 | 125 | 50 | Precast
Track Beam with Nose | cum | 8981 | 996 | 83 | 13 | 156 | 11 | 120 | 12 | 144 | 6 | 72 | 42 | 492 | 41 | 504 | 21 | 29 | Trapezoidal
Track Beam without Nose | cum | 9585 | 408 | 34 | 15 | 180 | 13 | 156 | 13 | 156 | 2 | 24 | 43 | 516 | -9 | -108 | 9 | 7 | Pier Cap
h - Section Beam | cum | 4483 | 420 | 35 | 4 | 48 | 3 | 36 | 7 | 84 | 7 | 84 | 21 | 252 | 14 | 168
U - Section Beam | cum | 4260 | 276 | 23 | 9 | 108 | 2 | 24 | 3 | 36 | 5 | 60 | 19 | 228 | 4 | 48 | 125
Pre-cast Slab | cum | 351 | 20 | 40 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0.5 | 39 | 19.5
Abutment wall- PART-A | cum | 491 | 90 | 1 | 1 | 46 | 0 | 0 | 0 | 0 | 3 | 178 | 4 | 224 | -3 | -134
Abutment wall- PART-D | cum | 830 | 120 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 120
Cast In-situ slab- 1- PART-G | cum | 471 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 529
Cast In-situ slab- 2- PART-G | cum | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- PART-C | cum | 650 | 0 | 1 | 2 | 844 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 844 | -1 | -844
Pre-cast Segment Erection | nos. | 3004 | 200 | 0 | 29 | 0 | 24 | 0 | 25 | 0 | 0 | 0 | 78 | 0 | -78 | 0
Track Beam with Nose | nos. | 783 | 42 | 0 | 13 |  | 11 |  | 12 |  | 0 |  | 36 |  | -36
Track Beam without Nose | nos. | 811 | 58 | 0 | 15 |  | 13 |  | 13 |  | 0 |  | 41 |  | -41
h-Section Beam | nos. | 369 | 24 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
U-Section Beam | nos. | 420 | 22 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Pre-cast Slab | nos. | 621 | 54 | 0 | 1 |  | 0 |  | 0 |  | 0 |  | 1 |  | -1
Elevated HMT works | RM | 5152 | 300 | 240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Track linking | RM | 5152 | 300 | 240 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 240 | 300

## Backup
Date | Area | Name | Description | Lifts for Pier | Total Number | No's | Quantity Nos. | Track Laying RM | Trapezoidal Girder | M-10 | M-20 | M-30 | M-40 | Month | Total Concreting CUM
|  |  | Description |  | 7128 | 6523 | 1515 | 1378 | 291 | 1914 | 0 | 23881.35 | 28390.2 |  | 54185.55
2022-03-02 | A |  | PCC | [10 empty] | 2022-03-01 | 0 | Historical work
2022-03-24 | A | 43,44 | PCC |  | 2 | 2 |  |  |  | 7 |  |  |  | 2022-03-01 | 7
2022-03-25 | A | 45,46 | PCC |  | 2 | 2 |  |  |  | 7 |  |  |  | 2022-03-01 | 7
2022-03-29 | A | 65,66 | PCC |  | 3 | 3 |  |  |  | 7 |  |  |  | 2022-03-01 | 7
2022-04-01 | A | 43,44 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-04-01 | 40
2022-04-02 | A | 67,68 | PCC | 0 | 3 | 3 |  |  |  | 8 |  |  |  | 2022-04-01 | 8
2022-04-02 | F | 10A | PCC | 0 | 1 | 1 |  |  |  | 5 |  |  |  | 2022-04-01 | 5
2022-04-03 | F | 10C,10B | PCC | 0 | 2 | 2 |  |  |  | 7 |  |  |  | 2022-04-01 | 7
2022-04-04 | F | 9A,9C,9B | PCC | 0 | 3 | 3 |  |  |  | 15 |  |  |  | 2022-04-01 | 15
2022-04-05 | F | 8A,8C,8B | PCC | 0 | 3 | 3 |  |  |  | 13 |  |  |  | 2022-04-01 | 13
2022-04-05 | A | 45,46 | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-04-01 | 40
2022-04-05 | A | 43,44 | Step Footing | 0 | 2 | 2 | [5 empty] | 10 |  | 2022-04-01 | 10
2022-04-06 | F | 7A,7C,7B | PCC | 0 | 3 | 3 |  |  |  | 13 |  |  |  | 2022-04-01 | 13
2022-04-09 | A | 65,66 | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-04-01 | 40
2022-04-09 | A | 45,46 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-04-01 | 10
2022-04-09 | F | 6A,6C | PCC | 0 | 2 | 2 |  |  |  | 7 |  |  |  | 2022-04-01 | 7
2022-04-10 | F |  | RCC Foundation |  | 1 | 1 |  |  |  | 0 |  | 20 |  | 2022-04-01 | 20
2022-04-11 | F |  | PCC |  | 7 | 7 |  |  |  | 0 |  |  |  | 2022-04-01 | 0
2022-04-12 | A |  | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-04-01 | 20
2022-04-13 | F | 1900-01-07 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-04-01 | 60
2022-04-14 | F | 1900-01-05 | RCC Foundation |  | 2 | 2 | [5 empty] | 39 |  | 2022-04-01 | 39
2022-04-14 | F | 10A,10C,10B | Step Footing |  | 3 | 3 | [5 empty] | 16 |  | 2022-04-01 | 16
2022-04-14 | F | 6B,5A,5C,5B,4A,4C | PCC | 0 | 6 | 6 |  |  |  | 21 |  |  |  | 2022-04-01 | 21
2022-04-15 | F | 9B,8A | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-04-01 | 40
2022-04-15 | F | 9B,8A | Step Footing |  | 3 | 3 | [5 empty] | 10 |  | 2022-04-01 | 10
2022-04-15 | F | 4B,3A,3C | PCC | 0 | 3 | 3 |  |  |  | 13 |  |  |  | 2022-04-01 | 13
2022-04-16 | F | 8C,8B | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-04-01 | 40
2022-04-16 | F | 8C,8B | Step Footing |  | 3 | 3 | [5 empty] | 8 |  | 2022-04-01 | 8
2022-04-18 | A | 43,44 | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-19 | F | 7A | RCC Foundation | 0 | 1 | 1 | [5 empty] | 20 |  | 2022-04-01 | 20
2022-04-19 | A | 65,66 | Step Footing | 0 | 2 | 2 | [5 empty] | 10 |  | 2022-04-01 | 10
2022-04-20 | F | 7C,7B,6A | RCC Foundation | 0 | 3 | 3 | [5 empty] | 60 |  | 2022-04-01 | 60
2022-04-20 | A | 45,46 | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-20 | A | 67,68 | Step Footing | 0 | 1 | 1 | [5 empty] | 5 |  | 2022-04-01 | 5
2022-04-21 | A | 68,10A,10C,10B | Step Footing | 0 | 3 | 3 | [5 empty] | 13 |  | 2022-04-01 | 13
2022-04-21 | F | 68,10A,10C,10B | Step Footing |  | 3 | 3 | [5 empty] | 7 |  | 2022-04-01 | 7
2022-04-21 | F | 45,46 | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-22 | A | 6C | RCC Foundation | 0 | 1 | 1 | [5 empty] | 20 |  | 2022-04-01 | 20
2022-04-22 | A | 65,66 | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-23 | F | 6C,6B,5A | RCC Foundation | 0 | 3 | 3 | [5 empty] | 60 |  | 2022-04-01 | 60
2022-04-23 | F | 9A | Step Footing | 0 | 1 | 1 | [5 empty] | 5 |  | 2022-04-01 | 5
2022-04-23 | A | 67,68 | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-25 | F | 5C | RCC Foundation | 0 | 1 | 1 | [5 empty] | 19 |  | 2022-04-01 | 19
2022-04-25 | F | 9C | Step Footing | 0 | 1 | 1 | [5 empty] | 4 |  | 2022-04-01 | 4
2022-04-25 | F | 10A,10C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-26 | F | 5B,4A | RCC Foundation | 0 | 2 | 2 | [5 empty] | 38 |  | 2022-04-01 | 38
2022-04-26 | F | 9B | Step Footing | 0 | 1 | 1 | [5 empty] | 5 |  | 2022-04-01 | 5
2022-04-26 | F | 10B,9A | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-27 | F | 4C,4B | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-04-01 | 40
2022-04-27 | F | 8A,8C | Step Footing | 0 | 2 | 2 | [5 empty] | 10 |  | 2022-04-01 | 10
2022-04-27 | F | 9C,9B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-04-28 | F | 3A | RCC Foundation | 0 | 1 | 1 | [5 empty] | 20 |  | 2022-04-01 | 20
2022-04-28 | F | 7A,7C | Step Footing | 0 | 2 | 2 | [5 empty] | 10 |  | 2022-04-01 | 10
2022-04-29 | F | 7B | Step Footing | 0 | 2 | 2 | [5 empty] | 6 |  | 2022-04-01 | 6
2022-04-29 | F | 8A,8C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-04-01 | 12
2022-05-02 | F | 3C,3B | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-05-01 | 40
2022-05-02 | F | 6A | Step Footing | 0 | 2 | 2 | [5 empty] | 6 |  | 2022-05-01 | 6
2022-05-02 | F | 8B,7A | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-04 | F | 6C,6B | Step Footing | 0 | 2 | 2 | [5 empty] | 10 |  | 2022-05-01 | 10
2022-05-04 | F | 7C,7B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-05 | F | 2A | RCC Foundation | 0 | 1 | 1 | [5 empty] | 20 |  | 2022-05-01 | 20
2022-05-05 | F | 6A,6C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-06 | F | 5A | Step Footing | 0 | 1 | 1 | [5 empty] | 5 |  | 2022-05-01 | 5
2022-05-06 | F | 5A,5C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-07 | F | 2C | RCC Foundation | 0 | 1 | 1 | [5 empty] | 20 |  | 2022-05-01 | 20
2022-05-07 | F | 5C,5B | Pier 1900 mm | 0 | 1 | 1 | [5 empty] | 6 |  | 2022-05-01 | 6
2022-05-09 | F | 5B | Step Footing | 0 | 1 | 1 | [5 empty] | 5 |  | 2022-05-01 | 5
2022-05-09 | D | 6A | PCC | 0 | 1 | 1 |  |  |  | 3 |  |  |  | 2022-05-01 | 3
2022-05-10 | D | 6C | PCC | 0 | 3 | 3 |  |  |  | 8 |  |  |  | 2022-05-01 | 8
2022-05-11 | D | 6B | PCC | 0 | 1 | 1 |  |  |  | 6 |  |  |  | 2022-05-01 | 6
2022-05-11 | F | 4A,4C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 13 |  | 2022-05-01 | 13
2022-05-13 | F | 2A,1A | RCC Foundation | 0 | 2 | 2 | [5 empty] | 40 |  | 2022-05-01 | 40
2022-05-13 | F | 4B,3A | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 11 |  | 2022-05-01 | 11
2022-05-14 | F | 1C | RCC Foundation | 0 | 1 | 1 | [5 empty] | 20 |  | 2022-05-01 | 20
2022-05-14 | F | 2A,2C | Step Footing | 0 | 2 | 2 | [5 empty] | 10 |  | 2022-05-01 | 10
2022-05-14 | F | 3C,3B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 11 |  | 2022-05-01 | 11
2022-05-14 | F | 10A | Pier 1600 mm | 1 | 1 | 0.33 | [5 empty] | 10 |  | 2022-05-01 | 10
2022-05-16 | F | 2A,2C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-16 | F | 1B | Step Footing | 0 | 1 | 1 | [5 empty] | 5 |  | 2022-05-01 | 5
2022-05-17 | F | 2B,1A | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-17 | D | 7A,7C,7B,8A,8C,8B,9A,9C | PCC | 0 | 8 | 8 |  |  |  | 22 |  |  |  | 2022-05-01 | 22
2022-05-19 | F | 1C | Pier 1900 mm | 0 | 1 | 1 | [5 empty] | 6 |  | 2022-05-01 | 6
2022-05-21 | D | 9B,10A,10C,10B,11A,11C,11B,12A | PCC | 0 | 9 | 9 |  |  |  | 25 |  |  |  | 2022-05-01 | 25
2022-05-21 | A | 43,44,45 | Pier 1600 mm | 3 | 3 | 3 | [5 empty] | 8 |  | 2022-05-01 | 8
2022-05-23 | D | 6A,6C,6B | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-05-01 | 60
2022-05-24 | D | 7A,7C,7B | RCC Foundation |  | 3 | 3 | [5 empty] | 58 |  | 2022-05-01 | 58
2022-05-24 | D | 6A,6C | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-05-01 | 10
2022-05-24 | B | PC- 92A,92B,93A,93B,94A,94B | PCC | 0 | 6 | 6 |  |  |  | 29 |  |  |  | 2022-05-01 | 29
2022-05-25 | D | 6B,7A | Step Footing |  | 2 | 2 | [5 empty] | 12 |  | 2022-05-01 | 12
2022-05-26 | D | 7C | Step Footing |  | 2 | 2 | [5 empty] | 5 |  | 2022-05-01 | 5
2022-05-26 | D | 8A,8C,8B | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-05-01 | 60
2022-05-26 | A | 46 | Pier 1600 mm | 1 | 3 | 3 | [5 empty] | 16 |  | 2022-05-01 | 16
2022-05-27 | D | 9A,9C,9B | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-05-01 | 60
2022-05-27 | D | 7B,8A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-05-01 | 15
2022-05-27 | D | 1B | Pier 1900 mm | 0 | 1 | 1 | [5 empty] | 6 |  | 2022-05-01 | 6
2022-05-30 | D | 10A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-05-01 | 20
2022-05-30 | D | 8C,8B,9A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-05-01 | 15
2022-05-30 | D | 6A | Pier 1900 mm | 0 | 1 | 1 | [5 empty] | 6 |  | 2022-05-01 | 6
2022-06-01 | D | 10A,10C | RCC Foundation |  | 2 | 2 | [5 empty] | 38.5 |  | 2022-06-01 | 38.5
2022-06-01 | D | 9B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-06-01 | 5
2022-06-01 | D | 6C,6B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 11.8 |  | 2022-06-01 | 11.8
2022-06-01 | D | 6A | Pier 1600 mm | 1 | 1 | 1 | [5 empty] | 5 |  | 2022-06-01 | 5
2022-06-04 | D | 10B,11A | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-04 | D | 7A,7C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-06 | D | 11C,11B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-06 | D | 10A,10C | Step Footing |  | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-07 | D | 12A,12C | RCC Foundation |  | 2 | 2 | [5 empty] | 38.5 |  | 2022-06-01 | 38.5
2022-06-07 | D | 10B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-06-01 | 5
2022-06-07 | D | 7B | Pier 1900 mm | 0 | 1 | 1 | [5 empty] | 5.8 |  | 2022-06-01 | 5.8
2022-06-08 | D | 11A,11B,11C,12A,12C | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2022-06-01 | 25
2022-06-08 | D | 8A,8C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-09 | B | 95A,95B | PCC | 0 | 2 | 2 |  |  |  | 7 |  |  |  | 2022-06-01 | 7
2022-06-10 | D | 92A,92B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-10 | D | 8B,9A | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-11 | D | 13A | PCC | 0 | 1 | 1 |  |  |  | 3 |  |  |  | 2022-06-01 | 3
2022-06-11 | B | 93A,93B | RCC Foundation |  | 2 | 2 | [5 empty] | 38.5 |  | 2022-06-01 | 38.5
2022-06-11 | D | 12B,92A | Step Footing |  | 2 | 2 | [5 empty] | 5 |  | 2022-06-01 | 5
2022-06-11 | D | 9C,9B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 11 |  | 2022-06-01 | 11
2022-06-11 | D | 6C,6B | Pier 1600 mm | 1 | 2 | 2 | [5 empty] | 4 |  | 2022-06-01 | 4
2022-06-14 | B | 94A,94B,95A | RCC Foundation |  | 3 | 3 | [5 empty] | 59 |  | 2022-06-01 | 59
2022-06-14 | B | 92B,93A | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-06-01 | 10
2022-06-14 | D | 10A,10C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 11 |  | 2022-06-01 | 11
2022-06-15 | D | 13C,13B | PCC | 0 | 2 | 2 |  |  |  | 7 |  |  |  | 2022-06-01 | 7
2022-06-16 | D | 14A,14C | PCC | 0 | 2 | 2 |  |  |  | 7 |  |  |  | 2022-06-01 | 7
2022-06-16 | D | 10B,11A | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-17 | D | 14B,15A,15C,15B,16A,16C | PCC | 0 | 6 | 6 |  |  |  | 18 |  |  |  | 2022-06-01 | 18
2022-06-17 | B | 96A | RCC Foundation |  | 1 | 1 | [5 empty] | 19.25 |  | 2022-06-01 | 19.25
2022-06-17 | B | 93B,94A,94B | Step Footing |  | 3 | 3 | [5 empty] | 14 |  | 2022-06-01 | 14
2022-06-17 | D | 11B,11C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 11 |  | 2022-06-01 | 11
2022-06-17 | D | 7A,7C | Pier 1600 mm | 1 | 2 | 2 | [5 empty] | 4 |  | 2022-06-01 | 4
2022-06-18 | B | 96B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-18 | B | 95A,95B,96A | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-06-01 | 10
2022-06-18 | D | 12A,12C | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-20 | B | 95B,13A,13C | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-06-01 | 15
2022-06-20 | I | 6A,6C,6B | PCC | 0 | 3 | 3 |  |  |  | 9 |  |  |  | 2022-06-01 | 9
2022-06-21 | B | 92A,92B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 13 |  | 2022-06-01 | 13
2022-06-22 | D | 13A,13C,13B | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-06-01 | 60
2022-06-22 | B | 93A,93B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-22 | D | 7B | Pier 1600 mm | 1 | 1 | 1 | [5 empty] | 2 |  | 2022-06-01 | 2
2022-06-23 | B | 14A,14C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-24 | D | 14B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-06-01 | 20
2022-06-24 | D | 13A,13C,13B,14A | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2022-06-01 | 20
2022-06-27 | D | 15C,15A | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-27 | D | 14C,14B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-06-01 | 10
2022-06-27 | B | 94A,94B | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-27 | D | 8A,8C,8B | Pier 1600 mm | 1 | 3 | 3 | [5 empty] | 6 |  | 2022-06-01 | 6
2022-06-28 | D | 15B,16A | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-06-01 | 40
2022-06-28 | D | 15A,15C | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-06-01 | 10
2022-06-28 | B | 95A,95 | Pier 1900 mm | 0 | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-06-28 | D | 9A,9C | Pier 1600 mm | 1 | 2 | 2 | [5 empty] | 4 |  | 2022-06-01 | 4
2022-06-30 | D | 15C,16A | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-06-01 | 10
2022-06-30 | B | 96A,96B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-06-01 | 12
2022-07-01 | D |  | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-07-01 | 6
2022-07-01 | D | 10A, 10B, 10C | Pier 1600 mm |  | 3 | 3 | [5 empty] | 6 |  | 2022-07-01 | 6
2022-07-03 | I | 7A, 7B, 7C | PCC |  | 3 | 3 |  |  |  | 9 |  |  |  | 2022-07-01 | 9
2022-07-03 | D |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-04 | D |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-05 | I | 4B, 4C | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-07-01 | 6
2022-07-05 | D |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-05 | D | 11A,11B,11C | Pier 1600 mm |  | 3 | 3 | [5 empty] | 7 |  | 2022-07-01 | 7
2022-07-08 | I | 4A,8A,9A,10A,11A | PCC |  | 5 | 5 |  |  |  | 15 |  |  |  | 2022-07-01 | 15
2022-07-08 | D |  | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-07-01 | 40
2022-07-08 | D |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-08 | D | 12A,, 12C, 12B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-07-01 | 6
2022-07-08 | A | PC-43 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2022-07-01 | 13
2022-07-11 | I |  | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-07-01 | 40
2022-07-11 | D | PCD-13 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-07-01 | 6
2022-07-12 | I |  | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-07-01 | 60
2022-07-12 | I |  | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-07-01 | 10
2022-07-12 | D |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-12 | A |  | Pier 1600 mm |  | 2 | 2 | [5 empty] | 4 |  | 2022-07-01 | 4
2022-07-14 | I |  | RCC Foundation |  | 4 | 4 | [5 empty] | 80 |  | 2022-07-01 | 80
2022-07-14 | I |  | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-07-01 | 10
2022-07-14 | D |  | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-07-01 | 6
2022-07-15 | I |  | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-07-01 | 60
2022-07-15 | I |  | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-07-01 | 15
2022-07-15 | I |  | PCC |  | 3 | 3 |  |  |  | 9 |  |  |  | 2022-07-01 | 9
2022-07-15 | A | PC-45 | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-07-01 | 15
2022-07-16 | I |  | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2022-07-01 | 25
2022-07-16 | A |  | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2022-07-01 | 10
2022-07-18 | I |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-19 | I | PC- I8 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-07-01 | 20
2022-07-19 | I | PC- I4A, I5C | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-19 | J | PC-J 1A, 1C, 1B | PCC |  | 3 | 3 |  |  |  | 12 |  |  |  | 2022-07-01 | 12
2022-07-21 | I | PC-I12A,12B | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-07-01 | 6
2022-07-21 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-07-01 | 12
2022-07-22 | I | PC-9 | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2022-07-01 | 3
2022-07-22 | I | PC-8 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-07-01 | 5
2022-07-22 | J | PC-1-A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-07-01 | 20
2022-07-22 | I | PC-6C, 7C | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-22 | A | PC-44 | Pier Cap |  | 1 | 1 | [6 empty] | 10 | 2022-07-01 | 10
2022-07-22 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-07-01 | 12
2022-07-23 | J | PC-J 1C, 1B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-07-01 | 40
2022-07-23 | I | PC-I 11A, 10A | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-07-01 | 6
2022-07-23 | A | PC- 43-45 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-07-01 | 12
2022-07-25 | I | PC- 9A | PCC |  | 1 | 1 |  |  |  | 10 |  |  |  | 2022-07-01 | 10
2022-07-25 | I | PC- I 8A | RCC Foundation |  | 1 | 1 | [5 empty] | 50 |  | 2022-07-01 | 50
2022-07-25 | J | PC-J 1A, 1C, 1B | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-07-01 | 15
2022-07-25 | I | PC-I 6B, 7B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-25 | D |  | Track Beam without Nose |  | 2 | 1 | [6 empty] | 24 | 2022-07-01 | 24
2022-07-26 | I | PC-8A | Step Footing |  | 2 | 2 | [5 empty] | 18 |  | 2022-07-01 | 18
2022-07-26 | J | PC- 2A,3A,4A,4C | PCC |  | 4 | 4 |  |  |  | 15 |  |  |  | 2022-07-01 | 15
2022-07-26 | A | PC-46 | Pier Cap |  | 1 | 1 | [6 empty] | 16 | 2022-07-01 | 16
2022-07-27 | J | PC- 2C, 3A | PCC |  | 1 | 1 |  |  |  | 6 |  |  |  | 2022-07-01 | 6
2022-07-27 | I | PC- 5A, 5B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-27 | B | PC - 95A, 95B, 96A | Pier 1600 mm |  | 3 | 3 | [5 empty] | 10 |  | 2022-07-01 | 10
2022-07-28 | J | PC-3c 3b | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-07-01 | 6
2022-07-28 | I | PC- 9A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-07-01 | 20
2022-07-28 | I | PCI- 8a, 5a | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-28 | D | PCD- 7A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-07-01 | 14
2022-07-28 | B | PC- 95B, 96A, 96B | Pier 1600 mm |  | 3 | 3 | [5 empty] | 10 |  | 2022-07-01 | 10
2022-07-29 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-07-01 | 12
2022-07-30 | I | PCI - 10A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-07-01 | 20
2022-07-30 | I | PCI - 9A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-07-01 | 5
2022-07-30 | I | PCI - 8 A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-07-01 | 12
2022-07-30 | A | PC- 44-46 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-07-01 | 12
2022-08-01 | I | PCI-11A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-01 | I | PCI - 10A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-01 | I | PC -8M | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-01 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-02 | I | PCI- 9A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-02 | B | PC- 92A, 92B, 93A, 93B | Pier 1600 mm |  | 4 | 4 | [5 empty] | 13 |  | 2022-08-01 | 13
2022-08-02 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-03 | A | PC-67 | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-08-01 | 15
2022-08-03 | I | PCI- 11A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-03 | I | PCI- 10A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-03 | J | PCJ- 1A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-03 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-04 | I | PCI- 12A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-04 | J | PCJ- 1C, 1B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-04 | I | PCI- 14A, 14B | PCC |  | 1 | 1 |  |  |  | 6 |  |  |  | 2022-08-01 | 6
2022-08-05 | D | PCD- 8A | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2022-08-01 | 13
2022-08-05 | J | PCJ-2A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-05 | I | PCI- 15A, 15B | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-08-01 | 6
2022-08-05 | J | PCJ-4b | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2022-08-01 | 3
2022-08-05 | I | PCI- 12A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-05 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-06 | J | PCJ- 3A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-06 | J | PCJ- 2A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-06 | I | PCI- 11A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-06 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-06 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-08 | J | PCJ- 4A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-08 | J | PCJ- 3A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-08 | J | PCJ- 2B | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2022-08-01 | 3
2022-08-08 | J | PCJ- 2A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-09 | I | PCI - 14A, 14B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-08-01 | 40
2022-08-09 | J | PCJ- 4A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-09 | I | PCI- 12A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-09 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-10 | A | PC-68 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-08-01 | 14
2022-08-11 | I | PCI - 14A, 14B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-08-01 | 10
2022-08-11 | J | PCJ- 4C | RCC Foundation |  | 1 | 1 | [5 empty] | 28 |  | 2022-08-01 | 28
2022-08-11 | J | PCJ- 3A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-11 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-08-01 | 24
2022-08-12 | A | pier no 44,46 ( restrainer) | Pier 1900 mm | [9 empty] | 0.7 | 2022-08-01 | 0.7
2022-08-12 | J | PCJ- 4C | Step Footing |  | 1 | 1 | [5 empty] | 9 |  | 2022-08-01 | 9
2022-08-12 | J | PCJ- 4A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-12 | I | PCI- 16A | pcc |  | 1 | 1 |  |  |  | 3 |  |  |  | 2022-08-01 | 3
2022-08-12 | J | PCJ- 3B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-12 | I | 15a,15b | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-08-01 | 40
2022-08-13 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-13 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-08-01 | 24
2022-08-13 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-16 | D | PCD - 9A | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2022-08-01 | 13
2022-08-16 | J | PCJ- 3A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-16 | J | PCJ- 2A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-16 | I | PCI- 15A, 15B | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2022-08-01 | 10
2022-08-16 | I | PCI - 14A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-16 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-16 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-17 | J | PCJ- 3B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-17 | I | PCI- 16B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-17 | J | PCJ- 4B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-17 | J | PCJ- 4C | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-18 | J | PCJ- 3C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-18 | I | PCI-11A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-18 | J | PCJ- 4C | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-18 | J | PCJ- 4A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-18 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-18 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-18 | I | PCI- 11 | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2022-08-01 | 3
2022-08-19 | J | PCJ- 2B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-19 | J | PCJ- 3B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-19 | J | PCJ- 2C | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-19 | I | PCI- 12A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-19 | F | PCF- 10B | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-19 | F | PCF- 10C | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-19 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-20 | I | PCI- 11 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-08-01 | 20
2022-08-20 | I | PCI- 16B, 12A | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2022-08-01 | 10
2022-08-20 | J | PCJ- 2B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-20 | J | PCJ- 3B, 4B | Pier 1900 mm |  | 3 | 3 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-20 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-08-01 | 24
2022-08-22 | I | PCI- 1A, 1C, 1B, 2A, 2C, 2B, 3A, 3C, 3B | PCC |  | 9 | 9 |  |  |  | 28 |  |  |  | 2022-08-01 | 28
2022-08-22 | F | PCF- 9B | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-22 | J | PCJ- 2B | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-22 | I | PCI- 15B | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-23 | I | PCI- 11 | Step Footing |  | 1 | 1 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-23 | D | PCD-10A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-08-01 | 14
2022-08-24 | I | PCI- 12A, 15A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-24 | F | PCF- 9C, 8B | Pier 1600 mm |  | 2 | 0.66 | [5 empty] | 13 |  | 2022-08-01 | 13
2022-08-24 | B | PC- 94A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-08-01 | 14
2022-08-25 | I | PCI- 9 | RCC Foundation |  | 1 | 1 | [5 empty] | 54 |  | 2022-08-01 | 54
2022-08-25 | F | PCF- 8C | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-26 | C | PC- C8, C9, C10 | PCC |  | 3 | 3 |  |  |  | 12 |  |  |  | 2022-08-01 | 12
2022-08-26 | F | PCF-9A | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-26 | I | PCI- 9 | Step Footing |  | 2 | 2 | [5 empty] | 18 |  | 2022-08-01 | 18
2022-08-26 | I | PCI- 16A, 11A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-28 | B | PC- 94B | Pier Cap |  | 1 | 1 | [6 empty] | 8 | 2022-08-01 | 8
2022-08-28 | F | PCF- 8A | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 6 |  | 2022-08-01 | 6
2022-08-28 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-08-01 | 24
2022-08-29 | I | PCI- 1A,2C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-08-01 | 40
2022-08-29 | F | PCF- 7A, 7C | Pier 1600 mm |  | 2 | 0.66 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-29 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-29 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-30 | I | PCI- 1C, 1b | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-08-01 | 40
2022-08-30 | I | PCI- 1A,2C | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-08-01 | 10
2022-08-30 | F | PCF- 7B | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 5 |  | 2022-08-01 | 5
2022-08-30 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-08-01 | 24
2022-08-30 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-08-01 | 12
2022-08-31 | I | PCI- 2A, 2B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-08-01 | 40
2022-08-31 | I | PCI- 1C, 1B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-08-01 | 10
2022-08-31 | I | PCI-9 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-08-01 | 12
2022-08-31 | F | PCF- 6A, 6C | Pier 1600 mm |  | 2 | 0.66 | [5 empty] | 10 |  | 2022-08-01 | 10
2022-08-31 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-08-01 | 24
2022-09-01 | I | PCI- 3A, 3C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-01 | I | PCI- 2A, 2B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-02 | H | PCH- 17 | PCC |  | 3 | 3 |  |  |  | 14 |  |  |  | 2022-09-01 | 14
2022-09-02 | I | PCI- 3B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-02 | F | PCF- 10C | Pier 1600 mm |  | 2 | 0.66 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-02 | F | PCF- 6B, 5A, 5C | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2022-09-01 | 15
2022-09-02 | I | PCI- 9 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-04 | A | PC- 66 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-09-01 | 14
2022-09-04 | I | PCI- 1B, 2A, 3A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-09-01 | 15
2022-09-04 | C | PCC- 10, 9 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-05 | H | PCH- 6 | PCC |  | 2 | 2 |  |  |  | 9 |  |  |  | 2022-09-01 | 9
2022-09-05 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-06 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-07 | I | PCI- 10 | PCC |  | 1 | 1 |  |  |  | 8 |  |  |  | 2022-09-01 | 8
2022-09-07 | I | PCI-2A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-07 | F | PCF- 5A, 5B, 4B | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 18 |  | 2022-09-01 | 18
2022-09-07 | C | PCC-8 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-07 | C | PCC- 10, 9 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-07 | D |  | Track Beam with Nose |  | 1 | [7 empty] | 12 | 2022-09-01 | 12
2022-09-07 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-08 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-08 | C | PCC- 7 | PCC |  | 1 | 1 |  |  |  | 4 |  |  |  | 2022-09-01 | 4
2022-09-08 | C | PCC- 8 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-08 | H | PCH- 7 | PCC |  | 1 | 1 |  |  |  | 4 |  |  |  | 2022-09-01 | 4
2022-09-08 | H | PCH- 6 | RCC Foundation |  | 1 | 1 | [5 empty] | 30 |  | 2022-09-01 | 30
2022-09-08 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-09 | H | PCH - H9,H1 | RCC Foundation |  | 2 | 2 | [5 empty] | 36 |  | 2022-09-01 | 36
2022-09-09 | D | PCD-12A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-09-01 | 14
2022-09-09 | I | PCI - 3A,3B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-09 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-10 | A | PC-65 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-09-01 | 14
2022-09-10 | H | PCH- 7 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-10 | I | PCI- 1C, 2C | Pier 1600 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-10 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-12 | H | PCH- 17 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-12 | C | PCC- 10,9,8 | PCC |  | 3 | 3 |  |  |  | 12 |  |  |  | 2022-09-01 | 12
2022-09-12 | C | PCC- 7 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-12 | I | PCI- 13A, 13B, 11A, 10A | PCC |  | 4 | 4 |  |  |  | 20 |  |  |  | 2022-09-01 | 20
2022-09-12 | F | PCF- 4B | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-12 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-12 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-13 | D | PCD- 11A | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2022-09-01 | 13
2022-09-13 | I | PCI- 2B, 3B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-13 | I | PCI- 18A, 19A, 19B | PCC |  | 3 | 3 |  |  |  | 9 |  |  |  | 2022-09-01 | 9
2022-09-13 | H | PCH- 19, H17 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-13 | C | PCC- 10L, 9L, 8L | PCC |  | 2 | 2 |  |  |  | 12 |  |  |  | 2022-09-01 | 12
2022-09-13 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-13 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-14 | I | PCI- 1B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-14 | B | PC- 95A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-09-01 | 14
2022-09-14 | H | PCH- 19, H10 | Step Footing |  | 1 | 1 | [5 empty] | 14 |  | 2022-09-01 | 14
2022-09-14 | C | PCC- 7R | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-14 | C | PCC- 7L | PCC |  | 1 | 1 |  |  |  | 4 |  |  |  | 2022-09-01 | 4
2022-09-14 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-14 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-15 | F | PCF- 10B | Pier 1600 mm |  | 2 | 0.64 | [5 empty] | 8 |  | 2022-09-01 | 8
2022-09-15 | H | PCH- 17 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-15 | H | PCH- 10A, 10B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-15 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-15 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-16 | I | PCI- 17B, 18B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-16 | H | PCH- 17 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-16 | H | PCH- 17 | RCC Foundation |  | 1 | 1 | [5 empty] | 37 |  | 2022-09-01 | 37
2022-09-16 | H | PCH- 4 | PCC |  | 2 | 2 |  |  |  | 10 |  |  |  | 2022-09-01 | 10
2022-09-16 | H | PCH- 7 | PCC |  | 1 | 1 |  |  |  | 4 |  |  |  | 2022-09-01 | 4
2022-09-16 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-16 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-19 | I | PCI- 19A, 19B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-19 | I | PCI- 17B, 18B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-19 | H | PCH- 6 | Step Footing |  | 1 | 1 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-19 | H | PCH- 10 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-19 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-19 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-19 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-20 | I | PCI- 13B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-20 | I | PCI- 19A, 19B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-20 | H | PCH- 11 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-20 | H | PCH- 19, | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-20 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-20 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-21 | I | PCI- 10A, 13A | RCC Foundation |  | 2 | 2 | [5 empty] | 90 |  | 2022-09-01 | 90
2022-09-21 | I | PCI- 19A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-21 | H | PCH- 7 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-21 | H | PCH- 11 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-21 | H | PCH- 19 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-21 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-21 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-22 | I | PCI - 10A, 13A | Step Footing |  | 2 | 2 | [5 empty] | 22 |  | 2022-09-01 | 22
2022-09-22 | B | PCB - 95A | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-09-01 | 15
2022-09-22 | H | PCH - 7 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-22 | H | PCH - 10 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-22 | H | PCH - 11 | RCC Foundation |  | 1 | 1 | [5 empty] | 27 |  | 2022-09-01 | 27
2022-09-22 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-22 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-23 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-23 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-23 | H | PCH- 3 | PCC |  | 3 | 3 |  |  |  | 16 |  |  |  | 2022-09-01 | 16
2022-09-23 | H | PCH- 6 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-23 | H | PCH- 11 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-23 | A | PC- 69,70,71,72,73,74,75,76 | PCC |  | 9 | 9 |  |  |  | 34 |  |  |  | 2022-09-01 | 34
2022-09-24 | D | PCD- 23A, 23C, 23B | PCC |  | 3 | 3 |  |  |  | 9 |  |  |  | 2022-09-01 | 9
2022-09-24 | B | PC- 96B | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-09-01 | 15
2022-09-24 | H | PCH- 6, 7 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-24 | H | PCH- 4 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-26 | D | PCD- 14b | Pier 1600 mm |  | 2 | 2 | [5 empty] | 4 |  | 2022-09-01 | 4
2022-09-26 | H | PCH- 9a, 9b | PCC |  | 2 | 2 |  |  |  | 12 |  |  |  | 2022-09-01 | 12
2022-09-26 | H | PCh- 4a, 6a | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-26 | H | PCH- 4B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-26 | H | PCH- 6B | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-26 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-27 | H | PCH-4 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-09-01 | 10
2022-09-27 | H | PCH-3A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-27 | H | PCH-11A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-27 | H | PCH-13 | PCC |  | 2 | 2 |  |  |  | 12 |  |  |  | 2022-09-01 | 12
2022-09-28 | H | PCH-3B | RCC Foundation |  | 1 | 1 | [5 empty] | 27 |  | 2022-09-01 | 27
2022-09-28 | H | PCH-3A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-09-01 | 5
2022-09-28 | H | PCH-11A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-09-01 | 6
2022-09-28 | A | PC- 69, 70 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-28 | D | PCD- 23A, 23B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-09-01 | 40
2022-09-28 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-28 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-28 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-09-01 | 24
2022-09-29 | D | PCD-23A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-09-01 | 20
2022-09-29 | H | PCH-3B | Step Footing |  | 1 | 1 | [5 empty] | 9 |  | 2022-09-01 | 9
2022-09-29 | H | PCH-6 | Pier 1900 mm |  | 1 | 2 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-29 | A | PCA-69,70 | Step Footing |  | 3 | 3 | [5 empty] | 12 |  | 2022-09-01 | 12
2022-09-29 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-29 | C | PCC-C1,C2 | PCC |  | 2 | 2 |  |  |  | 18 |  |  |  | 2022-09-01 | 18
2022-09-30 | D | PC- 7B, 7C | Pier Cap |  | 1 | 1 | [6 empty] | 28 | 2022-09-01 | 28
2022-09-30 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-30 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-09-30 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-09-01 | 12
2022-10-01 | H | PCH - 9A, 9B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-01 | H | PCH - 11B, 4A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-01 | C | PCC-2, 5, 4 | PCC |  | 2 | 2 |  |  |  | 10 |  |  |  | 2022-10-01 | 10
2022-10-01 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-01 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-01 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-03 | D | PCD- 13B | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-03 | D | PCD- 23A, 23C, 23B | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-10-01 | 15
2022-10-03 | H | PCH- 9a, 9b | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-03 | H | PCH- 9B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-03 | H | PCH- 4A, 4B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-04 | H | PCH- 15A | RCC Foundation |  | 1 | 1 | [5 empty] | 49 |  | 2022-10-01 | 49
2022-10-04 | H | PCH- 15 B, 9A | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-04 | H | PCH- 4 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-10-01 | 6
2022-10-04 | A | PC- 72, 73 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-04 | D | PCD- 23A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-10-01 | 6
2022-10-06 | A | PCA-71 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-06 | C | PCC-C1 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-06 | H | PCH-H15 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-06 | H | PCH-3 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-10-01 | 6
2022-10-06 | B | PCB-96A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-10-01 | 14
2022-10-06 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-06 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-06 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-07 | A | PC- 75, 74 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-07 | A | PC- 71, 72 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-07 | C | PCC- 2 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-07 | C | PCC- 1 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-07 | D | PCD- 23C, 23B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-07 | D | PCD- 15B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 3 |  | 2022-10-01 | 3
2022-10-07 | D | PCD- 14B | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2022-10-01 | 13
2022-10-07 | D |  | Track Beam with Nose |  | 1 | [7 empty] | 12 | 2022-10-01 | 12
2022-10-07 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-07 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-09 | I | PCI- 2B,2A,3A | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 18 |  | 2022-10-01 | 18
2022-10-09 | C | PCC- C1 | RCC Foundation |  | 1 | 1 | [5 empty] | 38 |  | 2022-10-01 | 38
2022-10-09 | C | PCC- C2 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-09 | A | PC- 76 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-09 | A | PC- 75, 74 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-09 | A | PC- 71, 72 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-09 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-09 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-09 | H | PCH-5 | PCC |  | 1 | 1 |  |  |  | 5 |  |  |  | 2022-10-01 | 5
2022-10-10 | A |  | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-10 | A |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-10 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-10 | D |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-10-01 | 36
2022-10-10 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-11 | I | PCI- 3B, 3C, 2C | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 18 |  | 2022-10-01 | 18
2022-10-11 | C | PCC- 1 | Step Footing |  | 3 | 3 | [5 empty] | 13 |  | 2022-10-01 | 13
2022-10-11 | C | PCC- 2, 10 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-11 | A | PC- 73, 74 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-11 | D |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-10-01 | 36
2022-10-11 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-12 | C | PCC- 9, 8 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-12 | D | PCD- 16B | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-12 | I | PCI- 1A, 1B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-12 | K | PCK- 19A, 19B | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-10-01 | 6
2022-10-12 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-12 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-12 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-13 | C | PCC- 5B,6,7 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-10-01 | 60
2022-10-13 | C | PCC- 4 | PCC |  | 2 | 2 |  |  |  | 7 |  |  |  | 2022-10-01 | 7
2022-10-13 | K | PCK- 19C | PCC |  | 2 | 2 |  |  |  | 5 |  |  |  | 2022-10-01 | 5
2022-10-13 | I | PCI- 1, 4, 4A | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 18 |  | 2022-10-01 | 18
2022-10-13 | D |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-10-01 | 36
2022-10-13 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-14 | D | PC- 15A | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-14 | I | PCI-5 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-14 | A | PC-75 | Pier 1900 mm |  | 1 | [6 empty] | 3 |  | 2022-10-01 | 3
2022-10-14 | H | PCH-15A, 15B | PCC |  | 3 | 3 |  |  |  | 12 |  |  |  | 2022-10-01 | 12
2022-10-14 | K | PCK- 18A | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-10-01 | 6
2022-10-14 | C | PCC- 5A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-14 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-16 | I | PCI- 1, 6,7, 5B | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-16 | C | PCC- 4A, 4B, 6 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-10-01 | 60
2022-10-16 | C | PCC- 10, 9, 8, 7, 6 | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2022-10-01 | 25
2022-10-16 | H | PCH- 5 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-16 | A | PC- 75,76 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-16 | D |  | Track Beam with Nose |  | 1 | [7 empty] | 12 | 2022-10-01 | 12
2022-10-16 | D |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-10-01 | 36
2022-10-16 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-17 | K | PCK- 19A, 19B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-17 | H | PCH- 9A, 9B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-17 | I | PCI- 1A, 1B,2,3,7 | Pier 1600 mm |  | 5 | 2.5 | [7 empty] | 2022-10-01 | 0
2022-10-17 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-18 | I | PCI- 1A, 1B, 2A, 2B, 4B | Pier 1600 mm |  | 5 | 2.5 | [5 empty] | 25 |  | 2022-10-01 | 25
2022-10-18 | H | PCH- 5, 13 | RCC Foundation |  | 2 | 2 | [5 empty] | 49 |  | 2022-10-01 | 49
2022-10-18 | C | PCC-4A, 4B, 5A, 5B, 6B | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2022-10-01 | 25
2022-10-18 | A | PC- 69, 70 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 4 |  | 2022-10-01 | 4
2022-10-18 | K | PC- 5A,5C, 5B | PCC |  | 3 | 3 |  |  |  | 12 |  |  |  | 2022-10-01 | 12
2022-10-19 | D | PCD- 23A, 23C, 23B | Pier 1600 mm |  | 4 | 4 | [5 empty] | 15 |  | 2022-10-01 | 15
2022-10-19 | H | PCH- 1A, 1B, 2A, 2B | PCC |  | 5 | 5 |  |  |  | 15 |  |  |  | 2022-10-01 | 15
2022-10-19 | H | PCH-9, 15 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-19 | K | PCK- 19C | RCC Foundation |  | 1 | 1 | [5 empty] | 29 |  | 2022-10-01 | 29
2022-10-19 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-19 | D |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-10-01 | 36
2022-10-19 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-20 | A | PC- 71, 72 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 4 |  | 2022-10-01 | 4
2022-10-20 | H | PCH- 13 | RCC Foundation |  | 1 | 1 | [5 empty] | 29 |  | 2022-10-01 | 29
2022-10-20 | H | PCH- 5 | Step Footing |  | 2 | 2 | [5 empty] | 15 |  | 2022-10-01 | 15
2022-10-20 | H | PCH- 15 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-20 | H | PCH-8 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2022-10-01 | 12
2022-10-20 | K | PCK- 18A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-20 | K | PCK- 18C, 18B | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-10-01 | 6
2022-10-21 | K | PCK- 17A, 17C, 17B | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2022-10-01 | 12
2022-10-21 | K | PCK- 18C | RCC Foundation |  | 1 | 1 | [5 empty] | 29 |  | 2022-10-01 | 29
2022-10-21 | K | PCK- 19A, 19C | Step Footing |  | 3 | 3 | [5 empty] | 13 |  | 2022-10-01 | 13
2022-10-21 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-21 | D |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-10-01 | 36
2022-10-24 | I | PC- 6A, 4 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-24 | D | PC- 8B | Pier Cap |  | 1 | 1 | [6 empty] | 28 | 2022-10-01 | 28
2022-10-24 | H | PCH-13 | Step Footing |  | 2 | 2 | [5 empty] | 15 |  | 2022-10-01 | 15
2022-10-24 | C | PCC- 2 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-24 | C | PCC- 1 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-24 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-24 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-25 | I | PCI- 5,6 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-25 | C | PCC- 2 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-25 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-25 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-26 | H | PCH-8A,8B | RCC Foundation |  | 2 | 2 | [5 empty] | 41 |  | 2022-10-01 | 41
2022-10-26 | H | PCH-13 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-10-01 | 6
2022-10-26 | C | PCC-2 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-26 | K | PCK-17 | RCC Foundation |  | 1 | 1 | [5 empty] | 28 |  | 2022-10-01 | 28
2022-10-26 | D | PCD-23 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-26 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-26 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-27 | D | PCD-23 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-27 | H | PCH-8C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-10-01 | 20
2022-10-27 | H | PCH-8 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2022-10-01 | 10
2022-10-27 | C | PCC-4A, 4B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-27 | K | PCK-17 | Step Footing |  | 2 | 2 | [5 empty] | 9 |  | 2022-10-01 | 9
2022-10-27 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-27 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-27 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-28 | K | PCK-17,18 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-10-01 | 60
2022-10-28 | H | PCH-8 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-10-01 | 5
2022-10-28 | C | PCC-6 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-28 | H |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-28 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-28 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-29 | I | PCI-4 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-29 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-29 | D |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-10-01 | 24
2022-10-29 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-31 | H | PCH-1,2,7 | RCC Foundation |  | 3 | 3 | [5 empty] | 74 |  | 2022-10-01 | 74
2022-10-31 | H | PCH-3 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 15 |  | 2022-10-01 | 15
2022-10-31 | K | PCK-16B,16C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-10-01 | 40
2022-10-31 | K | PCK-17B,17C,18B | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-10-01 | 15
2022-10-31 | I | PCI-2A,2B | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2022-10-01 | 30
2022-10-31 | C | PCC-5,6 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-10-01 | 12
2022-10-31 | A | PCA-69 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-10-31 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-10-01 | 12
2022-11-01 | K | PCK-16 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-01 | H | PCH-1,2,7 | Step Footing |  | 4 | 4 | [5 empty] | 21 |  | 2022-11-01 | 21
2022-11-01 | H | PCH-7 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-01 | I | PCI-2A,8 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-01 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-02 | I | PCI-8 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-02 | D |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-02 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-02 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-02 | H | PCH-1,2 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-02 | H | PCH-7 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-02 | C | PCC-7 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-02 | A | PCA-74 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-03 | H | PCH-1,2 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-03 | K | PCK-16B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-03 | C | PCC-18A, 18B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-03 | I | PCI-2B | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-11-01 | 15
2022-11-03 | D |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-03 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-03 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-04 | A | PCA-71 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-04 | J | PCJ 5,6 | RCC Foundation |  | 2 | 2 | [5 empty] | 46 |  | 2022-11-01 | 46
2022-11-04 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-04 | B |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-04 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-06 | A | PC- 70 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-06 | I | PCI- 3 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-06 | J | PCJ- 5B, 6A | RCC Foundation |  | 2 | 2 | [5 empty] | 50 |  | 2022-11-01 | 50
2022-11-06 | J | PCJ- 5A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-06 | C | PCC-8 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-06 | H | PCH- 13 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 15 |  | 2022-11-01 | 15
2022-11-06 | J | PCJ- 9,10,11,12 | PCC |  | 12 | 12 |  |  |  | 36 |  |  |  | 2022-11-01 | 36
2022-11-06 | D |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-06 | I |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-06 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-07 | J | PCJ- 9,10,11,12 | PCC |  | 10 | 10 |  |  |  | 31 |  |  |  | 2022-11-01 | 31
2022-11-07 | J | PCJ- 5B, 6C | RCC Foundation |  | 2 | 2 | [5 empty] | 69 |  | 2022-11-01 | 69
2022-11-07 | J | PCJ- 5C, 5A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-11-01 | 15
2022-11-07 | I | PCI- 8A | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-07 | H | PCH- 8A, 8B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-07 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-07 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-07 | I |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-08 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-08 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-08 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-08 | A | PC- 72 | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-11-01 | 15
2022-11-08 | I | PCI- 1B | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-11-01 | 15
2022-11-08 | I |  | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-08 | H | PCH-1 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 16 |  | 2022-11-01 | 16
2022-11-08 | J | PCJ- 5C,6B,7A | Step Footing |  | 3 | 3 | [5 empty] | 29 |  | 2022-11-01 | 29
2022-11-08 | K | PCk- 15 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-09 | J | PCJ- 7C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-09 | J | PCJ-7 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-09 | K | PCK-15, 16 | PCC |  | 3 | 3 |  |  |  | 10 |  |  |  | 2022-11-01 | 10
2022-11-09 | I | PCI- 17 | PCC |  | 1 | 1 |  |  |  | 5 |  |  |  | 2022-11-01 | 5
2022-11-09 | H | PCH- 7, 8 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-11-01 | 18
2022-11-09 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-09 | D |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-10 | J | PCJ- 10A,11A,11D | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-11-01 | 60
2022-11-10 | I | PCI- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-10 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-10 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-11 | J | PCJ- 9B, 9C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-11 | J | PCj- 7A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-11 | K | PCK- 14 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-11 | H | PCH- 7C, 5A, 5B, 5C | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2022-11-01 | 24
2022-11-11 | A | PC- 74 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-11 | A | PC- 76 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 2 |  | 2022-11-01 | 2
2022-11-11 | I | Pci- 2 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-11 | I | PCI- 9 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-11 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-11 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-11 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-13 | J | PCJ- 12, 10 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-13 | K | PCK- 14 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-13 | H | PCH- H1, H2 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-13 | C | PCC-9, 10 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-13 | A | PC- 73 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-13 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-13 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-13 | D |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-14 | K | PCK-14 | RCC Foundation |  | 1 | 1 | [5 empty] | 28 |  | 2022-11-01 | 28
2022-11-14 | K | PCK-14B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-14 | D | PCD- 23A | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-14 | I | PCI- 8A, 8B, 8C | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 18 |  | 2022-11-01 | 18
2022-11-14 | I | PCI- 10A, 10B, 19A | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-11-01 | 18
2022-11-14 | I |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-14 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-14 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-15 | J | PCJ- 10C, 11A, 11,B | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-11-01 | 60
2022-11-15 | J | PCJ- 10B, 10A, 12 | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-15 | A | PC- 76 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2022-11-01 | 13
2022-11-15 | K | PCK- 14 | Step Footing |  | 2 | 2 | [5 empty] | 7 |  | 2022-11-01 | 7
2022-11-15 | I | PCI- 10C, 19A, 19B | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-11-01 | 18
2022-11-15 | D | PCD- 17, 18, 19, 20 | PCC |  | 12 | 12 |  |  |  | 51 |  |  |  | 2022-11-01 | 51
2022-11-15 | I |  | Track Beam without Nose |  | 3 | [7 empty] | 36 | 2022-11-01 | 36
2022-11-15 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-15 | B |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-16 | I | PCI- 18B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-16 | I | PCI- 16B, 13A, 13B | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-11-01 | 18
2022-11-16 | I |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-16 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-16 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-17 | I | PCI- 18B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-17 | I | PCI- 19B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-11-01 | 6
2022-11-17 | I | PCI- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-17 | I | PCI- 12, 13 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-17 | J | PCJ- 11A, 9C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-17 | J | PCJ- 11C, 10B, J9, J12 | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-17 | J | PCJ- 9D | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-11-01 | 6
2022-11-17 | A | PC-75 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-17 | G | PCG- | PCC |  | 7 | 7 |  |  |  | 35 |  |  |  | 2022-11-01 | 35
2022-11-17 | C | PCC- 3 | PCC |  | 2 | 2 |  |  |  | 15 |  |  |  | 2022-11-01 | 15
2022-11-17 | I |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-17 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-17 | B |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-18 | J | PCJ-9 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-18 | J | PCJ- 11 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-18 | J | PCJ- 5 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-11-01 | 18
2022-11-18 | I | PCI- 18 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-11-01 | 6
2022-11-18 | I |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-18 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-18 | A |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-18 | A | PC-43,45 to PC- 44, 46 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2022-11-01 | 0 | 32
2022-11-18 | A | PC-43,45 to PC- 44, 46 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2022-11-01 | 0 | 120
2022-11-18 | A | PC-43,45 to PC- 44, 46 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2022-11-01 | 0 | 55
2022-11-20 | A | PC-43,45 to PC- 44, 46 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2022-11-01 | 0 | 31
2022-11-20 | D | PCD- 17A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-20 | I | PCI- 3B | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-20 | J | PCJ- 6 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2022-11-01 | 24
2022-11-20 | J | PCJ- 9 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-21 | B |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-21 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-21 | A |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-21 | D |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-22 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-22 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-22 | D | PCD-9B | Pier Cap |  | 1 | 1 | [6 empty] | 28 | 2022-11-01 | 28
2022-11-22 | I | PCI- 4B | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-22 | D | PCD- 17B, 17C, 18C | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-11-01 | 60
2022-11-22 | J | PCJ- 7 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2022-11-01 | 24
2022-11-23 | D | PCD- 18A, 18B, 19A, 19B | RCC Foundation |  | 4 | 4 | [5 empty] | 80 |  | 2022-11-01 | 80
2022-11-23 | I | PCI- 17A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-23 | J | PCJ- 9 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2022-11-01 | 24
2022-11-23 | H | PCH-17 | Pier 1600 mm |  | 3 | 3 | [5 empty] | 15 |  | 2022-11-01 | 15
2022-11-23 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-23 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-23 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-24 | D | PCD- 20A, 20B, 19C | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-11-01 | 60
2022-11-24 | D | PCD- 17C, 18C, 17A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-11-01 | 15
2022-11-24 | I | PCI- 17A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-24 | J | PCJ-10A, 10B, 11A, 11B | Pier 1900 mm |  | 4 | 4 | [5 empty] | 25 |  | 2022-11-01 | 25
2022-11-24 | H | PCH- 15,13 | Pier 1600 mm |  | 4 | 4 | [5 empty] | 25 |  | 2022-11-01 | 25
2022-11-24 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-24 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-24 | D |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-24 | A |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-25 | D | PCD- 20C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-25 | D | PCD- 17B, 18A, 20A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-11-01 | 15
2022-11-25 | I | PCI-17A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-11-01 | 6
2022-11-25 | H | PCH- 13 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2022-11-01 | 5
2022-11-25 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-25 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-25 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-27 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-27 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-27 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-27 | F |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-27 | D | PCD- 11B | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2022-11-01 | 30
2022-11-27 | G |  | PCC |  | 6 | 6 |  |  |  | 24 |  |  |  | 2022-11-01 | 24
2022-11-27 | D | PCD- 18B, 19A, 19B,20 C, 20 B | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2022-11-01 | 25
2022-11-27 | C | PCC- 3 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-11-01 | 40
2022-11-27 | J | PCJ- 10C, 10D | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-27 | D | PCD- 17A, 17C | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-27 | H | PCH- 15, 11 | Pier 1600 mm |  | 5 | 5 | [5 empty] | 25 |  | 2022-11-01 | 25
2022-11-28 | G | PCG- 9 | RCC Foundation |  | 2 | 2 | [5 empty] | 45 |  | 2022-11-01 | 45
2022-11-28 | D | PCD- 17B, 20A, 20B, 20C | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2022-11-01 | 24
2022-11-28 | C | PCC-11 | PCC |  | 2 | 2 |  |  |  | 10 |  |  |  | 2022-11-01 | 10
2022-11-28 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-28 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-28 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-29 | J | PCJ- 12B, 11B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-29 | G | PCG- 7A, Ab, 6A | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-11-01 | 60
2022-11-29 | H | PCH- 9A, 9B, 8A, 8B | Pier 1600 mm |  | 5 | 5 | [5 empty] | 25 |  | 2022-11-01 | 25
2022-11-29 | I | PCI-3A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-29 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-11-01 | 12
2022-11-29 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-29 | D |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2022-11-01 | 36
2022-11-30 | I | PCI-4A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-11-01 | 14
2022-11-30 | D | PCD- 10B | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2022-11-01 | 30
2022-11-30 | D | PCD- 18,19 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-11-01 | 12
2022-11-30 | G | PCG- 6B | RCC Foundation |  | 1 | [6 empty] | 20 |  | 2022-11-01 | 20
2022-11-30 | C | PCC- 11B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-11-01 | 20
2022-11-30 | H | PCH- 7 | Pier 1600 mm |  | 5 | 5 | [5 empty] | 25 |  | 2022-11-01 | 25
2022-11-30 | G |  | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-11-01 | 10
2022-11-30 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-11-30 | F |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-11-01 | 24
2022-12-01 | C | PCC- 11A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-01 | G |  | Step Footing |  | 1 | 2 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-01 | B |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-01 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-01 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-02 | H | PCH- 3B,3C,4A, 6A, 6B | Pier 1600 mm |  | 5 | 5 | [5 empty] | 25 |  | 2022-12-01 | 25
2022-12-02 | J | PCJ- 12A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-02 | C | PCC- 11A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-02 | G | PCG-6A, 7A, 7B | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-12-01 | 15
2022-12-02 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-02 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-02 | B |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-02 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-04 | D | PCD- 12B | Pier Cap |  | 1 | 1 | [6 empty] | 29 | 2022-12-01 | 29
2022-12-04 | D | PCD- 18,19 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-04 | D | PCD-16 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-04 | I | PCI-15 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-04 | H | PCH- 4 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-04 | F |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-04 | D |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-04 | I |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-04 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2022-12-01 | 2.5
2022-12-05 | D | PCD- 13A | Pier Cap |  | 1 | 1 | [6 empty] | 31 | 2022-12-01 | 31
2022-12-05 | D | PCD-15 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-05 | D | PCD-18B, 19B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-05 | C | PCC- 11 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-05 | H | PCh- 5 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-05 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-05 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-06 | I | PCI- 10, 17A, 17B, 18 | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-06 | C | PCC- C11A, C3A, 3B | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-12-01 | 18
2022-12-06 | H | PCH- 1, 2, 8, 10 | Pier 1600 mm |  | 4 | 4 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-06 | E | PCE- 13, 14, 15 | PCC |  | 7 | 7 |  |  |  | 18 |  |  |  | 2022-12-01 | 18
2022-12-07 | H | PCH- 3 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-07 | J | PCJ- 8 | PCC |  | 3 | 3 |  |  |  | 14 |  |  |  | 2022-12-01 | 14
2022-12-07 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-07 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-08 | G | PCG- 6,7 | Pier 1900 mm |  | 4 | 1 | [5 empty] | 24 |  | 2022-12-01 | 24
2022-12-08 | E | PCE- 13A, 13B, 14A | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-12-01 | 60
2022-12-08 | H | PCH- 3,2 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-08 | I | PCI- 12, 13 | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-08 | D | PCD- 16B | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2022-12-01 | 30
2022-12-08 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-08 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-08 | F |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-08 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-09 | E | PCE- 14, 15 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-12-01 | 60
2022-12-09 | E | PCE- 13 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-09 | B |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-09 | D |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-09 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-11 | D | PCD-15 | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2022-12-01 | 30
2022-12-11 | G | PCG-6,7 | Pier 1900 mm |  | 2 | 0.5 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-11 | D | PCD- 22 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-12-01 | 6
2022-12-12 | E | PCE- 15, 14 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-12-01 | 15
2022-12-12 | E | PCE- 13 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-12 | K |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-12 | A |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-13 | J | PCJ-8A,8B,8C | RCC Foundation |  | 3 | 3 | [5 empty] | 77 |  | 2022-12-01 | 77
2022-12-13 | E | PCE-13 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-13 | E | PCE-14 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-13 | I | PCI-18,17,13 | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 15 |  | 2022-12-01 | 15
2022-12-13 | D | PCD-21,22 | PCC |  | 4 | 4 |  |  |  | 16 |  |  |  | 2022-12-01 | 16
2022-12-13 | J |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-13 | D |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-13 | I |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-14 | D | PCD- 14 | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2022-12-01 | 30
2022-12-14 | D | PCD- 17, 18, 19 | Pier 1600 mm |  | 3 | 3 | [5 empty] | 8 |  | 2022-12-01 | 8
2022-12-14 | D | PCD- 22A,22B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-14 | I | PCI-19 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-14 | E | PCE- 15A, 15B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-14 | H | PCH- 1 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-14 | J |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-14 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-14 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2022-12-01 | 1
2022-12-15 | D |  | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-15 | D |  | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-15 | J | PCJ- 8 | Step Footing |  | 4 | 4 | [5 empty] | 23 |  | 2022-12-01 | 23
2022-12-15 | G | PCG- 8, 9 | PCC |  | 4 | 4 |  |  |  | 22 |  |  |  | 2022-12-01 | 22
2022-12-15 | H | PCH-10, 12, 14, 16, 18 | PCC |  | 5 | 5 |  |  |  | 14 |  |  |  | 2022-12-01 | 14
2022-12-15 | I |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 22 | 2022-12-01 | 22
2022-12-15 | B |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 10 | 2022-12-01 | 10
2022-12-15 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 7 | 2022-12-01 | 7
2022-12-15 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 9 | 2022-12-01 | 9
2022-12-16 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 38 | 2022-12-01 | 38
2022-12-16 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 27 | 2022-12-01 | 27
2022-12-16 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 15 | 2022-12-01 | 15
2022-12-16 | J | PCJ- 8 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2022-12-01 | 24
2022-12-16 | D | PCD- 21 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-16 | D | PCD- 21 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-16 | D | PCD- 17, 18, 19 | Pier 1600 mm |  | 3 | 3 | [5 empty] | 8 |  | 2022-12-01 | 8
2022-12-16 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 0.5 | 2022-12-01 | 0.5
2022-12-18 | D | PCD-21,22 | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-18 | I | PCI- 17 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-12-01 | 14
2022-12-18 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-18 | B |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 30 | 2022-12-01 | 30
2022-12-18 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-18 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-18 | D |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2022-12-01 | 1.5
2022-12-19 | D | PCD- 21, 22 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2022-12-01 | 18
2022-12-19 | K | PCK- 18 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-19 | H | PCH - 10, 12 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-19 | J | PCJ- 6 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-19 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-19 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-19 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-19 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2022-12-01 | 1
2022-12-20 | D | PCD-21 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-20 | H | PCH - 10, 12 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-20 | I | PCI- 12 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2022-12-01 | 35
2022-12-20 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-20 | B |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-20 | B |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-20 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-21 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-21 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-21 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1.5 | 2022-12-01 | 1.5
2022-12-22 | H | PCH- 14 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-22 | G | PCG- | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-22 | D | PCD-21 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-22 | K | PCK- 18 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-22 | J | PCJ- 7 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-22 | I | PCI- 10 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 8 |  | 2022-12-01 | 8
2022-12-22 | C | PCC- 19, 20 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2022-12-01 | 6
2022-12-22 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 32 | 2022-12-01 | 32
2022-12-22 | B |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 11 | 2022-12-01 | 11
2022-12-22 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 10.5 | 2022-12-01 | 10.5
2022-12-22 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 10.5 | 2022-12-01 | 10.5
2022-12-22 | D |  | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2022-12-01 | 0
2022-12-22 | D |  | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2022-12-01 | 0
2022-12-22 | D |  | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2022-12-01 | 0
2022-12-23 | D |  | Erection-Track Beam without Nose |  | 7 | 7 | 7 | [6 empty] | 2022-12-01 | 0
2022-12-23 | D |  | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2022-12-01 | 0
2022-12-25 | H | PCH- 10,12 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-25 | K | PCk-18 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-25 | J | PCJ-7 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-25 | I | PCI-17 | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2022-12-01 | 15
2022-12-25 | D |  | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2022-12-01 | 0
2022-12-26 | D | Restrainer Casting | Pier Cap | [9 empty] | 2 | 2022-12-01 | 2
2022-12-26 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 30 | 2022-12-01 | 30
2022-12-26 | B |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 31 | 2022-12-01 | 31
2022-12-26 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 9 | 2022-12-01 | 9
2022-12-26 | I |  | h - Section Beam |  | 2 | 2 | [6 empty] | 20 | 2022-12-01 | 20
2022-12-26 | D |  | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2022-12-01 | 0
2022-12-26 | D |  | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2022-12-01 | 0
2022-12-27 | H | PCH-16 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-27 | H | PCH-12 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-27 | G | PCG- 8 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-27 | G | PCG- 9 | Step Footing |  | 1 | 2 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-27 | K | PCK- 19 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-27 | I | PCI-11,13 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-27 | D | PCD-17 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-12-01 | 14
2022-12-27 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-27 | B |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-27 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-27 | I | PCI-16 | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2022-12-01 | 3
2022-12-27 | E | PCE-16,17,18,15 | PCC |  | 9 | 9 |  |  |  | 21 |  |  |  | 2022-12-01 | 21
2022-12-28 | D | PCD-17, 18, 19 | Pier 1600 mm |  | 5 | 5 | [5 empty] | 14 |  | 2022-12-01 | 14
2022-12-28 | G | PCG-1 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2022-12-01 | 40
2022-12-28 | C | PCC- 20 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2022-12-01 | 20
2022-12-28 | K | PCK- 17 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-28 | I |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 13 | 2022-12-01 | 13
2022-12-29 | H | PCH-16 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-29 | H | PCH-14 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2022-12-01 | 5
2022-12-29 | K | PCK- 17 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-29 | G | PCG-1 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-29 | I | PCI- 10,11 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-30 | E |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-30 | D |  | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2022-12-01 | 0
2022-12-30 | D |  | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2022-12-01 | 0
2022-12-30 | D |  | Track Beam with Nose |  | 1 | 1 | [7 empty] | 2022-12-01 | 0
2022-12-31 | H | PCH- 14 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2022-12-01 | 12
2022-12-31 | K | PCK- 17 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2022-12-01 | 6
2022-12-31 | I | PCI-11,13 | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 10 |  | 2022-12-01 | 10
2022-12-31 | E | PCE- 18, 17 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2022-12-01 | 60
2022-12-31 | D | PCD- 17 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-12-01 | 14
2022-12-31 | I | PCI- 19A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2022-12-01 | 14
2022-12-31 | G | PCG- | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2022-12-01 | 15
2022-12-31 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2022-12-01 | 36
2022-12-31 | E |  | Track Beam with Nose |  | 4 | 4 | [6 empty] | 48 | 2022-12-01 | 48
2022-12-31 | I |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2022-12-01 | 24
2022-12-31 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2022-12-01 | 12
2022-12-31 | D |  | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2022-12-01 | 0
2022-12-31 | D |  | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2022-12-01 | 0
2022-12-31 | D |  | Erection-U - Section Beam |  | 3 | 3 | 3 | [6 empty] | 2022-12-01 | 0
2022-12-31 | D |  | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2022-12-01 | 0
2023-01-02 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-02 | E |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-02 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-02 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-02 | I | PCI- 16B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-02 | E | PCE- 17, 16 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-01-01 | 40
2023-01-02 | E | PCE- 18 | Step Footing |  | 2 | 1 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-03 | J |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-03 | D |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-03 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-03 | G | PCG-8A,8B | Pier 1900 mm |  | 2 | 0.25 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-03 | K | PCK-16,17 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-03 | E | PCE-17 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-03 | I | PCI-20,21 | PCC |  | 2 | 2 |  |  |  | 10 |  |  |  | 2023-01-01 | 10
2023-01-03 | D |  | Erection-Track Beam without Nose |  | 1 | 1 | [7 empty] | 2022-12-01 | 0
2023-01-04 | I | PCI-21 | RCC Foundation |  | 1 | 1 | [5 empty] | 24 |  | 2023-01-01 | 24
2023-01-04 | E | PCE- 17,18,16 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-01-01 | 15
2023-01-04 | I | PCI- 15,13 | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 13 |  | 2023-01-01 | 13
2023-01-04 | E | PCE- 16 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-04 | D | PCD- 20, 19 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 9 |  | 2023-01-01 | 9
2023-01-04 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-04 | F |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-04 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-05 | I | PCI-14 | Pier Cap |  | 1 | 1 | [6 empty] | 31 | 2023-01-01 | 31
2023-01-05 | I | PCI- 15 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 3 |  | 2023-01-01 | 3
2023-01-05 | D | PCD- 19 | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-01-01 | 15
2023-01-05 | I | PCI- 16 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-05 | E | PCE- 16 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-05 | E | PCE- 11 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-05 | G | PCG-9 | Pier 1900 mm |  | 2 | 0.25 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-05 | K | PCK- 16 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-05 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-05 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-05 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-05 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-06 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-06 | I |  | Track Beam with Nose |  | 3 | [7 empty] | 36 | 2023-01-01 | 36
2023-01-06 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-06 | I |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-08 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-08 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-08 | I |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-08 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-09 | I | PCI-20A,20B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-01-01 | 40
2023-01-09 | I | PCI-19 | Step Footing |  | 1 | 1 | [5 empty] | 7 |  | 2023-01-01 | 7
2023-01-09 | I | PCI-16 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-09 | I | PCI-20 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-09 | E | PCE-16 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-09 | E | PCE-18 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-09 | E | PCE-16A,17A | PCC |  | 3 | 3 |  |  |  | 8 |  |  |  | 2023-01-01 | 8
2023-01-09 | D | PCD-22A,22B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-09 | H | PCH-18,20 | PCC |  | 2 | 2 |  |  |  | 20 |  |  |  | 2023-01-01 | 20
2023-01-09 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-09 | I |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-10 | G | PCG- 25.26,27,28,29,30 | PCC |  | 6 |  |  |  |  | 13 |  |  |  | 2023-01-01 | 13
2023-01-10 | I | Pci-19A | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-01-01 | 15
2023-01-10 | D | PCD-18B | Pier Cap |  | 1 | 1 | [6 empty] | 31 | 2023-01-01 | 31
2023-01-10 | I | PCI-21 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-10 | C | PCC- 20 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-10 | H | PCH-18 | RCC Foundation |  | 1 | [6 empty] | 20 |  | 2023-01-01 | 20
2023-01-10 | D | PCD-22 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 3 |  | 2023-01-01 | 3
2023-01-10 | I | PCI-20 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-10 | E | PCE- 18 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6
2023-01-10 | H |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-10 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-10 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-10 | D | PCD-15-16 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-10 | D | PCD-15-16 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-10 | D | PCD-15-16 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-11 | E | PCE-11A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-11 | D | PCD-14-15 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-11 | D | PCD-14-15 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-11 | D | PCD-14-15 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-11 | D | PCD-14-15 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-12 | D | PCD-13-14 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-12 | D | PCD-13-14 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-12 | D | PCD-13-14 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-12 | E | PCE-11B, 12 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-01-01 | 40
2023-01-12 | E | PCE-11A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-12 | E | PCE- 12A, 13A | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-12 | I | PCI- 20A, 20B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-12 | D | PCD- 17B | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2023-01-01 | 30
2023-01-12 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-12 | I |  | Track Beam with Nose |  | 4 | 4 | [6 empty] | 48 | 2023-01-01 | 48
2023-01-13 | E | PCE- 11B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-13 | E | PCE- 12 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-13 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-13 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-13 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-13 | D | PCD- 12-13 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-13 | D | PCD- 12-13 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-13 | D | PCD- 12-13 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-15 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-15 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-15 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-15 | H | PCH- 20 | RCC Foundation |  | 1 | [6 empty] | 26 |  | 2023-01-01 | 26
2023-01-15 | G | PCG- 25,26,29, 30 | RCC Foundation |  | 4 | [6 empty] | 100 |  | 2023-01-01 | 100
2023-01-15 | H | PCH- 18 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-15 | D | PCD- 22B | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-01-01 | 13
2023-01-16 | H | PCH- 20 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-16 | G | PCG- 25,26,29, 30 | Step Footing |  | 4 | [6 empty] | 20 |  | 2023-01-01 | 20
2023-01-16 | E | PCE-17 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-16 | E | PCE-16 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-16 | E | PCE-12,13 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-16 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-16 | I |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-16 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-16 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-17 | D | PCD- 21B | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-17 | A | PC- 47 | PCC |  | 1 | 1 |  |  |  | 4 |  |  |  | 2023-01-01 | 4
2023-01-17 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-17 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-17 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-17 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-18 | A | PC- 48,49,50 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-01-01 | 12
2023-01-18 | G | PCG- 11 | PCC |  | 1 | 1 |  |  |  | 6 |  |  |  | 2023-01-01 | 6
2023-01-18 | C | PCC- 20 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-01-01 | 6
2023-01-18 | E | PCE-12,13 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-18 | E | PCE-11,12 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-01-01 | 18
2023-01-18 | G | PCG- 26,28 | RCC Foundation |  | 2 | [6 empty] | 76 |  | 2023-01-01 | 76
2023-01-18 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-18 | I |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-18 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-18 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-19 | I | PCI-5 | Pier Cap |  | 1 | 1 | [6 empty] | 49 | 2023-01-01 | 49
2023-01-19 | I | PCI-18A | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-01-01 | 15
2023-01-19 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-19 | I |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-19 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-19 | D | PCD- 15-16 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-19 | D | PCD- 15-16 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-01-01 | 0
2023-01-19 | D | PCD- 15-16 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-20 | D | PCD- 19B | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2023-01-01 | 30
2023-01-20 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-20 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-20 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-20 | I |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-20 | D | PCD- 15-16 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-20 | D | PCD- 14-15 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-01-01 | 0
2023-01-20 | D | PCD- 14-15 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-22 | D | PCD- 6A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-01-01 | 14
2023-01-22 | D | PCD-22B | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-01-01 | 14
2023-01-22 | G |  | Pier 1900 mm |  | 1 | 0.5 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-22 | H | PCH-18 | Pier 1900 mm |  | 1 | [6 empty] | 6 |  | 2023-01-01 | 6
2023-01-22 | G | PCG-25 | Pier 1900 mm |  | 1 | [6 empty] | 6 |  | 2023-01-01 | 6
2023-01-22 | H | PCH-1,2 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-22 | G | PCG- 11 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-22 | C | PCC- 20 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-22 | G | PCG- 27, 28 | Step Footing |  | 2 | [6 empty] | 10 |  | 2023-01-01 | 10
2023-01-22 | H |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-22 | I |  | Track Beam with Nose |  | 4 | 4 | [6 empty] | 48 | 2023-01-01 | 48
2023-01-22 | D | PCD-15-16 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-22 | D | PCD-14-15 | Track Beam with Nose |  | 2 | 2 | [7 empty] | 2023-01-01 | 0
2023-01-22 | B | PCD-13-14 | Track Beam without Nose |  | 2 | 2 | [7 empty] | 2023-01-01 | 0
2023-01-23 | C | PCC-20 | Step Footing |  | 2 | 2 | [5 empty] | 12 |  | 2023-01-01 | 12
2023-01-23 | G | PCG-2,3 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-01-01 | 12
2023-01-23 | K | PCK- 15 | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2023-01-01 | 3
2023-01-23 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-23 | I |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-23 | I |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-23 | I |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-23 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-23 | D |  | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-23 | D |  | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-23 | G | PCG-3, 3a | PCC |  | 1 | 1 |  |  |  | 6 |  |  |  | 2023-01-01 | 6
2023-01-24 | G | PCG-2A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-24 | I | PCI- 16, 8 | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-24 | H | PCH- 20 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-01-01 | 6 |  | 23
2023-01-24 | G | PCG- 26,29 | Pier 1900 mm |  | 2 | [6 empty] | 12 |  | 2023-01-01 | 12
2023-01-24 | H | PCH- 12, 14 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-24 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-24 | I |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-24 | I | PCI- 8-9 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-24 | D | PCD- 10-11 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-01-01 | 0
2023-01-24 | D | PCD- 10-11 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-24 | D | PCD- 10-11 | Erection-U - Section Beam |  | 3 | 3 | 3 | [6 empty] | 2023-01-01 | 0
2023-01-26 | A | PC- 47, 48, 49, 50 | RCC Foundation |  | 4 | 4 | [5 empty] | 80 |  | 2023-01-01 | 80
2023-01-26 | G | PCG- 3A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-26 | G | PCG- 29, 28 | Pier 1900 mm |  | 2 | [6 empty] | 12 |  | 2023-01-01 | 12
2023-01-26 | G | PCG-11, 2A | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-26 | H | PCH- 19 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-26 | D | PCD- 20 A | Pier Cap |  | 1 | 1 | [6 empty] | 32 | 2023-01-01 | 32
2023-01-26 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-26 | I |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-26 | J |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-26 | A |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-26 | D | PCD- 11-12 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-26 | D | PCD- 11-12 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-27 | G | PCG- 3B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-27 | G | PCG- 3A | Step Footing |  | 2 | 2 | [5 empty] | 5 |  | 2023-01-01 | 5
2023-01-27 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-01-01 | 36
2023-01-27 | I |  | Track Beam with Nose |  | 4 | 4 | [6 empty] | 48 | 2023-01-01 | 48
2023-01-27 | J |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-27 | B |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-27 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-01-01 | 2.5
2023-01-29 | A | PC- 47, 48, 49, 50 | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2023-01-01 | 20
2023-01-29 | I | PCI- 18A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-01-01 | 14
2023-01-29 | I | PCI- 16A, 16B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-29 | H | PCH- 10, 19 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-29 | D | PCD- 13- 14 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 13- 14 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 15- 14 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 13- 14 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 13- 14 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 13- 14 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 12- 13 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 12- 13 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-29 | D | PCD- 12- 13 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-30 | D | PCD-21A | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2023-01-01 | 30
2023-01-30 | D | PCD-9-10 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-30 | D | PCD-9-10 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-30 | D | PCD-9-10 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-31 | D | PCD-6 | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2023-01-01 | 30
2023-01-31 | G | PCG-28,26 | Pier 1900 mm |  | 2 | [6 empty] | 12 |  | 2023-01-01 | 12
2023-01-31 | H | PCH-16,19 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-01-01 | 10
2023-01-31 | B |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-31 | I |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-01-01 | 24
2023-01-31 | I |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-01-01 | 12
2023-01-31 | D |  | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-01-01 | 0
2023-01-31 | D |  | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-01-31 | D |  | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-01-01 | 0
2023-02-01 | I |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-02-01 | 36
2023-02-01 | I |  | Track Beam with Nose |  | 4 | 4 | [6 empty] | 48 | 2023-02-01 | 48
2023-02-01 | B |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-01 | J |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-01 | D | PCD- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-01 | G | PCG- 11B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-01 | G | PCG- 21A, 20A, B, 19A,19B, 18A, 18B, 14A, 14B | PCC |  | 7 | 7 |  |  |  | 27 |  |  |  | 2023-02-01 | 27
2023-02-02 | D | PCD- 7-9 | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-02-01 | 0
2023-02-02 | D | PCD- 9-10 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-02 | E | PCE- 3A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-02 | K | PCK- 15 | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-02-01 | 35
2023-02-02 | K | PCK-14 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-02 | K | PCK-14 | PCC |  | 2 | 2 |  |  |  | 8 |  |  |  | 2023-02-01 | 8
2023-02-02 | I | I14-I15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-02 | I | I10-I11 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-02 | I | I13-I14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-02 | A | PC50- PC-52 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-02 | I | I15-I16 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-03 | I | PCI- 21A, B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-03 | E | PCE- 11A,B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-03 | C | PCC- 3A,B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-03 | E | PCE-3B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-03 | E | PCE-3A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-03 | G | PCG- 3B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-03 | I | PCI-21 | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2023-02-01 | 3
2023-02-03 | I | I14-I15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-03 | I | I10-I11 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-03 | I | I13-I14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-03 | A | PC50- PC-52 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-03 | I | I15-I16 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-03 | A |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-03 | D |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-03 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 5 | 2023-02-01 | 5
2023-02-03 | D | PCD-8-9 | Erection-Pre-cast Slab |  | 6 | 6 | 6 | [6 empty] | 2023-02-01 | 0
2023-02-03 | D | PCD-9-10 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-02-01 | 0
2023-02-04 | E | PCE- 2A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-04 | E | PCE- 3B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-04 | G | PCG- 11B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-04 | G | PCG- 6A, 8A | Pier 1900 mm |  | 2 | 0.25 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-04 | I | PCI- 20B | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-04 | D | PCD- 22A | Pier Cap |  | 1 | 1 | [6 empty] | 32 | 2023-02-01 | 32
2023-02-04 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-02-01 | 36
2023-02-04 | I |  | Track Beam with Nose |  | 4 | 4 | [6 empty] | 48 | 2023-02-01 | 48
2023-02-04 | J |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-04 | B |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-04 | I |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-02-01 | 2.5
2023-02-04 | D |  | Erection-Track Beam without Nose |  | 7 | 7 | 7 | [6 empty] | 2023-02-01 | 0
2023-02-04 | D |  | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-02-01 | 0
2023-02-06 | D | PCD- 17-19 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-06 | A | PC- 58- 60 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | I | PCI- 10-11 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | I | PCI- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | A | PC- 51- 53 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | H | PCH- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | F | PCF- 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-06 | G | PCG- 20B, 18A, 18B | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2023-02-01 | 60
2023-02-06 | C | PCC- 2A, 4A, 4B | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 15 |  | 2023-02-01 | 15
2023-02-06 | D |  | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-07 | D | PCD- 16-17 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-02-01 | 0
2023-02-07 | D | PCD- 16-17 | Erection-Track Beam without Nose |  | 6 | 6 | 6 | [6 empty] | 2023-02-01 | 0
2023-02-07 | D | PCD- 17-18 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-07 | D | PCD- 17-18 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-02-01 | 0
2023-02-07 | D | PCD- 17-19 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-07 | A | PC- 58-60 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-07 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-07 | I | PCI- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-07 | I | PCI- 10-11 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-07 | I | PCI- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-07 | A | PC- 51- 53 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-07 | H | PCH- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-07 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-02-01 | 2.5
2023-02-07 | K | PCK- 15C | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-02-01 | 35
2023-02-08 | I | PCI- 13 | Pier Cap |  | 1 | 1 | [6 empty] | 32 | 2023-02-01 | 32
2023-02-08 | I | PCI- 20A, 20B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-08 | G | PCG- 7B, 8C | Pier 1900 mm |  | 2 | 0.25 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-08 | D | PCD- 19-21 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-08 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-08 | I | PCI- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-08 | I | PCI- 10-11 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-08 | I | PCI- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-08 | A | PC- 51- 53 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-08 | H | PCH- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-08 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-02-01 | 2
2023-02-08 | D | PCD- 16-17 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-08 | D | PCD- 17-18 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-08 | D | PCD- 17-18 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 19 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 20 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 21 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 22 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 23 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 24 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 18 TO 25 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-09 | D | GRIDE 17 TO 19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-10 | K |  | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-02-01 | 6
2023-02-10 | I | I8 | Pier Cap |  | 1 | 1 | [6 empty] | 59 | 2023-02-01 | 59
2023-02-10 | D | GRID 18 TO 19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-10 | D | GRID 19 TO 20 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-10 | D | GRID 19 TO 20 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-10 | D | GRID 19 TO 20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-10 | D | GRID 19 TO 20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-10 | D | GRID 19 TO 20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-10 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 5 | 2023-02-01 | 5
2023-02-12 | A | PC- 47, 48 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2023-02-01 | 24
2023-02-12 | C | PCC- 1A, 3A, 3B, 5A | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-12 | I | PCI- 20 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-12 | G | PCG- 21A, 20B, 19A, 17A, 12A, 12B, 13 | RCC Foundation |  | 7 | 7 | [5 empty] | 200 |  | 2023-02-01 | 200
2023-02-12 | I | PCI-21A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-12 | G | PCG- 15, 16 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-02-01 | 12
2023-02-12 | K | PCK-12 | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2023-02-01 | 3
2023-02-12 | D | PCD- 21B-23B | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-12 | A | PC-61-64 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-12 | A | PC-- 53-55 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-12 | H | PCH- 4-5 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-12 | H | PCH- 15-17 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-12 | I | PCI-11-12 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-12 | I | PCI-15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-12 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 5 | 2023-02-01 | 5
2023-02-12 | D | PCD- 19-20 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-12 | D | PCD- 19-20 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-02-01 | 0
2023-02-12 | D | PCD- 19-20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-12 | D | PCD- 20-21 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-12 | D | PCD- 20-21 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-12 | D | PCD- 20-21 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-02-01 | 0
2023-02-13 | G | PCG- 6B, 8A | Pier 1900 mm |  | 2 | 0.25 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-13 | G | PCG-21A, 17A, 12 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-02-01 | 15
2023-02-13 | I | PCI- 21B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-13 | I | PCI- 11 | Pier Cap |  | 1 | 1 | [6 empty] | 30 | 2023-02-01 | 30
2023-02-13 | D | PCD- 21-22 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-13 | D | PCD- 21-22 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-13 | D | PCD- 21-22 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-13 | D | PCD- 20-21 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-13 | D | PCD- 20-21 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-13 | D | PCD- 20-21 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-13 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-13 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-13 | J |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-13 | I |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-14 | B | PC- 92 | Pier Cap |  | 1 | 1 | [6 empty] | 32 | 2023-02-01 | 32
2023-02-14 | H | PCH- 18, 20 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-14 | C |  | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-14 | G | PCG- 12, 13, 20A, B | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-14 | A | PC- 53-55 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-14 | H | PCH- 15-17 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-14 | I | PCI- 11-12 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-14 | I | PCI- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-14 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-02-01 | 2.5
2023-02-14 | D |  | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-15 | G | PCG- 15, 16 | RCC Foundation |  | 2 | 2 | [5 empty] | 96 |  | 2023-02-01 | 96
2023-02-15 | G | PCG- 12B, 13B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-15 | A | PC-47-51 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-15 | A | PC-64-67 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-15 | H | PCH- 5-6, 8-9 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-15 | I | PCI- 15-17 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-15 | D | PCD- 11-12 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-15 | D | PCD- 11-12 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-15 | D | PCD- 11-12 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-15 | D | PCD- 11-12 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-15 | D | PCD- 12-13 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-15 | D | PCD- 12-13 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-16 | G | PCG- 19A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-16 | G | PCG-30 | Pier 1600 mm |  | 1 | [6 empty] | 5 |  | 2023-02-01 | 5
2023-02-16 | G | PCG-11A, 11B, 8A | Pier 1900 mm |  | 3 | 1.5 | [5 empty] | 18 |  | 2023-02-01 | 18
2023-02-16 | K | PCK- 16 D | Step Footing |  | 2 | 2 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-16 | K | PCK-13 | PCC |  | 5 | 5 |  |  |  | 18 |  |  |  | 2023-02-01 | 18
2023-02-16 | I | PCI- 16 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-02-01 | 14
2023-02-16 | I | PCI- 21 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-02-01 | 6
2023-02-16 | C | PCC- 2B | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-16 | F | PCF- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-17 | G | PCG- 19A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-17 | K | PCK- 12D | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-02-01 | 35
2023-02-17 | D | PCD-6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-17 | D | PCD-6-7 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-17 | D | PCD-6-7 | Erection-Track Beam without Nose |  | 8 | 8 | 8 | [6 empty] | 2023-02-01 | 0
2023-02-17 | D | PCD-6-7 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-19 | B | PC-93 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-02-01 | 35
2023-02-19 | G | PCG- 25, 26, 27, 28, 29, 30 | Pier 1600 mm |  | 6 | [6 empty] | 30 |  | 2023-02-01 | 30
2023-02-19 | G | PCG- 12A, 13A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-19 | K | PCK- 12C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-19 | K | PCK- 12D | Step Footing |  | 1 | 1 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-19 | C | PCC- 3A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-02-01 | 14
2023-02-19 | I | PCI- 6 | Pier Cap |  | 1 | 1 | [6 empty] | 55 | 2023-02-01 | 55
2023-02-19 | A | PC- 65-68 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-19 | A | PC- 51- 53 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-19 | A | PC- 56- 58 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-19 | H | PCH- 9-11 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-19 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-19 | I | PCI- 12-13 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-19 | H | PCH- 1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-19 | A | PC- 44-47 | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-02-01 | 2.5
2023-02-19 | D | PCD- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-19 | D | PCD- 6-12 | Erection-Pre-cast Slab |  | 38 | 38 | 38 | [6 empty] | 2023-02-01 | 0
2023-02-20 | G | PCG- 28B, 25 | Pier 1600 mm |  | 2 | [6 empty] | 10 |  | 2023-02-01 | 10
2023-02-20 | G | PCG- 12B, 13B, 15A, 9B | Pier 1900 mm |  | 4 | 3 | [5 empty] | 24 |  | 2023-02-01 | 24
2023-02-20 | I | PCI- 16A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-02-01 | 14
2023-02-21 | H | PCH- 18, 20 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-21 | G | PCG- 27, 28A | Pier 1600 mm |  | 2 | [6 empty] | 10 |  | 2023-02-01 | 10
2023-02-21 | G | PCG- 15B | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-02-01 | 6
2023-02-21 | G | PCG- 18A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-21 | K | PCK- 12C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-21 | K | PCK- 12B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-21 | I | PCI- 21B | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-21 | I | PCI- 1-2 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-21 | I | PCI- 1-2 | Erection-U - Section Beam |  | 3 | 3 | 3 | [6 empty] | 2023-02-01 | 0
2023-02-21 | A | PC- 56-58 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-21 | I | PCI- 12-13 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-21 | H | PCH- 1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-22 | G | PCG- 16A, 16B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-22 | K | PCK- 12D, 13C, 13D | RCC Foundation |  | 3 | 3 | [5 empty] | 75 |  | 2023-02-01 | 75
2023-02-22 | K | PCK- 12C | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-22 | C | PCC- 3A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-02-01 | 14
2023-02-22 | G | PCG- 17B (Plum) | PCC |  | 1 | 1 |  |  |  | 25 |  |  |  | 2023-02-01 | 25
2023-02-22 | A | PC- 53-55 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-22 | A | PC- 67-69 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-22 | A | PC- 56-58 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-22 | H | PCH- 11-13, 13-15 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-22 | I | PCI- 12-13 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-22 | H | PCH- 1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-22 | A | PC- 45-48 | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-02-01 | 2.5
2023-02-22 | I | PCI- 1-2 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-22 | I | PCI- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-22 | I | PCI- 2-3 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-22 | I | PCI- 2-3 | Erection-U - Section Beam |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-22 | I | PCI- 2-3 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-22 | I | PCI- 3-4 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-23 | A | PC-51,52,53,54 | PCC |  | 6 | 6 |  |  |  | 18 |  |  |  | 2023-02-01 | 18
2023-02-23 | G | PCG-17 B (PLUM) | PCC |  | 1 | 1 |  |  |  | 18 |  |  |  | 2023-02-01 | 18
2023-02-23 | I | PCI-10A,C, 9A | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 12 |  | 2023-02-01 | 12
2023-02-23 | C | PCC-C/4A,6B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-23 | I | PCI-5 | Pier Cap | [10 empty] | 2023-02-01 | 0
2023-02-23 | A | PC-55-PC-57 | h - Section Beam |  | 1 | 1 | [6 empty] | 11 | 2023-02-01 | 11
2023-02-23 | A | PC-69-PC72 | U - Section Beam |  | 2 | 2 | [6 empty] | 23 | 2023-02-01 | 23
2023-02-23 | A | PC-57-PC-59 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 11 | 2023-02-01 | 11
2023-02-23 | G | PCG-28 A,B | Pier 1600 mm |  | 2 | [6 empty] | 10 |  | 2023-02-01 | 10
2023-02-23 | I | PCI- 3-4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-23 | I | PCI- 3-4 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-23 | I | PCI- 3-4 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-02-01 | 0
2023-02-24 | K | PCK- 13A, 13B | RCC Foundation |  | 2 | 2 | [5 empty] | 55 |  | 2023-02-01 | 55
2023-02-24 | K | PCK- 13C, 13D, 12A | Step Footing |  | 3 | 3 | [5 empty] | 22 |  | 2023-02-01 | 22
2023-02-24 | C | PCC-7A,7B, 8A, 8B, 9A, 9B, 10A | Pier 1600 mm |  | 7 | 3.5 | [5 empty] | 35 |  | 2023-02-01 | 35
2023-02-24 | C | PCC- 4A, 2A | Pier Cap |  | 2 | 2 | [6 empty] | 26 | 2023-02-01 | 26
2023-02-24 | H | PCH- 14 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-02-01 | 14
2023-02-24 | I | PCI- 1-4 | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-02-01 | 0
2023-02-24 | A | pc- 55-57 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-24 | A | PC- 57-59 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-24 | H | PCH- 11-13, 13-15 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-24 | I | PCI- 12-13 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-24 | H | PCH-1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-24 | A | PC- 45-48 | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-02-01 | 2.5
2023-02-26 | I | PCI- 20A | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-02-01 | 13
2023-02-26 | I | PCI- 21A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-02-01 | 5
2023-02-26 | I | PCI- 4-5 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-02-01 | 0
2023-02-26 | I | PCI- 4-5 | Erection-U - Section Beam |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-26 | I | PCI- 4-5 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-02-01 | 0
2023-02-26 | A | PC- 59-61 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-26 | J | PCJ- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-02-01 | 24
2023-02-26 | K | PCH- 19-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-26 | I | PCI- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-26 | H | PCH- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-26 | A | PC- 70-72 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-27 | I |  | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-02-01 | 0
2023-02-27 | G | PCG- 10A, 10B, 17A, 18A | Pier 1900 mm |  | 4 | 2.5 | [5 empty] | 24 |  | 2023-02-01 | 24
2023-02-27 | G | PCG- 17B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-02-01 | 20
2023-02-27 | E | PCE- 11A, 11B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-27 | C | PCC- 1A, 1B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-02-01 | 10
2023-02-27 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-02-01 | 36
2023-02-27 | I |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-02-27 | F |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-02-01 | 12
2023-03-01 | A | PC 60-PC 62 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-01 | K | PCH K10 -K18 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-01 | I | PC I6-I7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-01 | I | PC I13-I14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-01 | I | PCI 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-01 | A | PC 435-PC45 | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-03-01 | 2
2023-03-02 | A | PC72-PC74 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-02 | A | PC 60-PC 62 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-02 | I | PC I5-I6 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-02 | I | PC I5-I6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-02 | I | PC I5-I6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-02 | I | PC I5-I6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-03 | I | PCI- 21A, B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-03 | C | PCC- 4B | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-03-01 | 15
2023-03-06 | C | PCC- 2B | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | H | PCH-12 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | I | PCI- 20B | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | A | PC- 45-47 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | A | PC- 72-74 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | I | PCI- 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | K | PCK- 18-19 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-06 | I | PCI- 5-6 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-03-01 | 36
2023-03-08 | A | PC- 80-82 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-08 | A | PC_ 68-70, 69-71 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-08 | A | PC- 45-47, 46-48 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-08 | I | PCI- 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-08 | I | PCI- 5-6 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-08 | K | PC- 91-92 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-08 | I |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-09 | I | PCI-9 | Pier Cap |  | 1 | 1 | [6 empty] | 58 | 2023-03-01 | 58
2023-03-09 | A | PC- 51,52,53 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2023-03-01 | 60
2023-03-09 | G | PCG- 14A, 14B | RCC Foundation |  | 2 | 2 | [5 empty] | 54 |  | 2023-03-01 | 54
2023-03-09 | G | PCG- 6 | Pier 1900 mm |  | 2 | 0.5 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-09 | I | PCI- 7 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-09 | C | PCC- 11 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-09 | E | PCE- 15A, 15B, 16A, 16B, 17A, 17B | Pier 1600 mm |  | 6 | 3 | [5 empty] | 30 |  | 2023-03-01 | 30
2023-03-09 | G | PCG- 16A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-09 | I | PCI- 5-6 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-09 | A | PC- 45-47 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-09 | I | PCI- 6-7 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-09 | I | PCI- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-09 | B | PC- 86-87, 92-93 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-10 | I | PCI- 15 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-03-01 | 35
2023-03-10 | A | PC- 70-72, 71-73 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-10 | A | PC- 46-48, 47-49 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-10 | I | PCI- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-10 | B | PC- 86-87 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-10 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-12 | J | PCJ- 2,3 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-03-01 | 15
2023-03-12 | K | PCK- 13 | Step Footing |  | 2 | 2 | [5 empty] | 13 |  | 2023-03-01 | 13
2023-03-12 | G | PCG- 17, 14 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-12 | d | D-23 | Step Footing | [8 empty] | 10 |  | 2023-03-01 | 10
2023-03-12 | A | PC- 51,52,53 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-03-01 | 15
2023-03-12 | E | PCE- 18 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-12 | G | PCG- 6, 19,18 | Pier 1900 mm |  | 4 | 2.25 | [5 empty] | 24 |  | 2023-03-01 | 24
2023-03-12 | E | PCE- 2A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-12 | A | PC- 61,62 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-03-01 | 6
2023-03-12 | C | PCC- 18,19 | PCC |  | 3 | 3 |  |  |  | 9 |  |  |  | 2023-03-01 | 9
2023-03-12 | A |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-12 | K |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-12 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-12 | J |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-12 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-12 | B | PC- 95-96 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-13 | A | PC-47,48 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-13 | H | PCH-4 | Pier Cap |  | 1 | 1 | [6 empty] | 42 | 2023-03-01 | 42
2023-03-13 | J | PCJ-1,2 | Pier 1600 mm |  | 5 | 1.5 | [5 empty] | 25 |  | 2023-03-01 | 25
2023-03-13 | F | PCF- 3 | Pier 1600 mm |  | 2 | 0.25 | [7 empty] | 2023-03-02 | 0
2023-03-13 | B | PC- 95-96 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-03-01 | 0
2023-03-13 | B | PC- 95-96 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-13 | B | PC- 95-96 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-14 | B | PC- 94-95 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-03-01 | 0
2023-03-14 | B | PC- 94-95 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-14 | B | PC- 94-95 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-14 | A | PC- 50-52 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-14 | A | PC- 48-50 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-14 | I | PCI- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-14 | K | PCK- 17-18 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-14 | B | PC- 84-85 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-14 | B | PC- 87-88 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-14 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-14 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-14 | G | PCG- 8A, 8B | Pier 1900 mm |  | 2 | 1 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-14 | I | PCI- 21A | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-03-01 | 15
2023-03-14 | C | PCC- 19A, 19B | RCC Foundation |  | 2 | 2 | [5 empty] | 54 |  | 2023-03-01 | 54
2023-03-14 | C | PCC- 20A | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-15 | A | PC-47,48 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-15 | H | PCH- 6 | Pier Cap |  | 1 | 1 | [6 empty] | 44 | 2023-03-01 | 44
2023-03-15 | I | PCI- 7 | Pier Cap |  | 1 | 1 | [6 empty] | 54 | 2023-03-01 | 54
2023-03-15 | F | PCF- 1,2,3 | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 40 |  | 2023-03-01 | 40
2023-03-15 | J | PCJ- 5 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-15 | A | PC- 73-75, 74-76 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-15 | K | PCK- 17-18 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-15 | A | PC- 49-51 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-15 | B | PC- 84-85 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-15 | B | PC- 88-89 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-15 | K | PCF- 10A- PCk19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-15 | B | PC- 93-94 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-03-01 | 0
2023-03-15 | B | PC- 93-94 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-15 | B | PC- 93-94 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-16 | A | PC- 49,50 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-16 | A | PC-53 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-16 | H | PCH-1 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-16 | G | PCG- 9A, 8A | Pier 1900 mm |  | 2 | 1 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-16 | C | PCC- 19A, 19B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-16 | B | PC- 93-96 | Erection-Pre-cast Slab |  | 18 | 18 | 18 | [6 empty] | 2023-03-01 | 0
2023-03-16 | K | PCK- 17-18, PCK- 10A-19 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-16 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-16 | A | PC- 50-52 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-16 | K | PCK- 16-17 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-16 | A | PC- 51-53 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-17 | A | PC- 75-77 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-17 | B | PC- 84-85 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-17 | B | PC- 84-85 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-17 | K | PCK- 17-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-17 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-17 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-17 | B | PC- 92-93 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-17 | B | PC- 92-93 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-17 | B | PC- 92-93 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-17 | A | PC- 51 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-17 | A | PC- 63,64 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-03-01 | 40
2023-03-17 | G | PCG- 9B, 8B | Pier 1900 mm |  | 2 | 1 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-17 | I | PCI- 10 | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-17 | J | PCJ- 5,6 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-03-01 | 20
2023-03-19 | A | PC- 52 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-19 | A | PC- 63,64 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-19 | G | PCG- 10A, 10B | Pier 1900 mm |  | 2 | 1 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-19 | J | PCJ- 5, 6, 7,8 | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 35 |  | 2023-03-01 | 35
2023-03-19 | I | PCI- 10 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 3 |  | 2023-03-01 | 3
2023-03-19 | I | PCI-21 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-03-01 | 14
2023-03-19 | A | PC- 48, 49 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-19 | A | PC- 59-61 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-19 | A | PC- 51-53 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-19 | K | PCK- 17-16 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-19 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-19 | B | PC- 92-93 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-19 | B | PC- 92-93 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-03-01 | 0
2023-03-19 | B | PC- 92-93 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-19 | B | PC- 92-93 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-20 | A | PC- 63 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-20 | D | PCD- 23A, C | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-20 | A | PC- 77-79 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-20 | A | PC- 51-53 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-20 | K | PCK- 17-18 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-20 | K | PCF-10 - PCK-19 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-20 | K | PCK- 16-17 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-20 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1.5 | 2023-03-01 | 1.5
2023-03-20 | I | PCI- 5-6 | Erection-Track Beam without Nose |  | 8 | 8 | 8 | [6 empty] | 2023-03-01 | 0
2023-03-20 | I | PCI- 5-6 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-21 | H | PCH-1 | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-03-01 | 34
2023-03-21 | G | PCG- 14A, 14B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-21 | D | PCD- 23A, C | Pier 1600 mm |  | 2 | 1 | [5 empty] | 8 |  | 2023-03-01 | 8
2023-03-21 | A | PC- 59-61 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-21 | A | PC-54-56 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-21 | H | PCH- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-21 | H | PCH-1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-21 | H | PCH-3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-21 | K | PCK- 16-17 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-21 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-03-01 | 1
2023-03-22 | A | PC- 64 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-22 | J | PCJ- 9, 10,11 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-03-01 | 25
2023-03-22 | I | PCI- 11-12 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-22 | I | PCI- 11-12 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-22 | I | PCI- 11-12 | Erection-Track Beam without Nose |  | 6 | 6 | 6 | [6 empty] | 2023-03-01 | 0
2023-03-22 | H |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-22 | A |  | Pre-cast Slab |  | 4 | 4 | [6 empty] | 2 | 2023-03-01 | 2
2023-03-23 | A | PC- 54-56 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-23 | K | PC-15 -14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-23 | K | PCK- 16-17 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-23 | H | PCH- 4-5, 1-2 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-23 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-23 | I | PCI- 11-12 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-23 | I | PCI- 11-12 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-23 | I | PCI- 11-12 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-23 | I | PCI-12-13 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-23 | I | PCI-12-13 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-23 | I | PCI-12-13 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-24 | H | PCH- 18 | Pier Cap |  | 1 | [7 empty] | 15 | 2023-03-01 | 15
2023-03-24 | J | PCJ- 9,10,11,12 | Pier 1600 mm |  | 10 | 2.5 | [5 empty] | 50 |  | 2023-03-01 | 50
2023-03-24 | K | PCK-19 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-03-01 | 15
2023-03-24 | I | PCI- 12-13 | Erection-Track Beam without Nose |  | 6 | 6 | 6 | [6 empty] | 2023-03-01 | 0
2023-03-24 | I | PCI- 12-13 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-24 | I | PCI- 13-14 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-03-01 | 0
2023-03-24 | I | PCI- 13-14 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-24 | I | PCI- 13-14 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-24 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-24 | H |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-24 | B |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-26 | G | PCG-21, 17,19,20 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2023-03-01 | 24
2023-03-26 | K | PCK- 19 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-03-01 | 5
2023-03-26 | A | PC- 55-57 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-26 | K | PCK- 16-17 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-26 | H | PCH- 2-3, 4-5 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-26 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-26 | I | PCI- 12-13 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-26 | I | PCI- 13-14 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-26 | I | PCI- 13-14 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-26 | I | PCI- 13-14 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-03-01 | 0
2023-03-27 | I | PCI- 10 | Pier Cap |  | 1 | 1 | [6 empty] | 72 | 2023-03-01 | 72
2023-03-27 | H | PCH- 2 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-03-01 | 35
2023-03-27 | A | PC- 61-63 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-27 | A | PC- 56- 58 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-27 | K | PCK- 13-14 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-27 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-27 | H | PCh- 5-6, 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-27 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-27 | I | PCI- 14-15 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-27 | I | PCI- 14-15 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-27 | I | PCI- 14-15 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-03-01 | 0
2023-03-27 | I | PCI- 14-15 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-28 | G | PCG- 1A, 1B, 2B, 21 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2023-03-01 | 24
2023-03-28 | J | PCJ- 12A, B, 11B,C, 8A,B, 10A, B | Pier 1600 mm |  | 8 | 2.5 | [5 empty] | 40 |  | 2023-03-01 | 40
2023-03-28 | K | PCK- 19C, 18A, B, D | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-03-01 | 20
2023-03-28 | H | PCH- 16 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-28 | H | PCH- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-28 | K | PCK- 13-14 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-28 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-28 | H | PCH- 5-6, 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-28 | I | PCI- 14-15 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-28 | I | PCI- 14-15 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-28 | I | PCI- 15-16 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-28 | I | PCI- 15-16 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-03-01 | 0
2023-03-28 | I | PCI- 15-16 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-28 | I | PCI- 15-16 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-03-01 | 0
2023-03-29 | I | PCI- 14-15 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-29 | I | PCI- 15-16 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-29 | I | PCI- 15-16 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-29 | I | PCI- 15-16 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-29 | H | PCH- 6-7 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-29 | K | PCK- 13-14 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-29 | H | PC- 96- PCH-1 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-29 | H | PC- 96- PCH-1 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-29 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-29 | H | PCH- 3-4, 5-6 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-29 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-30 | C | PCC- 19A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-30 | E | PCE-3 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-03-01 | 12
2023-03-30 | J | PCJ- 1,2,3 | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 35 |  | 2023-03-01 | 35
2023-03-30 | I | PCI- 6-7 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-30 | H | PCH- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-30 | K | PCK- 12-13 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-30 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-30 | H | PCH- 4-5, 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-30 | I | PCI- 6-7 | Erection-Track Beam with Nose |  | 6 | 6 | 6 | [6 empty] | 2023-03-01 | 0
2023-03-30 | I | PCI- 6-7 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-31 | G | PCG- 15A, 16A | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-03-01 | 10
2023-03-31 | K | PCK- 17A, 17D, 17C, 18C | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-03-01 | 20
2023-03-31 | E | PCE-2 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-03-01 | 6
2023-03-31 | H | PCH- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-31 | H | PC-96 - PCH- 1 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-31 | H | PCH- 8-9 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-31 | K | PCK- 11-12 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-31 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-03-01 | 12
2023-03-31 | H | PCCH- 5-6, 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-03-01 | 24
2023-03-31 | H |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-03-01 | 2.5
2023-03-31 | I | PCI- 7-8 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-31 | I | PCI- 7-8 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-03-01 | 0
2023-03-31 | I | PCI- 7-8 | Erection-Track Beam without Nose |  | 10 | 10 | 10 | [6 empty] | 2023-03-01 | 0
2023-04-02 | H | PCH- 8 | Pier Cap |  | 1 | 1 | [6 empty] | 50 | 2023-04-01 | 50
2023-04-02 | C | PCC-18 | RCC Foundation |  | 1 | 1 | [5 empty] | 32 |  | 2023-04-01 | 32
2023-04-02 | H | PCH- 2-3 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-02 | H | PCH- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-02 | H | PCH- 14-16 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-02 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-02 | H | PCH- 6-7, 7-8 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-03 | J | PCJ- 1A,B, 4A, 5A, B | Pier 1600 mm |  | 5 | 2.5 | [5 empty] | 25 |  | 2023-04-01 | 25
2023-04-03 | G | PCG-6 | Pier 1900 mm |  | 1 | 0.2 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-03 | K | PCK- 16A, B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-03 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-03 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-04-01 | 36
2023-04-03 | B |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-03 | F |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-04 | A | PC- 58, 60, 62 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2023-04-01 | 60
2023-04-04 | H | PCH- 3-4 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-04 | H | PCH- 2-3 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-04 | H | PCH- 11-13 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-04 | K | PCK-10-11 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-04 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-04 | H | PCH- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-04 | H |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-04-01 | 2.5
2023-04-04 | D | PCD- 16-17 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-04 | D | PCD- 16-17 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 16-17 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 16-17 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 17-18 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 17-18 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 17-18 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 18-19 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 18-19 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-05 | D | PCD- 18-19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-05 | B |  | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2023-04-01 | 36
2023-04-05 | H |  | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-04-01 | 36
2023-04-05 | F |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-06 | K | PCK- 15 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-06 | K | PCK- 17 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-04-01 | 20
2023-04-06 | J | PCJ- 5,6,7 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-04-01 | 25
2023-04-06 | G | PCG- 7,9 | Pier 1900 mm |  | 2 | 0.5 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-06 | G | PCG- 12,13,16,17 | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2023-04-01 | 20
2023-04-06 | A | PC- 53, 55, 57, 59 | RCC Foundation |  | 4 | 4 | [5 empty] | 80 |  | 2023-04-01 | 80
2023-04-06 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-06 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-06 | F |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-06 | H |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-06 | D | PCD- 16-19 | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-04-01 | 0
2023-04-07 | H | PCH- 7,9 | Pier Cap |  | 2 | 2 | [6 empty] | 105 | 2023-04-01 | 105
2023-04-07 | J | PCJ- 1-2 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-07 | H | PCH- 13-17, 14-16 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 36 | 2023-04-01 | 36
2023-04-07 | K | PCK- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-07 | H | PCH- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-07 | B | PC- 92-93 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-07 | H |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-04-01 | 2
2023-04-07 | D | PCD- 19-20 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-07 | D | PCD- 19-20 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-07 | D | PCD- 20-21 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-07 | D | PCD- 20-21 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-07 | D | PCD- 21-22 | Erection-U - Section Beam |  | 3 | 3 | 3 | [6 empty] | 2023-04-01 | 0
2023-04-07 | D | PCD- 21-22 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-09 | G | PCG-8 | Pier 1900 mm |  | 1 | 0.5 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-09 | G | PCG- 12,13,16,17 | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2023-04-01 | 20
2023-04-09 | A | PC- 61, 62 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-04-01 | 40
2023-04-09 | A | PC- 53, 58, 60 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-04-01 | 15
2023-04-09 | H | PCH- 9-10 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-09 | H | PCH- 10-11 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-09 | H | PCH- 15-17 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-09 | K | PCK- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-09 | H | PCH- 15-17 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-09 | B | PC- 88-89 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-09 | H |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 0.5 | 2023-04-01 | 0.5
2023-04-09 | D | PCD- 19-20 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-09 | D | PCD- 20-21 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-09 | D | PCD- 21-22 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-09 | D | PCD- 21-22 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-10 | G | PCG-8 | Pier 1900 mm |  | 1 | 0.5 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-10 | E | PCE-2 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-10 | C | PCC-19 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-10 | G | PCG-11 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-04-01 | 5
2023-04-10 | J | PCJ-10,11 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-04-01 | 10
2023-04-10 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-10 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-10 | H | PCH- 4-5 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-10 | B |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-11 | C | PC-18 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-11 | G | PCG- 11,12,14,17 | Pier 1600 mm |  | 4 | 2 | [5 empty] | 20 |  | 2023-04-01 | 20
2023-04-11 | K | PCK- 17,18 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-04-01 | 15
2023-04-11 | A | PC- 53 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-04-01 | 6
2023-04-11 | A | PC- 56,57,59,55 | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2023-04-01 | 20
2023-04-11 | H | PCH- 9-10 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-11 | H | PCH- 12-13 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-11 | B | PC- 81-83 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-11 | A | PC- 56-58 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-11 | K | PCK- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-11 | K | PCK- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-11 | B | PC- 89-90 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-12 | H | PCH- 19 | Pier Cap |  | 1 | 1 | [6 empty] | 43 | 2023-04-01 | 43
2023-04-12 | K | PCK- | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-12 | H | PCH-5-6 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-12 | K | PCK- 15-16 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-12 | H | PCH- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-12 | K | PCK- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-12 | H | PCH- 17-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-12 | H |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1.5 | 2023-04-01 | 1.5
2023-04-13 | H | PCH- 10-11 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-13 | K | PCK- 12-13 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-13 | H | PCH- 7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-13 | B | PC- 84-85 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-13 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-13 | B | PC- 83-84 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-13 | H |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-04-01 | 1
2023-04-13 | I | PCI- 8-9 | Erection-Track Beam with Nose |  | 11 | 11 | 11 | [6 empty] | 2023-04-01 | 0
2023-04-13 | I | PCI- 8-9 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-13 | I | PCI- 9-10 | Erection-Track Beam without Nose |  | 7 | 7 | 7 | [6 empty] | 2023-04-01 | 0
2023-04-13 | G | PCG- 14,15,16,11 | Pier 1600 mm |  | 5 | 2.5 | [5 empty] | 25 |  | 2023-04-01 | 25
2023-04-13 | A | PC- 56,57,55,54 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-04-01 | 18
2023-04-13 | C | PCC- 15,16,17 | PCC |  | 5 | 5 | [7 empty] | 2023-04-01 | 0
2023-04-14 | B | PC- 88-89 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-14 | K | PCK- 15-16 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-14 | A | PC- 57-59 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-14 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-14 | B | PC- 85-86 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-14 | H |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2023-04-01 | 1.5
2023-04-14 | I | PCI- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-14 | I | PCI- 9-10 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-04-01 | 0
2023-04-14 | I | PCI- 9-10 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-14 | I | PCI- 10-11 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-14 | I | PCI- 10-11 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-14 | A | PC- 59,61,62 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-04-01 | 18
2023-04-14 | H | PCH- 3 | Pier Cap |  | 1 | 1 | [6 empty] | 36 | 2023-04-01 | 36
2023-04-16 | D | PCD-23 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-04-01 | 35
2023-04-16 | A | PC- 58-60 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-16 | K | PCK- 9-10 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-16 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-16 | B | PC- 89-90 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-16 | F | PCF- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-16 | G |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-04-01 | 1
2023-04-16 | I |  | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-16 | I |  | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-16 | I |  | Erection-Track Beam without Nose |  | 9 | 9 | 9 | [6 empty] | 2023-04-01 | 0
2023-04-17 | J | PCJ- 9,10 | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 28 |  | 2023-04-01 | 28
2023-04-17 | K | PCK- 19,18 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 16 |  | 2023-04-01 | 16
2023-04-17 | A | PC- 60-58 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-17 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-17 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-17 | H |  | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-17 | K |  | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-17 | I | PCI- 6-7 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-17 | I | PCI- 7-8 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-18 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-18 | H |  | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-18 | H |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-18 | K |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-18 | I | PCI- 6-7 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-19 | A | PC- 47 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-19 | K | PCK- 15 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-04-01 | 18
2023-04-19 | B | PC- 92-93 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-19 | F | PCF- 7- 8 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-19 | A | PC- 61-63 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-19 | H | PCH- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-19 | B | PC- 90-91 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-19 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-04-01 | 2.5
2023-04-19 | H | PC- 96- PCH-1 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-19 | H | PC- 96- PCH-1 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-04-01 | 0
2023-04-19 | H | PC- 96- PCH-1 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-04-01 | 0
2023-04-20 | C | PCC- 16 | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-04-01 | 35
2023-04-20 | G | PCG- 7 | Pier 1900 mm |  | 1 | 0.3 | [5 empty] | 5 |  | 2023-04-01 | 5
2023-04-20 | J | PCJ- 8A, B,C,D, 9D, 11C, D | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 33 |  | 2023-04-01 | 33
2023-04-20 | H | PCH- 15-17 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-20 | H | PCH- 17-19 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-20 | A | PC- 61-63 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-20 | K | PCK- 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-20 | K | PCK- 13-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-20 | B | PC-91-92 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-20 | H | PCH- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-20 | H | PCH- 1-2 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-20 | H | PCH- 1-2 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-04-01 | 0
2023-04-21 | K | PCK- 15B, 14C, 13A | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-04-01 | 18
2023-04-21 | F | PCF- 9A, B, C | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 15 |  | 2023-04-01 | 15
2023-04-21 | K | PCK- 19 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-04-01 | 5
2023-04-21 | C | PCC- 16 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-04-01 | 5
2023-04-21 | H | PCH- 17 | Pier Cap |  | 1 | 1 | [6 empty] | 36 | 2023-04-01 | 36
2023-04-21 | H | PCH- 1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-04-01 | 0
2023-04-21 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-23 | C | PCC- 15 | RCC Foundation |  | 1 | 1 | [5 empty] | 27 |  | 2023-04-01 | 27
2023-04-23 | H | PCH- 5 | Pier Cap |  | 1 | 1 | [6 empty] | 39 | 2023-04-01 | 39
2023-04-23 | J |  | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 35 |  | 2023-04-01 | 35
2023-04-23 | A | PC- 49 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-24 | C | PCC- 15 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-04-01 | 5
2023-04-24 | K | PCK- 13B, 13E, 12E | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-04-01 | 18
2023-04-24 | F | PCG- 9A, B, C | Pier 1600 mm |  | 4 | 1.25 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-24 | A |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-24 | K |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-24 | H |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-25 | E | PCE- 18,17, 16, 15 | Pier 1600 mm |  | 7 | 2.5 | [5 empty] | 26 |  | 2023-04-01 | 26
2023-04-25 | A | PC- 48 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-25 | B |  | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-04-01 | 24
2023-04-25 | K |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-25 | B |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-27 | K | PCK -12 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-27 | E | PCE- 12,13,14 | Pier 1600 mm |  | 5 | 2 | [5 empty] | 15 |  | 2023-04-01 | 15
2023-04-27 | A | PC- 50 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-04-01 | 12
2023-04-28 | H | PCH- 15 | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-04-01 | 34
2023-04-28 | C | PCC- 17, 15 | RCC Foundation |  | 2 | 2 | [5 empty] | 89 |  | 2023-04-01 | 89
2023-04-28 | D | PCD- 22- 23 | Erection-U - Section Beam |  | 3 | 3 | 3 | [6 empty] | 2023-04-01 | 0
2023-04-28 | D | PCD- 22- 23 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-04-01 | 0
2023-04-29 | C | PCC- 17 | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-04-01 | 35
2023-04-29 | C | PCC- 16,17 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-04-01 | 15
2023-04-29 | F | PCF- 6,7,8 | Pier 1600 mm |  | 4 | 1.25 | [5 empty] | 12 |  | 2023-04-01 | 12
2023-04-29 | K | PCK- 12 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-04-01 | 18
2023-04-29 | I | PCD- 23- PCI-1 | Erection-U - Section Beam |  | 3 | 3 | 3 | [6 empty] | 2023-04-01 | 0
2023-04-29 | I | PCD- 23- PCI-1 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-04-01 | 0
2023-05-02 | C | PCC- 16, 15 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-05-01 | 12
2023-05-02 | C | PCC- 17 | Step Footing |  | 1 | 1 | [5 empty] | 6 |  | 2023-05-01 | 6
2023-05-02 | K | PCK- 12, 13 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-05-01 | 12
2023-05-02 | D | PCD- 22- 23 | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-05-01 | 0
2023-05-02 | A |  | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-03 | K | PCK- 13 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-05-01 | 6
2023-05-03 | C | PCC- 15, 17 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-05-01 | 18
2023-05-03 | F | PCF-4,5 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-05-01 | 20
2023-05-03 | B | PC- 91 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-05-01 | 6
2023-05-04 | A | PC- 51, 53, 55,64 | Pier 1600 mm |  | 4 | 4 | [5 empty] | 20 |  | 2023-05-01 | 20
2023-05-04 | G |  | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-05-01 | 5
2023-05-04 | D |  | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-05-01 | 0
2023-05-05 | B |  | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-05 | H |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-05 | D |  | Erection-Pre-cast Slab |  | 13 | 13 | 13 | [6 empty] | 2023-05-01 | 0
2023-05-07 | A | PC-52, 54, 56, 57 | Pier 1600 mm |  | 4 | 4 | [5 empty] | 20 |  | 2023-05-01 | 20
2023-05-07 | D | PCD- 22- 23 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-07 | I | PCI- 23-1 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-07 | A | PC- 63-65 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-07 | K | PCK- 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-07 | K | PCK- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-07 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-05-01 | 1
2023-05-08 | H | PCH-13 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-05-01 | 35
2023-05-08 | G | PCG- 6 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 7 |  | 2023-05-01 | 7
2023-05-08 | A | PC- 58 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-05-01 | 5
2023-05-09 | B | PC- 91A, B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-05-01 | 40
2023-05-09 | G | PCG- | Pier 1600 mm |  | 3 | 1.5 | [5 empty] | 20 |  | 2023-05-01 | 20
2023-05-09 | D | PCD- 22- 23 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-09 | D | PCD- 22- 23 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-05-01 | 0
2023-05-10 | D | PCD- 22- 23 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-10 | D | PCD- 22- 23 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-05-01 | 0
2023-05-10 | B | PC- 88-89 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-10 | K | PCK- 11-12 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-10 | A | PC -63-65 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-11 | C | PCC-5 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-05-01 | 35
2023-05-11 | B | PC-91 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-05-01 | 10
2023-05-11 | A | PC- 53 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-05-01 | 5
2023-05-11 | G | PCG- 8A, 8B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 15 |  | 2023-05-01 | 15
2023-05-11 | K | PCK- 14-15 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-11 | D | PCD- 22-23 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-11 | I | PCD- 23- PCI-1 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-05-01 | 0
2023-05-11 | I | PCD- 23- PCI-1 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-11 | I | PCD- 23- PCI-1 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-05-01 | 0
2023-05-12 | K |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-12 | K | PCK- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-12 | G | PCG-9 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 7 |  | 2023-05-01 | 7
2023-05-12 | A | PC- 58,60 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-05-01 | 10
2023-05-12 | I | PCD-23 - PCI-1 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-13 | A | PCA-47,48 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 11.5 |  | 2023-05-01 | 11.5
2023-05-13 | B | PCB-91 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 11.5 |  | 2023-05-01 | 11.5
2023-05-13 | H | H1-H2 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-05-01 | 0
2023-05-15 | C | PCC-6 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-05-01 | 37
2023-05-15 | K | PCK14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-15 | K |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 6 | 2023-05-01 | 6
2023-05-15 | H | H2-H3 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-15 | H | H2-H3 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-15 | H | H2-H3 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-15 | H | H2-H3 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-05-01 | 0
2023-05-16 | H | H2-H3 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-16 | H | H2-H3 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-05-01 | 0
2023-05-16 | H | H3-H4 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-05-01 | 0
2023-05-16 | K | PCF10-PCK19 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 25 | 2023-05-01 | 25
2023-05-17 | H | H3-H4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-17 | H | H3-H4 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-17 | H | H3-H4 | Erection-Track Beam without Nose |  | 9 | 9 | 9 | [6 empty] | 2023-05-01 | 0
2023-05-17 | K | K12-13 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 29 | 2023-05-01 | 29
2023-05-18 | H | H4-H5 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-18 | H | H4-H5 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-18 | F | PCF-3 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 11 |  | 2023-05-01 | 11
2023-05-18 | F | PCF-2 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 3 |  | 2023-05-01 | 3
2023-05-18 | C | PCC-7 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-05-01 | 37
2023-05-18 | K | PCK14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-18 | K | PCK14-15 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-05-01 | 24
2023-05-18 | B | PCK14-15 | h - Section Beam |  | 1 | 1 | [6 empty] | 14 | 2023-05-01 | 14
2023-05-19 | A | PCA-64 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-19 | H | H4-H5 | Erection-Track Beam without Nose |  | 11 | 11 | 11 | [6 empty] | 2023-05-01 | 0
2023-05-19 | K | K13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-19 | K | K13-14 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 25 | 2023-05-01 | 25
2023-05-19 | G | PCG20A,G9A,B | Pier 1600 mm |  | 3 | 3 | [5 empty] | 9 |  | 2023-05-01 | 9
2023-05-20 | K | K13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-20 | K | K13-14 | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2023-05-01 | 36
2023-05-20 | H | H4-5 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-20 | H | H5-6 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-20 | H | H5-6 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-20 | H | H5-6 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-05-01 | 0
2023-05-22 | C | PCC-8 | Pier Cap |  | 1 | 1 | [6 empty] | 44 | 2023-05-01 | 44
2023-05-22 | C | PCC-10A,B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 6 |  | 2023-05-01 | 6
2023-05-22 | C | PCC-19A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 3 |  | 2023-05-01 | 3
2023-05-22 | C | PCC-9B | Pier 1900 mm |  | 1 | 1 | [5 empty] | 4 |  | 2023-05-01 | 4
2023-05-22 | H | H5-H6 | Erection-Track Beam without Nose |  | 9 | 9 | 9 | [6 empty] | 2023-05-01 | 0
2023-05-22 | K | K13-14 | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-05-01 | 2
2023-05-22 | K | K13-14 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 32 | 2023-05-01 | 32
2023-05-22 | K | K13-12 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 14 | 2023-05-01 | 14
2023-05-22 | B | K13-12 | h - Section Beam |  | 3 | 3 | [6 empty] | 40 | 2023-05-01 | 40
2023-05-23 | H | E13-14 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 22 | 2023-05-01 | 22
2023-05-23 | E | E13-12 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 22 | 2023-05-01 | 22
2023-05-23 | I | I5-6 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-24 | H | H5-6 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-24 | H | H6-7 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-05-01 | 0
2023-05-24 | H | H6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-24 | G | G2-3 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 23 | 2023-05-01 | 23
2023-05-24 | A | G2-3 | h - Section Beam |  | 2 | 2 | [6 empty] | 23 | 2023-05-01 | 23
2023-05-24 | G | G2-3 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 22 | 2023-05-01 | 22
2023-05-24 | G | 20B | Pier 1600 mm |  | 1 | 1 | [5 empty] | 3 |  | 2023-05-01 | 3
2023-05-24 | A | A63 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-05-01 | 14
2023-05-25 | H | H6-7 | Erection-Track Beam without Nose |  | 9 | 9 | 9 | [6 empty] | 2023-05-01 | 0
2023-05-25 | K | K13-12 | Track Beam with Nose |  | 3 | 3 | [6 empty] | 32 | 2023-05-01 | 32
2023-05-25 | B | K13-12 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-25 | A | A62 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-05-01 | 13
2023-05-25 | C | PCC-9 | Pier Cap |  | 1 | 1 | [6 empty] | 39 | 2023-05-01 | 39
2023-05-25 | G | 9B | Pier 1600 mm |  | 1 | 1 | [5 empty] | 3 |  | 2023-05-01 | 3
2023-05-26 | H | PCH- 6-7 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-05-01 | 0
2023-05-26 | H | PCH- 7-8 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-05-01 | 0
2023-05-26 | H | PCH- 7-8 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-26 | F | PCF- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-26 | A | PC- 67-69 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-05-01 | 24
2023-05-26 | A | PC- 73-75 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-26 | H | PCE- 17-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-26 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-05-01 | 2.5
2023-05-28 | A | PC-74-76, 56-58 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-05-01 | 24
2023-05-28 | A | PC- 68-70 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-28 | G | PCG- 4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-28 | F | PCF- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-28 | H | PCE- 17-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-28 | H | PCH-7-8 | Erection-Track Beam without Nose |  | 6 | 6 | 6 | [6 empty] | 2023-05-01 | 0
2023-05-28 | H | PCH- 8-9 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-05-01 | 0
2023-05-28 | H | PCH- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-05-01 | 0
2023-05-29 | H | PCH- 7-8 | Erection-Track Beam without Nose |  | 7 | 7 | 7 | [6 empty] | 2023-05-01 | 0
2023-05-29 | A | PC- 61-63 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-29 | A | PC- 68-70 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-05-01 | 24
2023-05-29 | G | PCG- 4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-29 | G | PCG- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-29 | F | PCF- 4-5 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-29 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-05-01 | 1
2023-05-29 | C | PCC-15A,15B,18A,19A,17B,16B | Pier 1600 mm |  | 6 | 3 | [5 empty] | 30 |  | 2023-05-01 | 30
2023-05-29 | A | PC-52 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-05-01 | 14
2023-05-29 | K | PCK-14 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-05-01 | 6
2023-05-30 | H | PCH- 11-12 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-30 | A | PC- 75-77 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-30 | A | PC-58-62 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-05-01 | 24
2023-05-30 | H | PCH- 8-9 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-30 | G | PCG- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-31 | A | PC- 63-65 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-31 | A | PC- 69-71 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-31 | G | PCG- 6-7 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-05-01 | 24
2023-05-31 | F | PCF- 4-5 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-31 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1.5 | 2023-05-01 | 1.5
2023-05-31 | A | PC- 59 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-05-01 | 12
2023-05-31 | C | PC-15A,B,16B,19A,B | Pier 1600 mm |  | 5 | 5 | [5 empty] | 21 |  | 2023-05-01 | 21
2023-05-31 | B | PC- 91A, B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-05-01 | 10
2023-05-31 | G | PCG- 12B | Pier 1600 mm |  | 1 | 1 | [5 empty] | 3 |  | 2023-05-01 | 3
2023-05-31 | D |  | Track Laying |  |  |  |  | 200 | [5 empty] | 2023-05-01 | 0
2023-06-01 | C | PCC-19A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-01 | A | PC- 57 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-06-01 | 14
2023-06-04 | I | PCI- 1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-04 | I | PCI- 1-2 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-04 | I | PCI- 2-3 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-04 | A | PC- 60,58 | Pier Cap |  | 2 | 2 | [6 empty] | 25 | 2023-06-01 | 25
2023-06-04 | G | PCG- 11A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-04 | C | PCC- 16A,B, 17A, B | Pier 1600 mm |  | 4 | 4 | [5 empty] | 22 |  | 2023-06-01 | 22
2023-06-05 | A | PC-51 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-06-01 | 13
2023-06-05 | G | PCG-11, 21 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-05 | C | PCC- 18A,17A,B,16A | Pier 1600 mm |  | 4 | 4 | [5 empty] | 20 |  | 2023-06-01 | 20
2023-06-05 | K | PCK- 14C,D | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-05 | I | PCI- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-05 | I | PCI- 2-3 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-05 | I | PCI- 3-4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-05 | I | PCI- 3-4 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-05 | I |  | Erection-Pre-cast Slab |  | 6 | 6 | 6 | [6 empty] | 2023-06-01 | 0
2023-06-06 | A | PC- 53 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-06 | C | PCC-18 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-06 | K | PCK- 11 | PCC |  | 4 | 4 |  |  |  | 23 |  |  |  | 2023-06-01 | 23
2023-06-06 | I | PCI- 4-5 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-07 | A | PC- 56 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-06-01 | 13
2023-06-07 | K | PCK- | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-06-01 | 15
2023-06-07 | G | PCG- | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-07 | A | PC- 62-64, 65-67 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-07 | A | PC- 70-72 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-07 | I | PCI- 5-6 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-07 | I | PCI- 5-6 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-08 | A | PC- 64-66 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-08 | H | PCH- 9-10 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-08 | A | PC- 74-76 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-08 | G | PCG- 6-7, 7-8 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-08 | G | PCG- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-08 | G | PCE- 16-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-08 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-06-01 | 2.5
2023-06-08 | I | PCI- 4-5 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-08 | I | PCI- 5-6 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-08 | I | PCI- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-08 | K | PCK- 16 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-06-01 | 15
2023-06-08 | G | PCG- 14, 2 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-09 | A | PC- 73-75 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-09 | A | PC- 73-75, 70-72 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-09 | G | PCG- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-09 | F | PCF- 4-5, 7-8 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-09 | H | PCH- 8-9 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-09 | K | PCK- 14 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-06-01 | 40
2023-06-09 | K | PCK- 14 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 6 |  | 2023-06-01 | 6
2023-06-09 | G | PCG- 2 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 4 |  | 2023-06-01 | 4
2023-06-09 | B | PC- 91A, B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 8 |  | 2023-06-01 | 8
2023-06-09 | A | PC- 54 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-06-01 | 13
2023-06-09 | K | PCK- 9 | PCC |  | 4 | 4 |  |  |  | 24 |  |  |  | 2023-06-01 | 24
2023-06-11 | A | PC- 55 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-06-01 | 13
2023-06-11 | K | PCK- 14 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-11 | K | PCK- 14 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 7 |  | 2023-06-01 | 7
2023-06-11 | G |  | Pier 1600 mm |  | 1 | 1 | [5 empty] | 3 |  | 2023-06-01 | 3
2023-06-11 | H | PCH- 8-9 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-11 | H | PCH- 8-9 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-11 | A | PC- 67-69 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-11 | A | PC- 71-73 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-11 | A | PC- 71-73, 75-77 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-11 | G | PCG- 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-11 | G | PCG- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-11 | F | PCF- 4-5 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-12 | K | PCK- 16 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-06-01 | 15
2023-06-12 | A | PC- 72-74, 74-76 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-12 | A | PC- 71-73 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-12 | G | PCG- 9-10, 10-11 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-12 | G | PCG- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-12 | G | PCG- 4-5 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-13 | A | PC- 69-71 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-13 | A | PC- 72-74, 76-78 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-13 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-13 | F | PCF- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-13 | D |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 2.5 | 2023-06-01 | 2.5
2023-06-13 | K | PCk - 14 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-06-01 | 12
2023-06-13 | G | PCG-3 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-13 | E | PCE-3 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 3 |  | 2023-06-01 | 3
2023-06-13 | E | PCE-2 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 3 |  | 2023-06-01 | 3
2023-06-13 | K | PCK- 13,16 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 11 |  | 2023-06-01 | 11
2023-06-14 | K | PCK- 12 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-14 | E | PCE- 3 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-14 | K | PCK- 11B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-06-01 | 20
2023-06-14 | K | PCK-5,6,8,9 | PCC |  | 15 | 15 |  |  |  | 45 |  |  |  | 2023-06-01 | 45
2023-06-14 | A | PC- 66-68 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-14 | A | PC- 72-74, 76-78 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-14 | G | PCG- 4-5 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-14 | F | PCF- 7-8 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-14 | A | PC- 73/74- 75/76 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-14 | A | PC- 73/74- 75/76 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-15 | K | PCK- 11A | RCC Foundation |  | 1 | 1 | [5 empty] | 30 |  | 2023-06-01 | 30
2023-06-15 | K | PCK- 11B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-15 | A | PC- 75-77 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-15 | A | PC- 77-79 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-15 | G | PCG- 4-5, 5-6 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-15 | F | PCF- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-15 | A | PC- 73/74- 75/76 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-15 | A | PC- 73/74- 75/76 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-15 | A | PC- 73/74- 75/76 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-16 | K | PCK- 11C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-06-01 | 20
2023-06-16 | K | PCK- 11A | Step Footing |  | 1 | 1 | [5 empty] | 11 |  | 2023-06-01 | 11
2023-06-16 | K | PCK- 12B | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-16 | G | PCG- 1,2 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-16 | A | PC- 68-70 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-16 | H | PCH- 10-11 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-16 | A | PC- 77-79 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-16 | J | PCJ- 4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-16 | G | PCG- 5-6, 1-2 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-16 | F | PCF- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-16 | A | PC- 51 | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-06-01 | 15
2023-06-18 | A | PC- 77-79 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-18 | A | PC- 78-80 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-18 | J | PCJ- 4-5 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-18 | G | PCG- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-18 | F | PCF- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-18 | K | PCK- 11D, 9B | RCC Foundation |  | 2 | 2 | [5 empty] | 49 |  | 2023-06-01 | 49
2023-06-18 | K | PCK- 11C | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-18 | K | PCK- 11D | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-06-01 | 6
2023-06-18 | K | PCK- 12 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 9 |  | 2023-06-01 | 9
2023-06-18 | E | PCE- 3 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-19 | K | PCK- 9C, 9D | RCC Foundation |  | 2 | 2 | [5 empty] | 55 |  | 2023-06-01 | 55
2023-06-19 | K | PCK- 11D | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-19 | K | PCK- 12A, 12C, 15C | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 14 |  | 2023-06-01 | 14
2023-06-19 | A | PC- 70-72 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-19 | A | PC- 78-80 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-19 | K | PCK- 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-19 | G | PCG- 2-3, 5-6, 6-7 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-06-01 | 36
2023-06-19 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-06-01 | 2.5
2023-06-19 | A | PC- 71/72- 73/74 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-19 | A | PC- 71/72- 73/74 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-19 | A | PC- 71/72- 73/74 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-20 | K | PCK- 9A, 8B | RCC Foundation |  | 2 | 2 | [5 empty] | 57 |  | 2023-06-01 | 57
2023-06-20 | K | PCK- 11A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-06-01 | 6
2023-06-20 | K | PCK- 16B | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-06-01 | 4
2023-06-20 | F | PCF- 4A, 6A | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-06-01 | 8
2023-06-20 | A | PC- 79-81, 82-83 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-20 | H | PCH- 11-13 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-20 | A | PC- 79-81 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-20 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-20 | G | PCG- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-20 | A | PC- 69/70- 71/72 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-20 | A | PC- 69/70- 71/72 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-20 | A | PC- 69/70- 71/72 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-21 | K | PCK- 8C | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-06-01 | 20
2023-06-21 | K | PCK- 9D | Step Footing |  | 1 | 1 | [5 empty] | 12 |  | 2023-06-01 | 12
2023-06-21 | K | PCK- 11B, D | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-06-01 | 12
2023-06-21 | K | PCK- 12, 13, 16 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 16 |  | 2023-06-01 | 16
2023-06-21 | A | PC- 76-78 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-21 | B | PC- 80-82 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-21 | G | PCG- 5-6, 4-5 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-21 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-21 | A | PC- 69/70- 73/74 | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-06-01 | 0
2023-06-22 | B | PC- 83-84 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-22 | K | PCF- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-22 | K | PCK- 7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-22 | G | PCG- 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-22 | G | PCG- 4-5 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-22 | A | PC- 67/68- 69/70 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-22 | A | PC- 67/68- 69/70 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-22 | A | PC- 67/68- 69/70 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-22 | A | PC- 65/66- 67/68 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-22 | K | PCK- 9D | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-06-01 | 35
2023-06-22 | K | PCK- 8C | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-22 | K | PCK- 9A | PCC |  | 1 | 1 |  |  |  | 3 |  |  |  | 2023-06-01 | 3
2023-06-23 | K | PCK- 6-7, 5-6 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-23 | G | PCG- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-23 | A | PC- 67/68- 69/70 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-23 | A | PC- 65/66- 67/68 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-23 | A | PC- 65/66- 67/68 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-23 | A | PC- 65/66- 67/68 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-23 | K | PCK- 9B, 9A | Step Footing |  | 2 | 2 | [5 empty] | 18 |  | 2023-06-01 | 18
2023-06-23 | K | PCK- 15A, 15B, 12B | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-06-01 | 15
2023-06-23 | H | PCH- 11 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-06-01 | 37
2023-06-23 | K | PCK- 11D | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-06-01 | 12
2023-06-25 | A | PC- 63/64- 65/66 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-25 | A | PC- 63/64- 65/66 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-25 | A | PC- 63/64- 65/66 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-25 | A | PC- 78-80 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-25 | B | PC- 84-85 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-25 | H | PCH- 13-15 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-25 | F | PCF- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-25 | G | PCG- 4-5, 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-25 | F | PCF- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-25 | K | PCK- 15,12,13 | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 34 |  | 2023-06-01 | 34
2023-06-25 | K | PCK- 9E,F | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-06-01 | 12
2023-06-26 | K | PCK-8 | Step Footing |  | 1 | 1 | [5 empty] | 9 |  | 2023-06-01 | 9
2023-06-26 | K | PCK-8 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-06-01 | 6
2023-06-26 | F | PCF- 2,3 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 13 |  | 2023-06-01 | 13
2023-06-26 | A | PC- 63/64- 65/66 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-26 | A | PC- 61/62- 63/64 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-26 | A | PC- 61/62- 63/64 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-26 | A | PC- 61/62- 63/64 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-06-01 | 0
2023-06-26 | B | PC- 86-87 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-26 | F | PCF- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-26 | H | PCH- 16-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-26 | G | PCG- 6-7, 5-6 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-26 | K | PCF- 10A- PCK19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | K | PCK- 12 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 9 |  | 2023-06-01 | 9
2023-06-27 | F | PCF- 2 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-06-01 | 5
2023-06-27 | G | PCG- 1, 2 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-27 | K | PCK- 9 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-06-01 | 6
2023-06-27 | K | PCK- 8 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-27 | A | PC- 80-82 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | B | PC- 87-88 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | H | PCH- 15-17 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | H | PCH- 16-18 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | F | PCF- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | G | PCG- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-27 | A | PC- 59/60- 61/62 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-28 | K | PCK- 8 | RCC Foundation |  | 1 | 1 | [5 empty] | 47 |  | 2023-06-01 | 47
2023-06-28 | K | PCK- 9 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-06-01 | 12
2023-06-28 | F | PCF- 2,3 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-06-01 | 10
2023-06-28 | A | PC- 59/60- 61/62 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-28 | A | PC- 59/60- 61/62 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-28 | B | PC- 90-91 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-28 | H | PCH- 18-20 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-06-01 | 24
2023-06-28 | G | PCG- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-28 | F | PCF- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-28 | G |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-06-01 | 2
2023-06-28 | H | PCH- 10 | Pier Cap |  | 1 | 1 | [6 empty] | 47 | 2023-06-01 | 47
2023-06-29 | B | PC- 91 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-06-01 | 37
2023-06-29 | K | PCK- 5,6 | RCC Foundation |  | 5 | 5 | [5 empty] | 100 |  | 2023-06-01 | 100
2023-06-29 | A | PC- 59/60- 61/62 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-29 | A | PC- 59/60- 61/62 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-06-01 | 0
2023-06-29 | A | PC- 59/60- 61/62 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-06-01 | 0
2023-06-29 | A |  | Erection-Pre-cast Slab |  | 6 | 6 | 6 | [6 empty] | 2023-06-01 | 0
2023-06-30 | K | PCK- 5,6 | RCC Foundation |  | 7 | 7 | [5 empty] | 140 |  | 2023-06-01 | 140
2023-06-30 | B | PC- 83-84 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-30 | F | PCF- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-06-30 | G | PCG- 8-9 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-06-01 | 36
2023-06-30 | K | PCK- 10-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-06-01 | 12
2023-07-02 | K |  | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-07-01 | 10
2023-07-02 | F |  | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-07-01 | 15
2023-07-02 | K | PCK- 8 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-07-01 | 10
2023-07-02 | B | PC- 91-92 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-02 | G | PCG- 9-10, 6-7 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-02 | F | PCF- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-02 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1.5 | 2023-07-01 | 1.5
2023-07-03 | K | PCK- 8 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-07-01 | 12
2023-07-03 | F | PCF- 2,3 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-07-01 | 15
2023-07-03 | F | PCF- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-03 | F | PCF- 2-3, 3-4 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-03 | G | PCG- 10-11, 6-7 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-03 | K | PCK- 19-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-03 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-07-01 | 1
2023-07-04 | K | PCK- 14 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-07-01 | 10
2023-07-04 | F | PCF- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-04 | K | PCK- 13-14 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-04 | G | PCG- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-04 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-07-01 | 1
2023-07-05 | K | PCK- 8 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-07-01 | 12
2023-07-05 | F | PCF- 2 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-07-01 | 4
2023-07-05 | B | PC- 85-86 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-05 | H | PCH- 17-19 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-05 | K | PCK- 13-14 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-05 | F | PCF- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-05 | A | PC- 57/58- 59/60 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-05 | A | PC- 57/58- 59/60 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-06 | K | PCK- 13 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-07-01 | 10
2023-07-06 | J | PCJ- 2, 3, 4 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-07-01 | 25
2023-07-06 | C | PCC- 20 | Pier Cap |  | 1 | 1 | [6 empty] | 43 | 2023-07-01 | 43
2023-07-06 | G | PCG- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-06 | G | PCG- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-06 | K | PCK- 7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-06 | G | PCG- 7-8 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-06 | F | PCF- 4-5 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-06 | A | PC- 57/58- 59/60 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-06 | A | PC- 57/58- 59/60 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-06 | A | PC- 57/58- 59/60 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-06 | A | PC- 55/56 - 57/58 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-06 | A | PC- 55/56 - 57/58 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-06 | A | PC- 55/56 - 57/58 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-07 | K | PCK- 6 | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2023-07-01 | 25
2023-07-07 | A | PC- 55/56 - 57/58 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-07 | A | PC- 55/56 - 57/58 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-07 | A | PC- 55/56 - 57/58 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-07 | B | PC- 84-85 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-07 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-07 | G | PCG- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-09 | K | PCK- 6,5 | Step Footing |  | 4 | 4 | [5 empty] | 20 |  | 2023-07-01 | 20
2023-07-09 | F | PCF- 4 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 4.5 |  | 2023-07-01 | 4.5
2023-07-09 | J | PCJ- 1, 2,3,4 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 11.5 |  | 2023-07-01 | 11.5
2023-07-09 | G | PCG- 11-12 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-09 | H | PCH- 10,11 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-09 | G | PCG- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-09 | K | PCK- 7-8 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-09 | K | PCK- 12-13 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-10 | G | PCG- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-10 | K | PCK- 7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-10 | K | PCK- 12-13, 17-18 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-10 | G | PCG- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-10 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-07-01 | 2.5
2023-07-11 | K | PCK- 5,6 | Step Footing |  | 5 | 5 | [5 empty] | 25 |  | 2023-07-01 | 25
2023-07-11 | K | PCK- 8 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-07-01 | 12
2023-07-11 | F | PCF- 6 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 3 |  | 2023-07-01 | 3
2023-07-11 | J | PCJ- 3 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-07-01 | 8
2023-07-11 | G | PCG- 11-12 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-11 | G | PCG- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-11 | K | PCK- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-11 | K | PCK- 13-14, 17-18 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-12 | K | PCK- 6 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-07-01 | 18
2023-07-12 | F | PCF- 2, 5 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 13 |  | 2023-07-01 | 13
2023-07-12 | F | PCF- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-12 | B | PC- 83-84 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-12 | F | PCF- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-12 | K | PCK- 13-14, 17-18, PCF- 10-PCK-10 | Track Beam without Nose |  | 4 | 4 |  |  | 1 |  |  |  | 48 | 2023-07-01 | 48
2023-07-12 | A | PC- 53/54- 55/56 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-12 | A | PC- 53/54- 55/56 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-07-01 | 0
2023-07-12 | A | PC- 53/54- 55/56 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-12 | A | PC- 51/52- 53/54 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-12 | A | PC- 51/52- 53/54 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-07-01 | 0
2023-07-12 | A | PC- 51/52- 53/54 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-13 | C | PCC- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 53 | 2023-07-01 | 53
2023-07-13 | K | PCK- 6 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-07-01 | 12
2023-07-13 | F | PCF- 1 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-07-01 | 10
2023-07-13 | J | PCJ- 1 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-07-01 | 5
2023-07-13 | F | PCF- 4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-13 | K | PCK- 17-18, 18-19 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-13 | A | PC- 53/54- 55/56 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-13 | A | PC- 51/52- 53/54 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-13 | A |  | Erection-Pre-cast Slab |  | 18 | 18 | 18 | [6 empty] | 2023-07-01 | 0
2023-07-14 | K | PCK- 5,6 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-07-01 | 12
2023-07-14 | F | PCF-1 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 8 |  | 2023-07-01 | 8
2023-07-14 | F | PCF- 2-3 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-14 | G | PCG- 11-12 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-14 | K | PCK- 7-8(Trapezoidal) | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-07-01 | 12
2023-07-14 | K | PCK- 11-12, 16-17, 18-19 | Track Beam without Nose |  | 4 | 4 | [6 empty] | 48 | 2023-07-01 | 48
2023-07-14 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-07-01 | 2.5
2023-07-16 | A | PC- 49/50- 51/52 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-16 | A | PC- 49/50- 51/52 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-16 | A | PC- 49/50- 51/52 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-16 | A | PC- 47/48- 49/50 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-16 | A | PC- 47/48- 49/50 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-16 | B | PC- 85-86 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-16 | F | PCF- 2-3 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-16 | K | PCK- 13-14, 17-18 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-17 | F | PCF- 1 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-07-01 | 5
2023-07-17 | J | PCJ- 2, 3, 4 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-07-01 | 15
2023-07-17 | A | PC- 49/50- 51/52 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-17 | A | PC- 49/50- 51/52 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-17 | A | PC- 49/50- 51/52 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-17 | A | PC- 47/48- 49/50 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-17 | A | PC- 47/48- 49/50 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-17 | A |  | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-07-01 | 0
2023-07-17 | F | PCF- 3-4 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-17 | G | PCG- 16-17 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-17 | F | PCF- 7-8 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-17 | K | PCK- 12-13, 16-17, 18-19 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-18 | B | PC- 86-87 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-18 | F | PCF- 3-4 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-18 | K | PCK- 10-11, 16-17, 17-18 | Track Beam without Nose |  | 4 | 4 | [6 empty] | 48 | 2023-07-01 | 48
2023-07-18 | C | PCC- 11 | Pier Cap |  | 1 | 1 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-18 | K | PCK- 11 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-07-01 | 25
2023-07-18 | K | PCK- 5 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2023-07-01 | 24
2023-07-18 | K | PCK- 10 | PCC |  | 3 | 3 |  |  |  | 9 |  |  |  | 2023-07-01 | 9
2023-07-19 | F | PCF- 4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-19 | K | PCK- 6-7 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-07-01 | 12
2023-07-19 | K | PCK-10-11, 15-16, 10-19 | Track Beam without Nose |  | 4 | 4 | [6 empty] | 48 | 2023-07-01 | 48
2023-07-19 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-07-01 | 2
2023-07-19 | A | PC- 47/48- 49/50 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-19 | A | PC- 45/46- 47/48 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-19 | A | PC- 45/46- 47/48 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-07-01 | 0
2023-07-19 | A | PC- 45/46- 47/48 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-20 | K | PCK- 10 | PCC |  | 1 | 1 |  |  |  | 7 |  |  |  | 2023-07-01 | 7
2023-07-20 | K | PCK- 5 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-07-01 | 6
2023-07-20 | C | PCC-10 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-07-01 | 37
2023-07-20 | A |  | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-07-01 | 0
2023-07-20 | J | PCF-1 - PCJ- 1 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-20 | J | PCJ-2 -3 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-20 | H | PCH- 11-13 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-20 | J | PCJ- 3-5 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-21 | K | PCK- 7 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-07-01 | 6
2023-07-21 | K | PCK- 11 | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 24 |  | 2023-07-01 | 24
2023-07-21 | J | PCJ- 7 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 6 |  | 2023-07-01 | 6
2023-07-21 | J | PCF-1 - PCJ- 1 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-21 | J | PCF-1 - PCJ- 1 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-21 | H | PCH- 13-15 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-21 | J | PCF-1 - PCJ- 1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-21 | K | PCK- 11-12 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-23 | K | PCK- 7A, B | RCC Foundation |  | 2 | 2 | [5 empty] | 54 |  | 2023-07-01 | 54
2023-07-23 | B | PC- 87-88 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-23 | J | PCF-1 - PCJ- 1 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-23 | I | PCI- 10-17A | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-07-01 | 12
2023-07-23 | K | PCK- 13-14 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-23 | F | PCF- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-23 | J | PCF-1 - PCJ- 1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-24 | K | PCK- 7 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-07-01 | 12
2023-07-24 | B | PC- 91-92 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-24 | B | PC- 91-92 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-24 | B | PC- 91-92 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-07-01 | 0
2023-07-24 | J | PCJ- 3-4 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-24 | J | PCF-1 - PCJ- 1 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-24 | I | PCI- 10-17A | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-07-01 | 12
2023-07-24 | K | PCK- 13-14,10-19,18-19 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-24 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-07-01 | 2
2023-07-25 | F | PCF- 4-5 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-25 | K | PCK- 10-11, 12-13, 10-19 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-25 | B | PC- 91-92 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-25 | B | PC- 91-92 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-25 | B | PC- 91-92 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-25 | B | PC- 91-92 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-26 | K | PCK- 10- 9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-26 | K | PCK- 10- 9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-26 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 0.5 | 2023-07-01 | 0.5
2023-07-27 | F | PCF- 7-8 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-27 | J | PCJ- 3-4 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-27 | J | PCJ- 4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-27 | H | PCH- 13-15 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-27 | K | PCK- 9-10, 14-15 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-27 | H | PCH- 9-10 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-27 | H | PCH- 9-10 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-27 | K | PCK- 10 | RCC Foundation |  | 2 | 2 | [5 empty] | 48 |  | 2023-07-01 | 48
2023-07-28 | C | PCC-15 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-07-01 | 37
2023-07-28 | F | PCF- 3A | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-07-01 | 13
2023-07-28 | K | PCK- 7 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-07-01 | 40
2023-07-28 | C | PCH- 19- PCC-1, C3-4 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-28 | I | PCI- 6-7 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-07-01 | 12
2023-07-28 | K | PCK- 9-10, 15-16 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-28 | H | PCH- 19- PCC-1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-28 | H | PCH- 9-10 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-28 | H | PCH- 9-10 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-07-01 | 0
2023-07-28 | H | PCH- 9-10 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-28 | H | PCH- 10-11 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-28 | H | PCH- 10-11 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-28 | H | PCH- 10-11 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-07-01 | 0
2023-07-30 | K | PCK- 7 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-07-01 | 40
2023-07-30 | F | PCF- 2A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-07-01 | 14
2023-07-30 | C | PCH- 19- PCC-1, C1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-30 | C | PCH- 19- PCC-1 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-30 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-30 | H | PCH- 10-11 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-30 | H | PCH- 10-11 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-07-01 | 0
2023-07-30 | H | PCH- 10-11 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-07-01 | 0
2023-07-31 | K | PCK- 7 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-07-01 | 40
2023-07-31 | H | PCC- 1-2 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-31 | C | PCC- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-07-01 | 12
2023-07-31 | C | PCC- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-07-01 | 24
2023-07-31 | I | PCI- 6-7 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-07-01 | 12
2023-07-31 | C | PCH- 19- PCC-1 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-07-01 | 36
2023-07-31 | D |  | Track Laying |  |  |  |  | 420 | [5 empty] | 2023-07-01
2023-08-01 | K | PCK- 10, 7 | Step Footing |  | 6 | 6 | [5 empty] | 35 |  | 2023-08-01 | 35
2023-08-01 | F | PCF- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-08-01 | 14
2023-08-01 | C | PCC- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-01 | H | PCC- 1-2 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-01 | H | PCH- 19- PCC-1 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-01 | K | PCK- 19-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-01 | C |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-08-01 | 1
2023-08-02 | K | PCK- 10, 7 | Step Footing |  | 4 | 4 | [5 empty] | 35 |  | 2023-08-01 | 35
2023-08-02 | K |  | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-08-01 | 4
2023-08-02 | C | PCC-17 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 8 |  | 2023-08-01 | 8
2023-08-02 | C | PCH-19 - PCC-1 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-08-01 | 24
2023-08-02 | C | PCH-19 - PCC-1 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-02 | F | PCF- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-02 | J | PCF-1 - PCJ- 1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-03 | K | PCK-10 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-03 | F | PCF-6,7,8 | Pier 1600 mm |  | 5 | 2.25 | [5 empty] | 25 |  | 2023-08-01 | 25
2023-08-03 | K | PCK-8,9 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 16 |  | 2023-08-01 | 16
2023-08-03 | I | PCC-2-3 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-03 | C | PCC-2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-03 | I | PCI- 10-17A | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-03 | C | PCH- 19- PCC-1 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-03 | K | PCK- 17-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-03 | J | PCJ- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-04 | F | PCF-5 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 13 |  | 2023-08-01 | 13
2023-08-04 | C | PCC- 2-3 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-04 | H | PCH- 10-11 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-04 | H | PCH- 10-11 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-04 | G | PCC- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-04 | J | PCJ- 2-3 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-08-01 | 36
2023-08-04 | K | PCK- 17-18 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-06 | J | PCJ- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-08-01 | 13
2023-08-06 | F | PCF- 7,8 | Pier 1600 mm |  | 5 | 2.25 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-06 | K | PCK- 7,8 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-06 | K | PCK- 10 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-06 | G | PCC- 2-3 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-06 | C | PCC- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-06 | F | PCF- 5-6, 1-2 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-06 | J | PCF-1 - PCJ- 1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-06 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2 | 2023-08-01 | 2
2023-08-06 |  | Abutment | Abutment wall- PART-A | [6 empty] | 20 |  |  |  | 2023-08-01 | 20
2023-08-07 | K | PCK- 7 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-07 | K | PCK- 8 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 12 |  | 2023-08-01 | 12
2023-08-07 | F | PCF- 8 | Pier 1600 mm |  | 1 | 0.33 | [5 empty] | 4 |  | 2023-08-01 | 4
2023-08-07 | C | PCC- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-07 | K | PCK- 15-16 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-07 | J | PCF-1 - PCJ- 1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-07 | B |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 1 | 2023-08-01 | 1
2023-08-07 | J | PCJ-2 | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-08-01 | 37
2023-08-08 | F | PCF- 7A, 9A,B,C | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 20 |  | 2023-08-01 | 20
2023-08-08 | K | PCK- 19A,B,C, 12C,D, 9A | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 23 |  | 2023-08-01 | 23
2023-08-08 | C | PCC- 4-5 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-08 | G | PCC- 4-5 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-08 | C | PCC- 2-3 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-08 | H | PCH- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-08 | J | PCF-1 - PCJ- 1 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-08 | H | PCH- 11-13 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-08 | H | PCH- 13-15 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-09 | J | PCJ- 3 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-08-01 | 14
2023-08-09 | K | PCK- 7 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-09 | K | PCK- 12B, 8C,E | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-08-01 | 15
2023-08-09 | C | PCC- 4-5 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-09 | G | PCC- 4-5 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-09 | F | PCF- 1- PCJ-1 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-09 | H | PCH- 10-12 | Track Beam with Nose |  | 1 | 1 |  |  | 2 |  |  |  | 12 | 2023-08-01 | 12
2023-08-09 | F | PCF- 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-09 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-09 | K | PCK- 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-09 | G |  | Pre-cast Slab |  | 4 | 4 | [6 empty] | 2 | 2023-08-01 | 2
2023-08-09 | H | PCH- 11-13 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-09 | H | PCH- 11-13 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-09 | H | PCH- 13-15 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-09 | H | PCH- 13-15 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-09 | D |  | Track Laying | [10 empty] | 2023-08-01 | 0
2023-08-09 | A |  | Track Laying |  |  |  |  | 288 | [5 empty] | 2023-08-01 | 0
2023-08-10 | K | PCK- 13 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-08-01 | 10
2023-08-10 | C | PCC-4-5 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-10 | C | PCC-4-5 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-10 | J | PCJ-1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-10 | H | PCH- 10-12 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-10 | F | PCF-8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-10 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-11 | F | PCF-3B | Pier Cap |  | 1 | 1 | [6 empty] | 33 | 2023-08-01 | 33
2023-08-11 | J | PCJ- 2A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-08-01 | 14
2023-08-11 | K | PCK- 14,12 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 18 |  | 2023-08-01 | 18
2023-08-11 | H | PCH- 9-10 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-11 | C | PCC- 3-4 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-11 | J | PCJ- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-11 | H | PCH- 16-18 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-11 | J | PCJ- 3-4, 1-2 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-11 | K | PCK | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-11 | H | PCH- 13-15 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-11 | H | PCH-15-17 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-11 | H | PCH-15-17 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-11 | H | PCH-15-17 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-10 | H | PCH- 11-13 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-10 | H | PCH- 11-13 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-10 | H | PCH- 11-13 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-10 | H | PCH- 11-13 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-13 | H | PCH- 10-12 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-13 | I | PCI- 10-11 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-08-01 | 24
2023-08-13 | F | PCF- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-13 | B | PC- 86-87 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-13 | J | PCJ- 1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-13 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-08-01 | 2.5
2023-08-15 | C | PCC- 16A,B | Pier 1600 mm |  | 2 | 1 | [5 empty] | 10 |  | 2023-08-01 | 10
2023-08-15 | K | PCK- 18, 16, 14,12 | Pier 1600 mm |  | 10 | 2.5 | [5 empty] | 41 |  | 2023-08-01 | 41
2023-08-15 | B | PC- 91-92 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-15 | C | PCC- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-15 | I | PCI- 10-11 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-15 | H | PC- 87-88 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-15 | J | PCJ- 1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-16 | K | PCK- 18,12,14,15,16 | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 24 |  | 2023-08-01 | 24
2023-08-16 | J | PCJ- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-16 | H | PCH- 14-16 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-16 | J | PCJ- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-16 | I | PCI- 10-11, 8-9 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-08-01 | 24
2023-08-16 | F | PCF- 5-6, 8-9 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-16 | J | PCJ- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-17 | C | PCC-18 | Pier 1600 mm |  | 1 | 0..25 | [5 empty] | 5 |  | 2023-08-01 | 5
2023-08-17 | F | PCF- 2B | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-08-01 | 34
2023-08-17 | J | PCJ- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-17 | J | PCJ- 2-3 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-17 | F | PCF- 8-9 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-17 | J | PCJ- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-18 | C | PCC-18 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-08-01 | 5
2023-08-18 | K | PCK- 6 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-08-01 | 25
2023-08-18 | J | PCJ- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 32 | 2023-08-01 | 32
2023-08-18 | J | PCJ- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-18 | H | PCH- 14-16 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-18 | J | PCJ- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-18 | I | PCI- 8-9 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-18 | I | PCI- 6-7 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-20 | K | PCK- 6,7 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 12 |  | 2023-08-01 | 12
2023-08-20 | C | PCC- 4-5 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-20 | C | PCC- 4-5 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-20 | I | PCI- 6-7 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-08-01 | 36
2023-08-20 | F | PCF- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-20 | D |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-08-01 | 2.5
2023-08-21 | F | PCF- 4A | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-08-01 | 14
2023-08-21 | G | PCG- 6 | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-08-01 | 34
2023-08-21 | K | PCK- 5 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-08-01 | 25
2023-08-21 | F | PCF- 8-9 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-21 | F | PCF- 8-9 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-21 | F | PCF- 9-10, 5-6 | Track Beam without Nose |  | 4 | 4 | [6 empty] | 48 | 2023-08-01 | 48
2023-08-22 | F | PCF- 4 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-08-01 | 8
2023-08-22 | F | PCF- 5-6 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-22 | F | PCF- 5-6, 6-7 | Track Beam with Nose |  | 3 | 3 | [6 empty] | 36 | 2023-08-01 | 36
2023-08-22 | F | PCF- 6-7 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-08-01 | 36
2023-08-22 | F |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-08-01 | 2.5
2023-08-23 | K | PCK- 10A,B, 18, 7D | Pier 1600 mm |  | 4 | 1 | [5 empty] | 16 |  | 2023-08-01 | 16
2023-08-23 |  | Abutment | Abutment wall- PART-D | [6 empty] | 36 |  |  |  | 2023-08-01 | 36
2023-08-24 | F | PCF-5A | Pier Cap |  | 1 | 1 | [6 empty] | 15 | 2023-08-01 | 15
2023-08-24 | J | PCJ- 3B | Pier Cap |  | 1 | 1 | [6 empty] | 37 | 2023-08-01 | 37
2023-08-24 | K | PCK- 5C | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-08-01 | 5
2023-08-24 | F |  | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-24 | F |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-23 | F | PCF- 2-3 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-23 | F | PCF- 2-3 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-23 | F | PCF- 2-3 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-24 | F | PCF- 2-3 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-24 | F | PCF-1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-24 | F | PCF-1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-24 | F | PCF-1-2 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-25 | F | PCF-1-2 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-25 | J | PCF-1 - PCJ- 1 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-25 | J | PCF-1 - PCJ- 1 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-25 | J | PCF-1 - PCJ- 1 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-25 | J | PCF-1 - PCJ- 1 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-25 | F | PCF- 5C | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-08-01 | 5
2023-08-25 | K |  | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 30 |  | 2023-08-01 | 30
2023-08-25 | F |  | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-27 |  | Abutment (Raft) | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 245 |  | 2023-08-01 | 245
2023-08-27 | F | PCF- 5-6 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-27 | F | PCF- 6-7 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-27 | F |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-08-01 | 2.5
2023-08-27 | F | PCJ- 1-2 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-27 | F | PCJ- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-27 | F | PCJ- 1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-27 | F | PCJ- 1-2 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-28 | F | PCF- 4B | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-08-01 | 34
2023-08-28 | G | PCG- 12 | Pier Cap |  | 1 | 1 | [6 empty] | 40 | 2023-08-01 | 40
2023-08-28 | K | PCK- | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 14 |  | 2023-08-01 | 14
2023-08-28 | J | PCJ- 2A-3A | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-28 | J | PCJ- 2A-3A | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-28 | J | PCJ- 2A-3A | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-28 | J | PCJ- 2A-3A | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-28 | F | PCF- 9-10 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-28 | I | PCI- 10-11 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-28 | F | PCF-5-6 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-28 | F | PCF- 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-28 | F | PCF- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-28 | I | PCI- 10-17A | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-28 | F | PCF- 6-7, 5-6 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-28 | F |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-08-01 | 2.5
2023-08-28 | K | PCK- 4 | PCC |  | 2 | 2 |  |  |  | 7 |  |  |  | 2023-08-01 | 7
2023-08-29 | K | PCK- 6,7 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-08-01 | 15
2023-08-29 | K | PCK-3,4 | PCC |  | 3 | 3 |  |  |  | 15 |  |  |  | 2023-08-01 | 15
2023-08-29 | F | PCF- 9-10 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-08-01 | 24
2023-08-29 | I | PCI- 18-19 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-08-01 | 24
2023-08-29 | F | PCF- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-29 | I | PCI- 10-17A | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-29 | I | PCI- 6-7 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-08-01 | 0
2023-08-29 | I | PCI- 6-7 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-30 | K | PCK- 4A | RCC Foundation |  | 1 | 1 | [5 empty] | 32 |  | 2023-08-01 | 32
2023-08-30 | I | PCI- 6-7 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-30 | I | PCI- 6-7 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-30 | I | PCI- 7-8 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-08-01 | 0
2023-08-30 | I | PCI- 7-8 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-08-01 | 0
2023-08-30 | F | PCF- 5-6 | h - Section Beam |  | 1 | 1 | [5 empty] | 12 |  | 2023-08-01 | 12
2023-08-30 | F | PCF- 1-2 | Track Beam with Nose |  | 1 | 1 | [5 empty] | 12 |  | 2023-08-01 | 12
2023-08-30 | B | PC- 84-85 | Track Beam with Nose |  | 1 | 1 | [5 empty] | 12 |  | 2023-08-01 | 12
2023-08-30 | I | PCI- 10-17A, 20-21 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  | 24 |  | 2023-08-01 | 24
2023-08-30 | F |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-08-01 | 2.5
2023-08-31 | K | PCK- 4B | RCC Foundation |  | 1 | 1 | [5 empty] | 23 |  | 2023-08-01 | 23
2023-08-31 | F | PCF- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-08-01 | 34
2023-08-31 | F | PCF- 5 | Pier Cap |  | 1 | [7 empty] | 34 | 2023-08-01 | 34
2023-08-31 | K | PCK- | Pier 1600 mm |  | 5 | 5 | [5 empty] | 22 |  | 2023-08-01 | 22
2023-08-31 | I | PCI- 5-6 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-08-01 | 12
2023-08-31 | C | PCC- 4-5 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-31 | F | PCF- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-08-01 | 12
2023-08-31 | I | PCI- | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-08-01 | 24
2023-08-31 | I | PCI- 19-20, 18-19 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-08-01 | 24
2023-09-01 | K | PCK-4C, 3C | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-09-01 | 40
2023-09-01 | K | PCK-7, 9 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 25 |  | 2023-09-01 | 25
2023-09-01 | K | Pck-4D, E, F | PCC |  | 3 | 3 |  |  |  | 10 |  |  |  | 2023-09-01 | 10
2023-09-01 | F | PCF-5-6 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-01 | F | PCF-9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-01 | I | PCI-19-20 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-01 | F | PCF-9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-01 | I | PCI-17-18, 19-20 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-01 | F |  | Pre-cast Slab |  | 2 | 2 | [6 empty] | 1 | 2023-08-01 | 1
2023-09-02 | I | PCI-6-7 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-02 | B | PCB-81-83 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-02 | F | PCF-4-5 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-02 | I | PCI-19-20, 20-21 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-02 | F | PCF-9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-02 | F |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2023-09-01 | 1.5
2023-09-02 | G | PCG-16 | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-09-01 | 34
2023-09-02 | I | PCI-8-9 | Track Laying |  | 2 | 2 | [7 empty] | 2023-09-01 | 0
2023-09-02 | I | PCI-8-9 | Track Laying |  | 1 | 1 | [7 empty] | 2023-09-01 | 0
2023-09-03 | F | PCF-5D | Pier Cap |  | 1 | 1 | [6 empty] | 34 | 2023-09-01 | 34
2023-09-03 | J | PCJ-4B, 5C | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 14 |  | 2023-09-01 | 14
2023-09-04 | K | PCK - 4B, 3B,3C | RCC Foundation |  | 3 | 3 | [5 empty] | 69 |  | 2023-09-01 | 69
2023-09-04 | K | PCK - 6D, 7E | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-09-01 | 8
2023-09-04 | I | PCI -18-19 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  | 12 |  | 2023-09-01 | 12
2023-09-04 | K | PCK-19 | Track Beam with Nose |  | 1 | 1 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-05 | K | PCK-4A | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-05 | K | PCK-4D | RCC Foundation |  | 1 | 1 | [5 empty] | 22 |  | 2023-09-01 | 22
2023-09-05 | K | PCK-7 E | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-09-01 | 4
2023-09-05 | K | PCK-9 E | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-09-01 | 4
2023-09-05 | F | PCF-5A-6A | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-05 | K | PCK-16-17 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-05 | I | PCI-20-21 | Track Beam with Nose |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-09-01 | 24
2023-09-05 | I | PCI-17-18 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-05 | J | PCJ-1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-05 | J | PCJ-1-2 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-05 | J | PCJ-1-2 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-05 | J | PCJ-1-2 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-05 | J | PCJ-1-2 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-09-01 | 0
2023-09-06 | K | PCK-14-15 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-06 | I | PCI-20-21 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-06 | K | PCK-15-16 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-06 | I | PCI-8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-06 | C | PCC-5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-06 | J | PCJ-1-2 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-06 | J | PCJ-1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-06 | J | PCJ-1-2 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-09-01 | 0
2023-09-06 | K | PCK-4B-4C | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-06 | K | PCK-4E | RCC Foundation |  | 1 | 1 | [5 empty] | 39 |  | 2023-09-01 | 39
2023-09-07 | G | PCG-J1A-G1 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-07 | G | PCG-J1A-G1 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-07 | C | PCC-5-6 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-07 | I | PCI-19-20 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-07 | F |  | Pre-cast Slab |  | 4 | 4 | [6 empty] | 2 | 2023-09-01 | 2
2023-09-07 | K | PCK-E6,E7,E8,E9 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 16 |  | 2023-09-01 | 16
2023-09-07 | K | PCK - 3B,3C,3D | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-09-01 | 15
2023-09-07 | K | PCK-4C,4D | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-07 | H | PCH-18-20 | PCC |  | 2 | 2 |  |  |  | 14 |  |  |  | 2023-09-01 | 14
2023-09-07 |  | PCC-16-17 | Cast In-situ slab- PART-C |  | 1 | 1 |  |  |  | 18 |  |  |  | 2023-09-01 | 18
2023-09-08 | G | PCG-J11A-G1 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-08 | C | PCC-5-6 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-08 | I | PCI-8-9 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-08 | C | PCC-13-14 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-08 | I | PCI-8-9 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-08 | K | PCK-4A,4C,4D | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-09-01 | 18
2023-09-08 | K | PCK-4E | Step Footing |  | 1 | 1 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-08 | J | PCJ-4C-5P | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-09-01 | 8
2023-09-08 |  | PCA | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 27 |  | 2023-09-01 | 27
2023-09-08 | G | PCG-7 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-09-01 | 35
2023-09-08 | K | PCK-3D,3E | PCC |  | 4 | 4 |  |  |  | 19 |  |  |  | 2023-09-01 | 19
2023-09-09 | J | PCI -J2-J3 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-09 | J | PCI -J2-J3 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-09 | J | PCI -J2-J3 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-09 | J | PCI -J2-J3 | Erection-Track Beam without Nose |  | 2 | 2 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-09 | J | PCI -J2-J3 | Erection-Track Beam without Nose |  | 2 | 2 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-09 | G | PCG-J11A-G1 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-09 | G | PCG-J11A-G1 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-09 | C | PCC-7-8 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-09 | C | PCC-10-11 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-09 | I | PCI-8-9 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-09 | F |  | Pre-cast Slab |  | 1 | 1 | [6 empty] | 5 | 2023-09-01 | 5
2023-09-09 | K | PCK-4 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2023-09-01 | 24
2023-09-09 | K | PCK-4 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-09 | F | PCF-7 | Pier Cap |  | 1 | 1 | [6 empty] | 49 | 2023-09-01 | 49
2023-09-09 | G | PCG-25,26,27 | PCC |  | 3 | 3 |  |  |  | 14 |  |  |  | 2023-09-01 | 14
2023-09-11 | G | PCG-2-3 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-11 | I | PCI-19-20, 20-21 | U - Section Beam |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-11 | G | PCG-3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-11 | C | PCC-7-8 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-11 | C | PCC-12-13 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-11 | G | PCG-28 | PCC |  | 1 | 1 |  |  |  | 5 |  |  |  | 2023-09-01 | 5
2023-09-11 | K | PCK-4D-4E | RCC Foundation |  | 2 | 2 | [5 empty] | 53 |  | 2023-09-01 | 53
2023-09-11 | F | PCF-9 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-09-01 | 4
2023-09-11 | J | PCJ-5-6 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-09-01 | 8
2023-09-11 | G | PCG-9 | Pier Cap |  | 1 | 1 | [6 empty] | 33 | 2023-09-01 | 33
2023-09-12 | G | PCG-J11A-G1 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-12 | G | PCG-3-4 , 7-8 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-12 | C | PCC-7-8 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-12 | C | PCC- 6-7, 8-9 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-12 | G | PCG-J11A-G1 | Pre-cast Slab |  | 2 | 2 | [6 empty] | 1 | 2023-09-01 | 1
2023-09-12 | K | PCK-4B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-12 | K | PCK - 11-A,B,C | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-12 | K | PCK-9A | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-09-01 | 4
2023-09-12 | A | PCA-77-80 | PCC |  | 6 | 6 |  |  |  | 20 |  |  |  | 2023-09-01 | 20
2023-09-12 | G | PCG-29, 30 | PCC |  | 2 | 2 |  |  |  | 7 |  |  |  | 2023-09-01 | 7
2023-09-13 | G | PCG-8-9 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-13 | C | PCC-6-7, 7-8 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-13 | C | PCC-6-7, 8-9 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-13 | G | PCG-J11A-G1 | Pre-cast Slab |  | 2 | 2 | [6 empty] | 1 | 2023-09-01 | 1
2023-09-13 | K | PCK-3E | Step Footing |  | 1 | 1 | [5 empty] | 11 |  | 2023-09-01 | 11
2023-09-13 | J | PCJ-5A,4C,6B,6C | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-13 | K | PCK-2 | PCC |  | 4 | 4 |  |  |  | 21 |  |  |  | 2023-09-01 | 21
2023-09-14 | F | PCF-J1-F1 | Erection-U - Section Beam |  | 1 | 1 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-14 | F | PCF-J1-F1 | Erection-Track Beam with Nose |  | 1 | 1 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-14 | F | PCF-J1-F1 | Erection-Track Beam without Nose |  | 1 | 1 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-14 | F | PCF-J1-F1 | Erection-Track Beam without Nose |  | 1 | 1 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-14 | G | PCG-3-4 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-14 | I | PCI-19-20 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-14 | G | PCG-9-10 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-14 | C | PCC-6-7 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-14 | C | PCC-14-15 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-14 | C | PCC-20-21 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-14 | H | PCH-20 | PCC |  | 1 | 1 |  |  |  | 2 |  |  |  | 2023-09-01 | 2
2023-09-14 | G | PCG-8 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-09-01 | 35
2023-09-14 | K | PCK-9C,10A-B-C | Pier 1600 mm |  | 4 | 1 | [5 empty] | 39 |  | 2023-09-01 | 39
2023-09-15 | J | PCJ- 1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-15 | J | PCJ- 1-2 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-15 | J | PCJ- 1-2 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-15 | G | PCG- 10-11 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-15 | C | PCC- 6-7,7-8 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-15 | C | PCC-9-10 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-15 | C |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-09-01 | 2.5
2023-09-17 | A | PC- 80-82 | PCC |  | 2 | 2 |  |  |  | 6 |  |  |  | 2023-09-01 | 6
2023-09-17 | B | PC- 83-85 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-09-01 | 12
2023-09-17 | F | PCJ- 1-PCF-1 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-17 | F | PCJ- 1-PCF-1 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-09-01 | 0
2023-09-17 | G | PCG- 11-12 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-17 | C | PCC- 8-9 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-17 | C | PCC-5-6, 8-9 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-18 | F | PCF- 9 | Pier Cap |  | 1 | 1 | [6 empty] | 57 | 2023-09-01 | 57
2023-09-18 | G | PCG- 10 | Pier Cap |  | 1 | 1 | [6 empty] | 36 | 2023-09-01 | 36
2023-09-18 | K | PCK -3A | RCC Foundation |  | 1 | 1 | [5 empty] | 30 |  | 2023-09-01 | 30
2023-09-18 | J | PCJ- 6,7,8 | Pier 1600 mm |  | 5 | 5 | [5 empty] | 25 |  | 2023-09-01 | 25
2023-09-18 | K |  | Pier 1600 mm |  | 4 | 4 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-18 |  | Wing Wall | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 16 |  | 2023-09-01 | 16
2023-09-18 | F | PCF- 1-2 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-18 | F | PCF- 1-2 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-09-01 | 0
2023-09-18 | F | PCF- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-18 | G | PCG- 11-12 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-18 | C | PCC- 8-9 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-18 | C | PCC- 8-9 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-18 | C |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-09-01 | 2.5
2023-09-19 |  | Wing Wall | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 6 |  | 2023-09-01 | 6
2023-09-19 | K | PCK- 3A | Step Footing |  | 1 | 1 | [5 empty] | 8 |  | 2023-09-01 | 8
2023-09-19 | K |  | Pier 1600 mm |  | 5 | 5 | [5 empty] | 24 |  | 2023-09-01 | 24
2023-09-19 | F | PCF- 2-3 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-19 | F | PCF- 2-3 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-19 | F | PCF- 1-2 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-19 | F | PCF- 1-2 | Erection-Pre-cast Slab |  | 6 | 6 | 6 | [6 empty] | 2023-09-01 | 0
2023-09-19 | G | PCG- 11-12, 16-17 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-19 | C | PCC- 12-13 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-19 | C | PCC- 5-6 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-20 | K | PCK-2D | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-20 | A | PC -77,78 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-09-01 | 40
2023-09-20 | G | PCG-25A,26A | RCC Foundation |  | 2 | 2 | [5 empty] | 54 |  | 2023-09-01 | 54
2023-09-20 | G | PCG-16-17 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-20 | C | PCC-8-9,12-13 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-20 | C | PCC-9-10 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-20 | C |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2023-09-01 | 1.5
2023-09-20 | F | PCF-2-3 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-20 | F | PCF-2-3 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-09-01 | 0
2023-09-21 | A | PC- 79 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-21 | G | PCG- 28, 29 | RCC Foundation |  | 2 | 2 | [5 empty] | 55 |  | 2023-09-01 | 55
2023-09-21 | K | PCK- 2D | Step Footing |  | 1 | 1 | [5 empty] | 15 |  | 2023-09-01 | 15
2023-09-21 | F | PCF- 3-4 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-21 | F | PCF- 3-4 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-21 | F | PCF- 3-4 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-09-01 | 0
2023-09-21 | F | PCF- 4-5 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-21 | F | PCF- 4-5 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-21 | F | PCF- 5-6 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-21 | K | PCK- 14-15 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-21 | C | PCC- 12-13 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-21 | F | PCF- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-21 | C |  | Pre-cast Slab |  | 2 | 2 | [6 empty] | 1 | 2023-09-01 | 1
2023-09-22 | A | PC- 80 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-22 | A | PC- 77,78,79 | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-09-01 | 15
2023-09-22 | G | PCG- 11 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-09-01 | 35
2023-09-22 | K | PCK- | Pier 1600 mm |  | 4 | 1 | [5 empty] | 15 |  | 2023-09-01 | 15
2023-09-22 | J | PCJ- | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 18 |  | 2023-09-01 | 18
2023-09-22 | F | PCF- 3-4 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-22 | F | PCF- 3-4 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-09-01 | 0
2023-09-22 | F | PCF- 4-5 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-09-01 | 0
2023-09-22 | F | PCF- 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-22 | K | PCK- 13-14 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-22 | C | PCC-12-13 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-22 | J | PCJ- 3-4, 5-6 | Track Beam without Nose |  | 3 | 3 |  |  | 2 |  |  |  | 36 | 2023-09-01 | 36
2023-09-24 | A | PC- 81,82 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-09-01 | 40
2023-09-24 | B | PC- 83,84 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-09-01 | 40
2023-09-24 | A | PC- 80 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-09-01 | 5
2023-09-24 | G | PCG- 1-2 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-24 | K | PCK- 13-14 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-24 | C | PCC- 12-13 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-24 | G | PCJ- 11-PCE-1 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-24 | F | PCF- 3-4 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-24 | F | PCF- 4-5 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-24 | F | PCF- 4-5 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-24 | F | PCF- 4-5 | Erection-Pre-cast Slab |  | 6 | 6 | 6 | [6 empty] | 2023-09-01 | 0
2023-09-24 | F | PCF- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-24 | F | PCF- 1-2 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-25 | G | PCG- 1 | Pier 1600 mm |  | 2 | 1 | [5 empty] | 9 |  | 2023-09-01 | 9
2023-09-25 | K | PCK-6, 16 | Pier 1600 mm |  | 4 | 1 | [5 empty] | 18 |  | 2023-09-01 | 18
2023-09-25 | J | PCJ- 10,11 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-25 | F | PCF- 6 | Pier Cap |  | 1 | 1 | [6 empty] | 60 | 2023-09-01 | 60
2023-09-25 | I | PCI- 18-19 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-25 | K | PCK- 13-14 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-25 | C | PCC- 13-14 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-25 | K | PCK- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-25 | K |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2023-09-01 | 1.5
2023-09-25 | F | PCF- 3-4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-25 | F | PCF- 3-4 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-25 | F | PCF- 4-5 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-25 | F | PCF- 4-5 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-09-01 | 0
2023-09-26 | J | PCJ- | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-09-01 | 5
2023-09-26 | F | PCF- 3-4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-26 | F | PCF- 3-4 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-09-01 | 0
2023-09-26 | F | PCF- 4-5 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-26 | F | PCF- 4-5 | Erection-Pre-cast Slab |  | 3 | 3 | 3 | [6 empty] | 2023-09-01 | 0
2023-09-27 | G | PCG- 2-3 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-27 | K | PCK- 12-13 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-27 | C | PCC- 13-14 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-27 | G | PCE- 1-2, 2-3 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-27 | I | PCI- 5-6 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-28 | B | PC- 85,86 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-09-01 | 40
2023-09-28 | A | PC- 81,82 | Step Footing |  | 2 | 2 | [5 empty] | 5 |  | 2023-09-01 | 5
2023-09-28 | B | PC- 83, 84 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-28 | A | PC- 77,78 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-28 | G | PCG- 3 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-28 | I | PCI- 6-7 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-28 | I | PCI- 18-19 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-28 | K | PCK- 10-11 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-28 | C | PCC- 14-15 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-09-01 | 24
2023-09-28 | G | PCE- 2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-28 | K | PCK- 18-19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-28 | B |  | Pre-cast Slab |  | 1 | 1 | [6 empty] | 0.5 | 2023-09-01 | 0.5
2023-09-28 | I |  | Pre-cast Slab |  | 1 | 1 | [6 empty] | 0.5 | 2023-09-01 | 0.5
2023-09-29 | K | PCK- 2 | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-09-01 | 35
2023-09-29 | K |  | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-09-01 | 15
2023-09-29 | F | PCF- 10 | Pier Cap |  | 1 | 1 | [6 empty] | 55 | 2023-09-01 | 55
2023-09-29 | K | PCK- 11-12 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-29 | C | PCC- 20- I-21 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-29 | G | PCE-2-3 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-29 | C |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2023-09-01 | 1.5
2023-09-29 | I | PCI -5-6 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-29 | I | PCI- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-09-01 | 0
2023-09-30 | B | PC- 87 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-30 | K | PCK-1 | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-09-01 | 40
2023-09-30 | B | PC- 85,86 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-30 | A | PC- 79,80 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-30 | K | PCK- 3 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-09-01 | 12
2023-09-30 | J |  | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-09-01 | 10
2023-09-30 | K |  | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-09-01 | 20
2023-09-30 | G | PCG- 1 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-09-01 | 35
2023-09-30 | K | PCK- 11-12 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-30 | C | PCC- 20- I-21 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-30 | E | PCE- 2-3 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-09-01 | 12
2023-09-30 | B |  | Pre-cast Slab |  | 3 | 3 | [6 empty] | 1.5 | 2023-09-01 | 1.5
2023-09-30 | K | PCK- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-30 | J | PCJ- 2-3 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-09-01 | 12
2023-09-30 | C | PCC- 13-14, 14-15 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-09-30 | E | PCE- 2-3, 3-4 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-09-01 | 24
2023-10-03 |  | Raft | Abutment wall- PART-D |  | 1 | 1 | [5 empty] | 500 |  | 2023-10-01 | 500
2023-10-03 | G | PCG- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-03 | G | PCG- 6-7 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-03 | G | PCG- 6-7 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-03 | G | PCG- 7-8 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-03 | G | PCG- 7-8 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-03 | G | PCG- 7-8 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-03 | F | PCF- 9-10 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-03 | I | PCI- 7-8 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-03 | K | PCK- 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-03 | C | PCC- 20- I-21 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-03 | E | PCE- 3-4 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-03 | F |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-10-01 | 2.5
2023-10-04 | F | PCF- 8 | Pier Cap |  | 1 | 1 | [6 empty] | 60 | 2023-10-01 | 60
2023-10-04 | J | PCJ- 10,11 | Pier 1600 mm |  | 4 | 4 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-04 | K | pck- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-04 | C | PCC- 9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-04 | E | PCE-4-5, 5-6 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-04 | G | PCG- 6-7 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-10-01 | 0
2023-10-04 | G | PCG- 7-8 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-05 | G | PCG- 27A | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-10-01 | 35
2023-10-05 | H | PCH- 18A, 20A | RCC Foundation |  | 2 | 2 | [5 empty] | 45 |  | 2023-10-01 | 45
2023-10-05 | B | PC- 83 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-05 | K | PCK- 2 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-05 | G | PCG- 25 | Step Footing |  | 1 | 1 | [5 empty] | 7 |  | 2023-10-01 | 7
2023-10-05 | K |  | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 30 |  | 2023-10-01 | 30
2023-10-05 | G | PCG- 3 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-10-01 | 35
2023-10-05 | B | PC- 83 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-05 | K | PCK- 3 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-05 | K | PCK- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-05 | C | PCC- 9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-05 | K | PCK- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-05 | G | PCG- 6-7 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-05 | G | PCG- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-05 | G | PCG- 7-8 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-05 | G | PCG- 7-8 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-05 | G | PCG- 7-8 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-06 | G | PCG- 30A | RCC Foundation |  | 1 | 1 | [5 empty] | 44 |  | 2023-10-01 | 44
2023-10-06 | K | PCK- 2 | RCC Foundation |  | 1 | 1 | [5 empty] | 29 |  | 2023-10-01 | 29
2023-10-06 | G | PCG- | Step Footing |  | 1 | 1 | [5 empty] | 7 |  | 2023-10-01 | 7
2023-10-06 | B | PC- 82-83 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-06 | K | PCK- 7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-06 | C | PCC- 9-10 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-06 | K | PCK- 9-10 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-06 | G | PCG- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-06 | G | PCG- 8-9 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-06 | G | PCG- 8-9 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-06 | G | PCG- 9-10 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-06 | G | PCG- 9-10 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-06 | G | PCG- 9-10 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-08 | I | PCI- 17-18 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-08 | I | PCI- 8-9 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-08 | K | PCK- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-08 | I |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-10-01 | 2.5
2023-10-08 | G | PCG- 8-9 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-08 | G | PCG- 8-9 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-08 | G | PCG- 8-9 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-08 | G | PCG- 9-10 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-09 | K | PCK- 3 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-09 | K | PCK- 2 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-09 | G | PCG- 27,29, 30 | Step Footing |  | 3 | 3 | [5 empty] | 21 |  | 2023-10-01 | 21
2023-10-09 | H | PCH- 18A | Step Footing |  | 1 | 1 | [5 empty] | 7 |  | 2023-10-01 | 7
2023-10-09 | G | PCG- 9-10 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-09 | F | PCF- 5-6 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-09 | K | PCK- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-09 | C | PCC- 9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-09 | J | PCJ- 5-6 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-09 | F | PCF- 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-09 | E | PCE- 11-12, 6-7 | Track Beam without Nose |  | 3 | 3 |  |  | 2 |  |  |  | 36 | 2023-10-01 | 36
2023-10-09 | I |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-10-01 | 2.5
2023-10-09 | G | PCG- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-09 | G | PCG- 9-10 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-09 | G | PCG- 9-10 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-09 | G | PCG- 9-10 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-09 | G | PCG- 9-10 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-09 | G |  | Erection-Pre-cast Slab |  | 12 | 12 | 12 | [6 empty] | 2023-10-01 | 0
2023-10-10 | A | PC- 81,82 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-10 | B | PC- 86,87 | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-10-01 | 12
2023-10-10 | I | PCI- 18-19 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-10 | B | PC- 90-91 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-10 | K | PCK- 7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-10 | J | PCJ- 5-6 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-10 | E | PCE- 6-7 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-11 | G | PCG- 13A, B | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 7 |  | 2023-10-01 | 7
2023-10-11 | J | PCJ- 12 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-10-01 | 35
2023-10-11 | I | PCI- 10-11 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-11 | K | PCK-7-8 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-11 | J | PCJ- 5-6 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-11 | F | PCF- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-11 | E | PCE- 6-7 | Track Beam without Nose |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-10-01 | 24
2023-10-12 | G | PCG- 28 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-12 | G | PCG- 25, 26 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-12 | B | PC- 84 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-12 | K | PCK- | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-12 |  | Wall 1 st lift | Abutment wall- PART-D | [8 empty] | 59 |  | 2023-10-01 | 59
2023-10-12 | K | PCK- 18 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-10-01 | 65
2023-10-12 | C | PCC- 14-15 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-12 | E | PCE- 10-11 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-12 | G | PCG- 3-4 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-12 | K | PCK- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-12 | E | PCE- 6-7 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-13 | B | PC- 86,87,88, 89 | PCC |  | 8 | 8 |  |  |  | 24 |  |  |  | 2023-10-01 | 24
2023-10-13 | J | PCJ- 11B | Pier Cap |  | 1 | 1 | [6 empty] | 36 | 2023-10-01 | 36
2023-10-13 | G | PCG- 27A, 28A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-13 | I | PCI- 19-20 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-13 | F | PCF- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-13 | E | PCE- 6-7 | Track Beam without Nose |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-10-01 | 24
2023-10-13 | I |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-10-01 | 2.5
2023-10-13 | G | PCG- 10-11 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-13 | G | PCG- 10-11 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-13 | G | PCG- 10-11 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-13 | G | PCG- 11-12 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-13 | G | PCG- 11-12 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-15 | B | PC- 86, 87 | RCC Foundation |  | 3 | 3 | [5 empty] | 60 |  | 2023-10-01 | 60
2023-10-15 | G | PCG- 28B, 29, 30 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-10-01 | 18
2023-10-15 | A | PC- 77, 78 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-15 | K |  | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-15 | K | PCK- 1 | PCC |  | 4 | 4 |  |  |  | 20 |  |  |  | 2023-10-01 | 20
2023-10-15 | H | PCH- 9-10 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-15 | H | PCH- 9-10 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-15 | K | PCK- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-15 | J | PCJ- 5-6 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-15 | F | PCF- 6-7 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-15 | E | PCE- 9-10, 12-13 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-15 | K | PCK- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-15 | G | PCG- 10-11 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-15 | G | PCG- 10-11 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-15 | G | PCG- 10-11 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-15 | G | PCG- 11-12 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-15 | G | PCG- 11-12 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-16 | B | PC- 86A, 87B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-16 | A | PC- 78, 80 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-16 | G | PC- 27A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-10-01 | 6
2023-10-16 | K | PCK- | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-16 | E | PCE- 3 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-10-01 | 35
2023-10-16 | G | PCG- 10-11 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-16 | G | PCG- 11-12 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-16 | G |  | Erection-Pre-cast Slab |  | 9 | 9 | 9 | [6 empty] | 2023-10-01 | 0
2023-10-16 | B | PC- 84-85 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-16 | G | PCG- 8-9 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-16 | J | PCJ- 4-5 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-16 | E | PCE- 16-17 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  |  | 2023-10-01 | 0
2023-10-17 | A | Abutment wall 2nd Lift | Abutment wall- PART-A | [8 empty] | 53 |  | 2023-10-01 | 53
2023-10-17 | B | PC- 88A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-17 | H | PCH- 18 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-10-01 | 6
2023-10-17 | C | PCC- 5-6 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-17 | B | PC- 84-85 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-17 | J | PCJ- 4-5 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-17 | B | PC- 84-85 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-17 | E | PCE- 16-17 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-17 | K | PCK- 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-17 | F | PCF- 5-6 | Erection-Track Beam without Nose |  | 6 | 6 | 6 | [6 empty] | 2023-10-01 | 0
2023-10-17 | F | PCF- 5-6 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-17 | F | PCF- 5-6 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-18 | B | PC- 86B, 87A | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-10-01 | 40
2023-10-18 | K | PCK- | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 11 |  | 2023-10-01 | 11
2023-10-18 | I | PCI- 20-21 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-18 | G | PCG- 9-10 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-18 | K | PCK-9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-18 | E | PCE- 5-6 | Track Beam without Nose |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-10-01 | 24
2023-10-18 | F | PCF- 5-6 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-18 | F | PCF- 6-7 | Erection-Track Beam without Nose |  | 9 | 9 | 9 | [6 empty] | 2023-10-01 | 0
2023-10-18 | F | PCF- 6-7 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-19 | K | PCK- 1 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-19 | B | PC- 86B, 87A, 88A | Step Footing |  | 3 | 3 | [5 empty] | 15 |  | 2023-10-01 | 15
2023-10-19 | B | PC- 86A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-10-01 | 6
2023-10-19 | A | PC- 81,82 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-19 | J | PCJ- 11 | Pier 1600 mm |  | 2 | 0.25 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-19 | K | PCK- 17 | Pier Cap |  | 1 | 1 | [6 empty] | 68 | 2023-10-01 | 68
2023-10-19 | C | PCC- 7-8 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-19 | C | PCC- 5-6 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-19 | J | PCJ- 5-6 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-19 | F | PCF- 5-6 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-19 | F | PCF- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-19 | F | PCF- 6-7 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-20 | K | PCK-1 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-20 | B | PC-88B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-20 | B | PC-83A. 83B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-20 | G | PCG -14A,14B | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 8 |  | 2023-10-01 | 8
2023-10-20 | K | PCK-19 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-10-01 | 4
2023-10-20 | F | PCF- 9-10 | Track Beam without Nose |  | 3 | 3 |  |  | 1 |  |  |  | 36 | 2023-10-01 | 36
2023-10-20 | C | PCC- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-20 | J | PCJ- 5-6 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-20 | C | PCC- 6-7 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-20 | I | PCI- 17-18 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-20 | I |  | Pre-cast Slab |  | 1 | 1 | [6 empty] | 0.5 | 2023-10-01 | 0.5
2023-10-20 | C |  | Pre-cast Slab |  | 4 | 4 | [6 empty] | 2 | 2023-10-01 | 2
2023-10-22 | B | PC 88-B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-22 | K | PC K1 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-22 | B | PC 87A | Pier 1900 mm |  | 1 | 1 |  |  | 1 |  |  | 6 |  | 2023-10-01 | 6
2023-10-22 | C | PCC 8-9 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-22 | C | PCC 6-7, 20-21 | U - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-10-01 | 24
2023-10-22 | B | PCB 84-85 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-22 | C | PCC 10-11 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-22 | C | PCC 10-11 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-22 | J | PCJ 5-6 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-22 | E | PCE 14-15 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-24 | B | PC-89B | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-24 | A | PC 77 | Pier Cap |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-24 | J | PCJ-4 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-10-01 | 65
2023-10-24 | K | PCK-78 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-10-01 | 4
2023-10-24 | C | PCC 6-7 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-24 | K | PCK 14-13 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-24 | C | PCC 10-11 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-24 | F | PCF 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-24 | C | PCC 10-11 | Track Beam without Nose |  | 1 | 1 |  |  | 2 |  |  |  | 12 | 2023-10-01 | 12
2023-10-24 | J | PCJ 5-6 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-24 | F | PCF 5-6 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-24 | F | PCF 5-6 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-24 | F | PCF 5-6 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-24 | F | PCF 6-7 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-24 | F | PCF 6-7 | Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-24 | F | PCF 6-7 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-25 | K | PCK- 2A | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-25 | K | PCK- 1 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-25 | B | PC- 88B | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-25 | K | PCK- 19 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 3 |  | 2023-10-01 | 3
2023-10-25 | I | PCI- 17-18 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-25 | C | PCC- 9-10 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-25 | K | PCK- 6-7 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-25 | C | PCC- 9-10 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-25 | F | PCF- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-25 | C | PCC- 10-11 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-25 | K | PCK- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-25 | F | PCF- 6-7 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-25 | F | PCF- 7-8 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-25 | F | PCF- 7-8 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-25 | F | PCF- 7-8 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-26 | K | PCK-1 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-26 | J | PCJ-11 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-10-01 | 35
2023-10-26 | A | PCA-77 | Pier Cap |  | 1 | 1 | [6 empty] | 13 | 2023-10-01 | 13
2023-10-26 | B |  | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-10-01 | 6
2023-10-26 | G | PCG 10-11 | h - Section Beam |  | 1 | 1 | 1 | [5 empty] | 12 | 2023-10-01 | 12
2023-10-26 | K | PCK 6-5 | Track Beam with Nose |  | 1 | 1 | 1 | [5 empty] | 12 | 2023-10-01 | 12
2023-10-26 | K | PCK 10-9 | Track Beam without Nose |  | 1 | 1 | 1 | [5 empty] | 12 | 2023-10-01 | 12
2023-10-26 | C | PCC 10-11 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-26 | F | PCF 7-8 | Erection-Track Beam without Nose |  | 8 | 8 | 8 | [6 empty] | 2023-10-01 | 0
2023-10-26 | F | PCF 7-8 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-26 | F | PCF 7-8 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-27 | F | PCF 7-8 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-27 | F | PCF 8-9 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-27 | F | PCF 8-9 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-27 | F | PCF 9-10 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-27 | K | PCK-1 | RCC Foundation |  | 1 | 1 | [5 empty] | 39 |  | 2023-10-01 | 39
2023-10-27 | K | PCK-1 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-27 | B | PCB | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-10-01 | 6
2023-10-27 | C | PCC 7-8 | U - Section Beam |  | 2 | 2 | 2 | [5 empty] | 24 | 2023-10-01 | 24
2023-10-27 | C | PCC 10-11 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-29 | B | PC- 89A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-10-01 | 20
2023-10-29 | K | PCK- 1 | RCC Foundation |  | 1 | 1 | [5 empty] | 37 |  | 2023-10-01 | 37
2023-10-29 | K | PCK- 1 | Step Footing |  | 1 | 1 | [5 empty] | 11 |  | 2023-10-01 | 11
2023-10-29 | K | PCK- 2 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-10-01 | 6
2023-10-29 | B | PC- | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-29 | A | PC- 79 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-10-01 | 14
2023-10-29 | C | PCC- 7-8 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-29 | I | PCI- 9-10 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-29 | K | PCK- 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-29 | C | PCC- 10-11 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-10-01 | 24
2023-10-29 | F | PCF- 9-10 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-29 | E | PCE- 14-15 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 12 | 2023-10-01 | 12
2023-10-29 | F | PCF- 8-9 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-10-01 | 0
2023-10-29 | F | PCF- 8-9 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-29 | F | PCF- 8-9 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-29 | F | PCF- 9-10 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-29 | F | PCF- 9-10 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-30 | A | PC- 80, 82 | Pier Cap |  | 2 | 2 | [6 empty] | 30 | 2023-10-01 | 30
2023-10-30 | B | PC- 89A | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-10-01 | 10
2023-10-30 | K | PCK- 2 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-10-01 | 5
2023-10-30 | G | PCG- 9-10 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-30 | C | PCC- 9-10 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-30 | I | PCI- 10-17A | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-30 | K | PCK- 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-30 | F | PCF- 9-10 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-30 | J | PCJ- 9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-30 | K | PCF- 10- PCK- 19 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-10-01 | 12
2023-10-30 | E | PCE- 14-15 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-10-01 | 12
2023-10-30 | F | PCF- 8-9 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-30 | F | PCF- 8-9 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-30 | F | PCF- 8-9 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-30 | F | PCF- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-30 | H | PCH- 17-19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-10-31 | B |  | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-10-01 | 12
2023-10-31 | G | PCG-14 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 4 |  | 2023-10-01 | 4
2023-10-31 | A | PC-81 | Pier Cap |  | 1 | 1 | [6 empty] | 14 | 2023-10-01 | 14
2023-10-31 | E | PCE-11 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-10-01 | 35
2023-10-31 | K | PCK-19 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-10-01 | 65
2023-10-31 | H | PCH 17-19 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-10-01 | 0
2023-10-31 | H | PCH 17-19 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-31 | H | PCH 17-19 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-31 | C | PCC H19-C1 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-10-01 | 0
2023-10-31 | C | PCC H19-C1 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-10-01 | 0
2023-11-01 | C | PCC-9-10 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-01 | I | PCI 10A-17A | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-01 | K | PCK | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-01 | C | PCC 11-12 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-01 | E | PCE 14-15 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-01 | K | PC -K1 | RCC Foundation |  | 1 | 1 | [5 empty] | 35 |  | 2023-11-01 | 35
2023-11-01 | K | PC-K2 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-11-01 | 12
2023-11-01 | H | PCH 17-19 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-11-01 | 0
2023-11-01 | C | PCC 1-2 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-01 | C | PCC 1-2 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-02 | C | PCC 15-20 | Cast In-situ slab- PART-C | [8 empty] | 249 |  | 2023-11-01 | 249
2023-11-02 | K | PCK-2 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-02 | B | PCB-85 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-02 | H | PC H19-C1 | Erection-Track Beam without Nose |  | 3 | 3 | 3 | [6 empty] | 2023-11-01 | 0
2023-11-02 | H | PC H19-C1 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-02 | C | PCC 1-2 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-02 | C | PCC 1-2 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-03 | K | PCK-1 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-11-01 | 20
2023-11-03 | K | PCK-2 | Step Footing |  | 1 | 1 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-03 | K | PCK-1 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-11-01 | 12
2023-11-03 | C | PCC 15-20 | Cast In-situ slab- PART-C |  | 1 | 1 | [5 empty] | 360 |  | 2023-11-01 | 360
2023-11-03 | C | PCC 9-10 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-03 | H | PCH 1-2 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-03 | C | PCC 13-14 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-03 | K | PCK 6-5 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-03 | J | PCJ 7-10 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-03 | J | PCJ 11B-12 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-03 | E | PCE 11-12 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-03 | J | PCJ 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-03 | I |  | Pre-cast Slab |  | 1 | 1 | [6 empty] | 0.5 | 2023-11-01 | 0.5
2023-11-03 | C | PCH- 19- PCC-1 | Erection-Track Beam without Nose |  | 7 | 7 | 7 | [6 empty] | 2023-11-01 | 0
2023-11-05 | C | PCC 15-20 | Cast In-situ slab- PART-C |  | 1 | 1 | [5 empty] | 235 |  | 2023-11-01 | 235
2023-11-05 | C | PCC 14-15 | U - Section Beam |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-11-01 | 24
2023-11-05 | J | PCJ9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-05 | J | PCJ 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-05 | J | PCJ 8-9 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-05 | C | PCC 2-3 | Erection-Track Beam with Nose |  | 4 | 4 | 4 | [6 empty] | 2023-11-01 | 0
2023-11-05 | C | PCC 2-3 | Erection-Track Beam without Nose |  | 4 | 4 | 4 | [6 empty] | 2023-11-01 | 0
2023-11-06 | K | PCK-1 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-06 | K | PCK-1 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-11-01 | 5
2023-11-06 | C | PCC 12-13 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-06 | J | PCJ 7-8 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-06 | J | PCJ 8-9 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-06 | J | PCJ 3-4 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-06 | J | PCJ 7-8 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-06 | F | PCF 9-10 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-06 | F | PCF 9-10 | Erection-Track Beam without Nose |  | 7 | 7 | 7 | [6 empty] | 2023-11-01 | 0
2023-11-07 | K | PCK-1 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-11-01 | 18
2023-11-07 | K | PCK-1 | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-07 | B | PCB-89 | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-11-01 | 20
2023-11-07 | B | PCB- 84,85,86 | Pier 1600 mm |  | 3 | 3 | [5 empty] | 15 |  | 2023-11-01 | 15
2023-11-07 | G | PCG 15 | Pier 1600 mm |  | 2 | 2 | [5 empty] | 8 |  | 2023-11-01 | 8
2023-11-07 |  | ABUTMENT | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 46 |  | 2023-11-01 | 46
2023-11-07 | C | PCC 12-13, 13-14 | U - Section Beam |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-07 | K | PCK 5-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-07 | J | PCJ 9-10, 10-11B | Track Beam without Nose |  | 3 | 3 |  |  | 3 |  |  |  | 36 | 2023-11-01 | 36
2023-11-08 | K | PCK-15 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-11-01 | 65
2023-11-08 | K | PCK-3 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 14 |  | 2023-11-01 | 14
2023-11-08 | B | PCB 84A-84B | Pier 1600 mm |  | 2 | 2 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-08 |  | TRESTLE FOUNDATION |  |  | 1 | [6 empty] | 15 |  | 2023-11-01 | 15
2023-11-08 | C | PCC 20-21 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-08 | C | PCC 12-13 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-08 | K | PCK 5-4 | Track Beam with Nose |  | 3 | 3 |  |  | 2 |  |  |  | 36 | 2023-11-01 | 36
2023-11-08 | J | PCJ 4-5, PCJ 7-8 | Track Beam without Nose |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-11-01 | 24
2023-11-09 | K | PCK 4A,4B | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-09 | K | PCK 3B | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-11-01 | 5
2023-11-09 | K | PCK 10B, 10E | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-09 | K | PCK 1E | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-09 |  | TRESTLE FOUNDATION | [9 empty] | 21 |  | 2023-11-01 | 21
2023-11-09 | B | PCB 84A,84B | Pier 1600 mm |  | 2 | 0.75 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-09 | B | PCB 89A | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-09 | B | PCB -89A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-11-01 | 5
2023-11-09 | C | PCC 14-15 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-09 | K | PCK 5-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-09 | J | PCJ 10-11 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-09 | J | PCJ 6-7, 7-8, 10-11B | Track Beam without Nose |  | 3 | 3 |  |  | 3 |  |  |  | 36 | 2023-11-01 | 36
2023-11-10 | K | PCK | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 30 |  | 2023-11-01 | 30
2023-11-10 |  | TRESTLE FOUNDATION |  |  | 2 | 2 | [5 empty] | 27 |  | 2023-11-01 | 27
2023-11-10 | C | PCC 20-21 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-10 | C | PCC 20-21 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-10 | K | PCK 5-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-10 | J | PCJ 10-11B, 11-12 | Track Beam with Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-10 | J | PCJ 6-7 | Track Beam without Nose |  | 2 | 2 |  |  | 1 |  |  |  | 24 | 2023-11-01 | 24
2023-11-10 | C | PCC 3-4 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-10 | C | PCC 3-4 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-10 | C | PCC 4-5 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-10 | C | PCC 4-5 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-11 | K | PCK-5-6 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-11 | J | PCJ 4-5, PCJ 7-8 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-11 | E | PCE 16-17 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-11 | K | PCK 3D,8D,9E | Pier 1600 mm |  | 3 | 0.25 | [5 empty] | 15 |  | 2023-11-01 | 15
2023-11-11 | J | PCJ -5 | Pier Cap |  | 1 | 1 | [6 empty] | 66 | 2023-11-01 | 66
2023-11-11 | C | PCC- 3-4 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-11 | C | PCC- 3-4 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-11 | C | PCC- 4-5 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-11 | C | PCC- 4-5 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-15 | C | PCJ 13-14 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-15 | G | PCG 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-15 | K | PCK 5-6 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-15 | J | PCJ 4-5 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-15 | E | PCE 8-9, 15-16 | Track Beam without Nose |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-15 | C | PCC 3-4, 4-5 | Erection-h - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-15 | C |  | Erection-Pre-cast Slab |  | 15 | 15 | 15 | [6 empty] | 2023-11-01 | 0
2023-11-15 |  | TRESTLE FOUNDATION | [11 empty] | 2023-11-01 | 0
2023-11-15 | B | PCB 88B | Pier 1600 mm |  | 1 | 1 | [5 empty] | 5 |  | 2023-11-01 | 5
2023-11-15 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-15 | K | PCK-K9B,K9E,K4C,K3D | Pier 1600 mm |  | 4 | 1 | [5 empty] | 20 |  | 2023-11-01 | 20
2023-11-15 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-15 | C | PCC- 3-4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01
2023-11-15 | C | PCC- 3-4 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01
2023-11-16 | K | PCK-5-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-16 | J | PCJ -9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-16 | E | PCE-10 -11 | Track Beam without Nose |  | 3 | 3 |  |  | 3 |  |  |  | 36 | 2023-11-01 | 36
2023-11-16 | K | PCK-7B | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-16 | K | PCK-4C | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-16 | K | PCK-7C | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-16 | B | PCB-87A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-16 | G | PCG-23A-6 | RCC Foundation |  | 1 | 1 | [5 empty] | 45 |  | 2023-11-01 | 45
2023-11-16 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-17 | H | PCH -8-9 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-17 | H |  | Erection-Pre-cast Slab |  | 15 | 15 | 15 | [6 empty] | 2023-11-01 | 0
2023-11-17 | C | PCC-5-6,6-7 | h - Section Beam |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-17 | J | PCJ- 9-10 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-17 | E | PCE-16-17 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-17 | K | PCK7-8 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-17 | K | PCK-1B,2F,7B,7E | Pier 1600 mm |  | 4 | 1 | [5 empty] | 16 |  | 2023-11-01 | 16
2023-11-17 | B | PCB-87A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-17 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-17 | G | PCG-23B | RCC Foundation |  | 1 | 1 | [5 empty] | 45 |  | 2023-11-01 | 45
2023-11-18 | H | PCH-7-8 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-18 | H | PCH-7-8 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-18 | H | PCH-8-9 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-18 | H | PCH-8-9 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-18 | H |  | Erection-Pre-cast Slab |  | 9 | 9 | 9 | [6 empty] | 2023-11-01 | 0
2023-11-18 | H | PCH-19-20 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-18 | K | PCK-6-7 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-18 | E | PCE13-14 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-18 | K | PCK-4-5,6-7.7-8 | Track Beam without Nose |  | 3 | 3 |  |  | 3 |  |  |  | 36 | 2023-11-01 | 36
2023-11-18 | K | PCK -1C,1D,2F,7A,7D | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 20 |  | 2023-11-01 | 20
2023-11-18 | B | PCB 89A | Pier 1600 mm |  | 1 | 1 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-18 |  | TRESTLE COLUMN |  |  | 2 | 2 | [5 empty] | 2 |  | 2023-11-01 | 2
2023-11-18 | G | PCG23A-24B0 | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-11-01 | 10
2023-11-18 | G | PCG 22A | RCC Foundation |  | 1 | 1 | [5 empty] | 45 |  | 2023-11-01 | 45
2023-11-20 | F | PCF8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-20 | F | PCF9-10 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-20 | F | PCF9-10 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-20 | B | PCB-83 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-11-01 | 65
2023-11-20 | B | PCB-88-89 | Pier 1600 mm |  | 1 | 1 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-20 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 4 |  | 2023-11-01 | 4
2023-11-20 | K | PCK-16 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-11-01 | 65
2023-11-20 | K | PCK-2H,1C,1E,7A,9A | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 20 |  | 2023-11-01 | 20
2023-11-20 | C | PCC-8-9 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-20 | K | PCK3-4,4-5,5-6 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-11-01 | 36
2023-11-21 | K | PCK-F10-19 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-11-01 | 0
2023-11-21 | K | PCK-F18-19 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-21 | C | PCC-8-9 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-21 | C | PCC-10-11 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-21 | K | PCK-4-5 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-21 | K | PCK-4-5 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-21 | G | PCG-24A,25B | RCC Foundation |  | 2 | 2 | [5 empty] | 20 |  | 2023-11-01 | 20
2023-11-21 | K | PCK-1G,2A,2E,2G,2H,1F | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 24 |  | 2023-11-01 | 24
2023-11-22 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 2 |  | 2023-11-01 | 2
2023-11-22 | G | PCG- 22A, 23A,B, 24B | Pier 1900 mm |  | 4 | 4 | [5 empty] | 24 |  | 2023-11-01 | 24
2023-11-22 | K | PCK- 2A, 2B, 2D, 2E, 2G, 1G, 1H, 9A | Pier 1600 mm |  | 8 | 2 | [5 empty] | 30 |  | 2023-11-01 | 30
2023-11-22 | G | PCG- | PCC |  | 1 | 1 |  |  |  | 6 |  |  |  | 2023-11-01 | 6
2023-11-22 | C | PCC- 8-9 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-22 | H | PCH- 1-2 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-22 | K | PCK- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-22 | K | PCF- 10- PCK- 19 | Erection-Track Beam without Nose |  | 5 | 5 | 5 | [6 empty] | 2023-11-01 | 0
2023-11-22 | K | PCK- 18-19 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-23 | K | PCK- 9F, 2B,C,D, 1B,F,H | Pier 1600 mm |  | 7 | 1.75 | [7 empty] | 2023-11-01 | 0
2023-11-23 | G | PCG- 22B | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-23 |  | TRESTLE COLUMN |  |  | 4 | 4 | [5 empty] | 5 |  | 2023-11-01 | 5
2023-11-23 | C | PCC- 8-9 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-23 | K | PCK- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-23 | K | PCK- 2-3 | Track Beam without Nose |  | 3 | 3 |  |  | 3 |  |  |  | 36 | 2023-11-01 | 36
2023-11-23 | K | PCF-10 - PCK-19 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-23 | K | PCF-10 - PCK-19 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-23 | G |  | PCC |  | 1 | 1 |  |  |  | 6 |  |  |  | 2023-11-01 | 6
2023-11-24 | G | PCG- 25 | RCC Foundation |  | 1 | 1 | [5 empty] | 57 |  | 2023-11-01 | 57
2023-11-24 | K | PCK- 1A,B,F, 2C, 3G,F, 9C | Pier 1600 mm |  | 7 | 1.75 | [5 empty] | 35 |  | 2023-11-01 | 35
2023-11-24 | G | PCG- 24,25, 26 | PCC |  | 5 | 5 |  |  |  | 27 |  |  |  | 2023-11-01 | 27
2023-11-24 |  | TRESTLE COLUMN |  |  | 2 | 2 | [5 empty] | 3 |  | 2023-11-01 | 3
2023-11-24 | C | PCC- 8-9 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-24 | K | PCK- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-24 | E | PCE- 13-14 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-24 | J | PCJ- 7-8 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-24 | K | PCK- 10-11 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-24 | K | PCF- 10- PCK- 19 | Erection-Track Beam without Nose |  | 6 | 6 | 6 | [6 empty] | 2023-11-01 | 0
2023-11-24 | K | PCF- 10- PCK- 19 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-24 | F | PCF- 9-10 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-26 | G | PCG- 25 | Step Footing |  | 1 | 1 | [5 empty] | 15 |  | 2023-11-01 | 15
2023-11-26 | K | PCK- 1A,3F,G,H, 4F,E, 9C,F | Pier 1600 mm |  | 8 | 2 | [5 empty] | 40 |  | 2023-11-01 | 40
2023-11-26 | B | PC- 85 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-11-01 | 35
2023-11-26 |  | TRESTLE COLUMN |  |  | 6 | 6 | [5 empty] | 2 |  | 2023-11-01 | 2
2023-11-26 | K | PCF- 10- PCK- 19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-26 | K |  | Erection-Pre-cast Slab |  | 6 | 6 | 6 | [6 empty] | 2023-11-01 | 0
2023-11-26 | I | PCI- 18-19 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-26 | C | PCC- 12-13 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-26 | C | PCC_ 8-9 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-26 | K | PCK- 3-4 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-26 | K | PCK- 1-2 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-27 | K | PCK- 3H, 4E,F, 6C | Pier 1600 mm |  | 4 | 1 | [5 empty] | 15 |  | 2023-11-01 | 15
2023-11-27 | G | PCG- 26 | RCC Foundation |  | 1 | 1 | [5 empty] | 58 |  | 2023-11-01 | 58
2023-11-27 | C | PCC- 14-15 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-27 | C | PCC- 10-11 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-27 | K | PCK- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-27 | H |  | Erection-Pre-cast Slab |  | 9 | 9 | 9 | [6 empty] | 2023-11-01 | 0
2023-11-28 |  | Abutment Raft And Wall | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 93 |  | 2023-11-01 | 93
2023-11-28 | G | PCG- 26 | RCC Foundation |  | 1 | 1 | [5 empty] | 15 |  | 2023-11-01 | 15
2023-11-28 | B | PC-85 | Pier Cap |  | 1 | 1 | [6 empty] | 33 | 2023-11-01 | 33
2023-11-28 | I | PCI- 8-9 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-28 | C | PCC- 10-11 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-28 | K | PCK- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-29 |  | Abutment Raft And Wall | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 63 |  | 2023-11-01 | 63
2023-11-29 | G | PCG-24 | RCC Foundation |  | 1 | 1 | [5 empty] | 40 |  | 2023-11-01 | 40
2023-11-29 | K | PCK- 4G, 5A,B,C, 8B | Pier 1600 mm |  | 1 | 1.25 | [5 empty] | 25 |  | 2023-11-01 | 25
2023-11-29 | G | PCG-25 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-11-01 | 6
2023-11-29 | I | PCI-7-8 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-29 | C | PCC- 6-7, 14-15 | h - Section Beam |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-11-01 | 24
2023-11-29 | C | PCC- 10-11 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-29 | K | PCK- 1-2 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-11-01 | 12
2023-11-30 |  | Abutment wall 3rd Lift | Abutment wall- PART-A |  | 1 | 1 | [5 empty] | 22 |  | 2023-11-01 | 22
2023-11-30 | K | PCK- 6A,B,D, 4G,H, 8A | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 30 |  | 2023-11-01 | 30
2023-11-30 | G | PCG- 24 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-11-01 | 5
2023-11-30 | I | PCI- 9-10 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-11-01 | 0
2023-11-30 | I | PCI- 9-10 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-11-01 | 0
2023-11-30 | I | PCI- 9-10 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-30 | C | PCC- 10-11 | U - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-11-01 | 12
2023-11-30 | K | PCK- 3-4 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-11-01 | 24
2023-11-30 | J | PCJ- 8 | Pier Cap |  | 1 | 1 | [6 empty] | 70 | 2023-11-01 | 70
2023-11-30 | B | PC- 88 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-11-01 | 35
2023-11-30 | B | PC-87 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-11-01 | 35
2023-12-01 | G | PCG- 26 | Pier 1900 mm |  | 1 | 1 | [5 empty] | 6 |  | 2023-12-01 | 6
2023-12-01 | K | PCK- 4A, 6A,B, 7F, 8B,C | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 28 |  | 2023-12-01 | 28
2023-12-01 | C | PCC- 10-11, PCC-20-PCI-21 | h - Section Beam |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-12-01 | 24
2023-12-01 | K | PCK- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-03 | G | PCG- 30B | RCC Foundation |  | 1 | 1 | [5 empty] | 26 |  | 2023-12-01 | 26
2023-12-03 | I | PCI- 9-10 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-03 | I | PCI- 9-10 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-03 | C | PCC- 10-11, 11-12 | h - Section Beam |  | 2 | 2 |  |  | 2 |  |  |  | 24 | 2023-12-01 | 24
2023-12-04 | K | PCK- 2-3 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-04 | K | PCK- 15-16, 16-17 | Track Beam without Nose |  | 3 | 3 | [6 empty] | 36 | 2023-12-01 | 36
2023-12-04 | H | PCH- 18,20 | PCC |  | 2 | 2 |  |  |  | 7 |  |  |  | 2023-12-01 | 7
2023-12-04 | G | PCG- 30 | PCC |  | 1 | 1 |  |  |  | 10 |  |  |  | 2023-12-01 | 10
2023-12-04 | I | PCI- 8-9 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-04 | I | PCI- 9-10 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-04 | C | PCC- 10-11 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-04 | H | PCH- 3-4 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-04 | K | PCK- 14-15 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-05 | K | PCK- 8A,C, 7F | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 15 |  | 2023-12-01 | 15
2023-12-05 | G | PCG- 22B | RCC Foundation |  | 1 | 1 | [5 empty] | 25 |  | 2023-12-01 | 25
2023-12-05 | I | PCI-7-8 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-05 | I | PCI- 17-18 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-05 | E | PCE- 16-18 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-05 | K | PCK- 2-3 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-05 | E | PCE- 13-14 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-05 | K | PCE- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-05 | K | PCE- 15-16 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-06 | G | PCG- 23B, 30B | Step Footing |  | 2 | 2 | [5 empty] | 15 |  | 2023-12-01 | 15
2023-12-06 | K | PCK- 1 | Pier 1600 mm |  | 5 | 1.25 | [5 empty] | 20 |  | 2023-12-01 | 20
2023-12-06 | A | Abutment main wall 3rd lift | Abutment wall- PART-A | [8 empty] | 39 |  | 2023-12-01 | 39
2023-12-06 | B | PC- 87 | Pier Cap |  | 1 | 1 | [6 empty] | 29 | 2023-12-01 | 29
2023-12-06 | I | PCI- 10-17A | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-06 | I | PCI- 10-17A | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-06 | E | E-17-18 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-06 | E | PCE- 15-16 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-06 | K | PCk- 13-14 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-07 | G | PCG- 25, 26 | RCC Foundation |  | 2 | 2 | [5 empty] | 140 |  | 2023-12-01 | 140
2023-12-07 | K | PCK- 1 | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-12-01 | 5
2023-12-07 | G | PCG- 28 | PCC |  | 1 | 1 |  |  |  | 5 |  |  |  | 2023-12-01 | 5
2023-12-07 | H | PCH- 2-3 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-07 | E | PCE- 17-18 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-07 | K | PCK- 1-2 | Track Beam with Nose |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-07 | E | PCE- 8-9 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-07 | I | PCI- 10-17 | Erection-Track Beam with Nose |  | 3 | 3 | 3 | [6 empty] | 2023-12-01 | 0
2023-12-07 | I | PCI- 10-17 | Erection-Track Beam without Nose |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-07 | I | PCI- 10-17 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-08 | K | PCK- 1H | Pier 1600 mm |  | 1 | 0.25 | [5 empty] | 5 |  | 2023-12-01 | 5
2023-12-08 | G | PCG-22 | Step Footing |  | 1 | 1 | [5 empty] | 6 |  | 2023-12-01 | 6
2023-12-08 | H | PCH- 18 | RCC Foundation |  | 1 | 1 | [5 empty] | 25 |  | 2023-12-01 | 25
2023-12-08 | A | Abutment Wall final lift | Abutment wall- PART-A | [8 empty] | 10 |  | 2023-12-01 | 10
2023-12-08 | B | PC- 86 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-12-01 | 35
2023-12-08 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-08 | E | PCE- 10-11 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-08 | E | PCE- 11-12 | Track Beam without Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-08 | I | PCI- 10-17 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-08 | I | PCI- 17-18 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-08 | I | PCI- 17-18 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-08 | I | PCI- 17-18 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-08 | I | PCI- 18-19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-10 | H | PCH-20 | RCC Foundation |  | 1 | 1 | [5 empty] | 25 |  | 2023-12-01 | 25
2023-12-10 | H | PCH-18 | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-12-01 | 5
2023-12-10 | G | PCG- 22, 24,25,26 | Pier 1900 mm |  | 4 | 4 | [5 empty] | 20 |  | 2023-12-01 | 20
2023-12-10 | K | PCK- 1 | Pier 1600 mm |  | 7 | 7 | [5 empty] | 29 |  | 2023-12-01 | 29
2023-12-10 | H | PCH- 5-6 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-10 | B | PC- 90-91 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-10 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-10 | E | PCE- 11-12 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-10 | I | PCI- 17-18 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-10 | I | PCI- 17-18 | Erection-U - Section Beam |  | 1 | 1 | 1
2023-12-10 | I | PCI- 18-19 | Erection-Track Beam with Nose |  | 2 | 2 | 2
2023-12-10 | I | PCI- 18-19 | Erection-Track Beam without Nose |  | 1 | 1 | 1
2023-12-11 | G | PCG- 27, 28 | RCC Foundation |  | 2 | 2 | [5 empty] | 75 |  | 2023-12-01 | 75
2023-12-11 | H | PCH- 20 | Step Footing |  | 1 | 1 | [5 empty] | 7 |  | 2023-12-01 | 7
2023-12-11 | K | PCK- 8D, 5B, 1G | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 13 |  | 2023-12-01 | 13
2023-12-11 | H | PCH-4-5 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-11 | B | PC- 88-90 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-11 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-11 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-11 | I | PCI- 17-18 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-11 | I | PCI- 17-18 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-11 | I | PCI- 17-18 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-11 | I | PCI- 18-19 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-12 | J | PCJ- 6 | Pier Cap |  | 1 | 1 | [6 empty] | 65 | 2023-12-01 | 65
2023-12-12 | I | PCI-17-18 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-12 | I | PCI- 18-19 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-12 | I | PCI- 18-19 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-12 | I | PCI- 18-19 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-12 | I | PCI- 19-20 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-12 | I | PCI- 19-20 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-12 | E | PCE- 17-18 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-12 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-12 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-12 | K | PCK- 12-13 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-13 | E | PCE- 10A, B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-12-01 | 40
2023-12-13 | G | PCG- 27, 28 | Step Footing |  | 2 | 2 | [5 empty] | 12 |  | 2023-12-01 | 12
2023-12-13 | H | PCH- 18, 20 | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-12-01 | 12
2023-12-13 | G | PCG-23 | Pier 1600 mm |  | 1 | 0.5 | [5 empty] | 5 |  | 2023-12-01 | 5
2023-12-13 | A | Wing Wall | Abutment wall- PART-A | [8 empty] | 12 |  | 2023-12-01 | 12
2023-12-13 | E |  | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-12-01 | 12
2023-12-13 | I | PCI- 19-20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-13 | I | PCI- 19-20 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-13 | I | PCI- 19-20 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-13 | I | PCI- 20-21 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-13 | I | PCI- 20-21 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-13 | H | PCH- 4-5 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-13 | K | PCK- 17-18, 18-19 | h - Section Beam |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-13 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-14 | K | PCK-1,5 | Pier 1600 mm |  | 3 | 0.75 | [5 empty] | 12 |  | 2023-12-01 | 12
2023-12-14 | E | PCE- 9A, B | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-12-01 | 40
2023-12-14 | E | PCE- 10A, B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-12-01 | 10
2023-12-14 | E | PCE- 18 | Pier Cap |  | 1 | 1 | [6 empty] | 32 | 2023-12-01 | 32
2023-12-14 | I | PCI- 19-20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-14 | I | PCI- 19-20 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-14 | I | PCI- 19-20 | Erection-U - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-14 | I | PCI- 20-21 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-14 | I | PCI- 20-21 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-14 | K | PCK- 11-12 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-14 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-14 | K | PCK- 12-13 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-15 | G | PCG- 27,29, 30 | Pier 1900 mm |  | 3 | 3 | [5 empty] | 18 |  | 2023-12-01 | 18
2023-12-15 | E | PCE- 9A, B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-12-01 | 10
2023-12-15 | E | PCE- 8A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-12-01 | 20
2023-12-15 | A | Wing Wall and Main Wall | Abutment wall- PART-A | [8 empty] | 21 |  | 2023-12-01 | 21
2023-12-15 | E |  | PCC |  | 6 | 6 |  |  |  | 20 |  |  |  | 2023-12-01 | 20
2023-12-15 | G |  | PCC |  | 4 | 4 |  |  |  | 15 |  |  |  | 2023-12-01 | 15
2023-12-15 | H | PCH- 11-13 | h - Section Beam |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-15 | K | PCK- 16-17 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-15 | K | PCK- 1-2 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-15 | E | PCE- 12-13 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-15 | I | PCI- 19-20 | Erection-Track Beam with Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-15 | I | PCI- 19-20 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-15 | I | PCI- 20-21 | Erection-h - Section Beam |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-15 | I | PCI- 20-21 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-15 | I | PCI- 20-21 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-17 | K | PCK- 9-10 | U - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-17 | J | PCJ- 3-4 | Track Beam with Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-17 | K | PCK- 13-14 | Track Beam without Nose |  | 2 | 2 | [6 empty] | 24 | 2023-12-01 | 24
2023-12-17 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-17 | A |  | Pre-cast Slab |  | 5 | 5 | [6 empty] | 2.5 | 2023-12-01 | 2.5
2023-12-17 | E |  | PCC |  | 4 | 4 |  |  |  | 12 |  |  |  | 2023-12-01 | 12
2023-12-17 | E | PCE-9A,B | Step Footing |  | 2 | 2 | [5 empty] | 10 |  | 2023-12-01 | 10
2023-12-17 | E | PCE- 8A | RCC Foundation |  | 1 | 1 | [5 empty] | 20 |  | 2023-12-01 | 20
2023-12-17 | K |  | Pier 1600 mm |  | 6 | 1.5 | [5 empty] | 30 |  | 2023-12-01 | 30
2023-12-17 | C | PCI- 21- PCC-20 | Erection-Track Beam with Nose |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-17 | C | PCI- 21- PCC-20 | Erection-Track Beam without Nose |  | 1 | 1 | 1 | [6 empty] | 2023-12-01 | 0
2023-12-10 | I |  | Track Laying |  |  |  |  | 470 | [5 empty] | 2023-12-01 | 0
2023-12-18 | E | PCE- 8B, 7A | RCC Foundation |  | 2 | 2 | [5 empty] | 40 |  | 2023-12-01 | 40
2023-12-18 | E | PCE- 8A | Step Footing |  | 1 | 1 | [5 empty] | 5 |  | 2023-12-01 | 5
2023-12-18 | E | PCE- 10A, B | Pier 1900 mm |  | 2 | 2 | [5 empty] | 12 |  | 2023-12-01 | 12
2023-12-18 | K |  | Pier 1600 mm |  | 2 | 0.5 | [5 empty] | 10 |  | 2023-12-01 | 10
2023-12-18 | B | PC- 90A, B | PCC |  | 2 | 2 |  |  |  | 10 |  |  |  | 2023-12-01 | 10
2023-12-18 | D | PCD- 8-11 Screed) | PCC | [6 empty] | 18 |  |  |  | 2023-12-01 | 18
2023-12-18 | C | PCI- 21- PCC-20 | Erection-U - Section Beam |  | 2 | 2 | 2 | [6 empty] | 2023-12-01 | 0
2023-12-18 | C | Abutment- PC-43 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-18 | G | PCG- 5-6 | h - Section Beam |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-18 | J | PCJ- 3-4 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-18 | E | PCE- 12-13 | Track Beam with Nose |  | 1 | 1 |  |  | 1 |  |  |  | 12 | 2023-12-01 | 12
2023-12-18 | K | PCK- 13-14 | Track Beam without Nose |  | 1 | 1 | [6 empty] | 12 | 2023-12-01 | 12
2023-12-18 | E | PCE- 15 | Pier Cap |  | 1 | 1 | [6 empty] | 35 | 2023-12-01 | 35
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
[14 empty] | 2023-12-01 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Drop-down (hidden)
PCC | 2022-01-01 | A | Cloudy
RCC Foundation | 2022-02-01 | B | Sunny
Pier 1900 mm | 2022-03-01 | C | Rainy
Pier 1600 mm | 2022-04-01 | D | Windy
Pier Cap | 2022-05-01 | E
Step Footing | 2022-06-01 | F
Track Beam with Nose | 2022-07-01 | G
Track Beam without Nose | 2022-08-01 | H
h - Section Beam | 2022-09-01 | I
U - Section Beam | 2022-10-01 | J
Pre-cast Slab | 2022-11-01 | K
Erection-Track Beam with Nose | 2022-12-01
Erection-Track Beam without Nose | 2023-01-01
Erection-h - Section Beam | 2023-02-01
Erection-U - Section Beam | 2023-03-01
Erection-Pre-cast Slab | 2023-04-01
Excavation | 2023-05-01
Filling | 2023-06-01
OHE & Cabling | 2023-07-01
S&T | 2023-08-01
Parapet Wall | 2023-09-01
Track Laying | 2023-10-01
Abutment wall- PART-A | 2023-11-01
Abutment wall- PART-D | 2023-12-01
Cast In-situ slab- 1- PART-G | 2024-01-01
Cast In-situ slab- 2- PART-G | 2024-02-01
Cast In-situ slab- PART-C | 2024-03-01
2024-04-01
2024-05-01

## Summary (hidden)
Excluding PCC
DPR - ELEVATED HOT METAL TRACK - TARGET VS. ACTUAL
Description | Total RCC Qty in Cum | Executed qty in Cum | Balance to execute | Target qty in Dec-23 | Achieved qty in Dec-23 | Average Manpower trend FTM | Cumulative work progress % | Work progress % FTM
Total RCC qty (Cast in-situ + Precast) | 61107 | 52164.55 | 8942.45 | 4037 | 2659 | #REF! | 85.37% | 65.87% |  | 2023-12-01 |  | 2023-12-18
Target Vs. Actual
Description | Scope | UoM | Daily |  | Monthly |  | Cumulative Till Date |  | Balance | Achieved in % | Remarks
|  |  | Target | Achieved | Target | Achieved | Target | Achieved
Excavation for foundation | 495 | Nos. | 0 | 2 | 0 | 24 | 470 | 522 | -27 | 105.5% | Footings under hindrance: 4 nos. total E: 3 Cable Gallery G: 1 Cable gallery
Pier Cap | 259 | Nos. | 0 | 1 | 0 | 5 | 124 | 208 | 51 | 80.31%
RCC Cast-in-situ & Pre-cast | 61107 | Cum | 108.7333 | 162 | 4037 | 2659 | 74263.16 | 50118.55 | 10988.45 | 82.02%
Erection-For all Beams | 2946 | Nos. | 0 | 2 | 245 | 59 | 5584.5 | 1509 | -2638.5 | 189.6%
Cast-in-situ Status:
Part | No of Piers | Drawing qty in Cum | Qty in Cum /Nos | Executed qty in Cum | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
A | 40 | 2414 | 60.35 | 1959.2 | 0 | 256 | 24 | 0 | 68 | 29.7 | 80 | 216 | 101 | 0 | 100 | 24 | 195 | 317 | 136.5 | 118 | 0 | 0 | 169 | 125 | 0 | 0 | 0 | 0 | 0 | 0
B | 28 | 1408 | 50.2857 | 1400.25 | 0 | 0 | 0 | 306.75 | 20 | 35 | 44 | 14 | 0 | 0 | 0 | 67 | 0 | 0 | 71.5 | 45 | 0 | 0 | 120 | 317 | 296 | 64 | 0 | 0 | 0 | 0
H | 52 | 2156 | 41.4615 | 2531 | 0 | 0 | 0 | 0 | 0 | 0 | 547 | 510 | 318 | 216 | 113 | 34 | 199 | 343 | 35 | 84 | 0 | 0 | 0 | 58 | 0 | 74 | 0 | 0 | 0 | 0
G | 62 | 4885 | 78.7903 | 3298 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135 | 206 | 379 | 678 | 223 | 125 | 72 | 62 | 0 | 74 | 371 | 226 | 399 | 348 | 0 | 0 | 0 | 0
C | 40 | 3437 | 85.925 | 1872 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 448 | 108 | 75 | 37 | 164 | 107 | 255 | 292 | 52 | 206 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
I | 55 | 2141 | 38.9273 | 3006 | 0 | 0 | 0 | 0 | 522 | 532 | 376 | 178 | 314 | 188 | 301 | 300 | 295 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D | 54 | 2668 | 49.4074 | 2613.6 | 0 | 0 | 327 | 594.6 | 151 | 40 | 119 | 138 | 443 | 437 | 269 | 32 | 28 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 30 | 2442 | 81.4 | 1916.5 | 0 | 597 | 310 | 0 | 0 | 76 | 56 | 0 | 0 | 0 | 0 | 0 | 40 | 39 | 34 | 36 | 104.5 | 305 | 259 | 60 | 0 | 0 | 0 | 0 | 0 | 0
J | 43 | 2580 | 60 | 2444.5 | 0 | 0 | 0 | 0 | 75 | 315 | 0 | 0 | 749 | 160 | 0 | 0 | 250 | 156 | 0 | 0 | 70.5 | 147 | 120 | 201 | 136 | 65 | 0 | 0 | 0 | 0
K | 110 | 6453 | 58.6636 | 5184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 283 | 120 | 60 | 18 | 343 | 73 | 176 | 18 | 977 | 489 | 542 | 739 | 538 | 641 | 167 | 0 | 0 | 0 | 0
E | 36 | 3367 | 93.5278 | 1080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 279 | 90 | 58 | 47 | 0 | 16 | 0 | 0 | 0 | 70 | 0 | 274 | 0 | 0 | 0 | 0
Abutment wall- PART-A |  |  |  | 673 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 49 | 53 | 224 | 82 | 0 | 0 | 0 | 0
Abutment wall- PART-D |  |  |  | 595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- 1- PART-G |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- 2- PART-G |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- PART-C |  |  |  | 862 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 844 | 0 | 0 | 0 | 0 | 0
Sub-total: | 550 | 33951 |  | 29435.05 | 0 | 853 | 661 | 901.35 | 836 | 1027.7 | 1322 | 1787 | 2288 | 1588 | 1496 | 1732 | 1468 | 1493 | 659 | 1390 | 870 | 1397 | 1845 | 2207 | 2540 | 1074 | 0 | 0 | 0 | 0
Pre-cast Status
Track Beam with Nose | 773 | 8766 | 11.3402 | 7692 | 0 | 0 | 0 | 0 | 0 | 36 | 120 | 180 | 468 | 457 | 528 | 599 | 672 | 588 | 372 | 492 | 408 | 588 | 912 | 516 | 492 | 264 | 0 | 0 | 0 | 0
Track Beam without Nose | 807 | 9591 | 11.8848 | 9069 | 0 | 0 | 0 | 0 | 60 | 228 | 228 | 480 | 612 | 627 | 672 | 528 | 768 | 492 | 294 | 588 | 972 | 744 | 432 | 624 | 516 | 204 | 0 | 0 | 0 | 0
h - Section Beam | 357 | 4330 | 12.1289 | 2875.5 | 0 | 0 | 0 | 0 | 0 | 36 | 48 | 36 | 144 | 159.5 | 204 | 215 | 144 | 192 | 209 | 240 | 276 | 192 | 72 | 168 | 252 | 288 | 0 | 0 | 0 | 0
U - Section Beam | 406 | 4131 | 10.1749 | 2896.5 | 0 | 0 | 0 | 0 | 24 | 48 | 156 | 216 | 252 | 185.5 | 180 | 239 | 156 | 204 | 60 | 120 | 120 | 192 | 168 | 312 | 228 | 36 | 0 | 0 | 0 | 0
Pre-cast Slab | 603 | 338 | 0.56053 | 196.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17.5 | 32 | 29 | 12.5 | 14 | 9.5 | 13 | 22 | 23.5 | 12.5 | 0.5 | 2.5 | 0 | 0 | 0 | 0
Total: | 2946 | 27156 | 46.0893 | 22729.5 | 0 | 0 | 0 | 0 | 84 | 348 | 552 | 912 | 1476 | 1437 | 1601.5 | 1613 | 1769 | 1488.5 | 949 | 1449.5 | 1789 | 1738 | 1607.5 | 1632.5 | 1488.5 | 794.5 | 0 | 0 | 0 | 0
Total RCC achieved quantity: |  |  |  | 52164.55 | 0 | 853 | 661 | 901.35 | 920 | 1375.7 | 1874 | 2699 | 3764 | 3025 | 3097.5 | 3345 | 3237 | 2981.5 | 1608 | 2839.5 | 2659 | 3135 | 3452.5 | 3839.5 | 4028.5 | 1868.5 | 0 | 0 | 0 | 0
Target RCC Quantity: | [5 empty] | 1200 | 1300 | 1444 | 2502.16 | 3030 | 4024 | 3628 | 4272 | 4972 | 5498 | 5463 | 4649 | 5656 | 4133 | 4552 | 4424 | 3276 | 4054 | 4998 | 4785 | 4037 | 0 | 0 | 0 | 0
Achived in %: | [5 empty] | 71.08% | 50.85% | 62.42% | 36.77% | 45.4% | 46.57% | 74.39% | 88.11% | 60.84% | 56.34% | 61.23% | 69.63% | 52.71% | 38.91% | 62.38% | 60.1% | 95.7% | 85.16% | 76.82% | 84.19% | 46.28% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Phase-wise Details
Phase | Particulars | No of Footings in No's | Front available in No's | RCC Qty in Cum | 2022-03-01: Executed Qty in Cum; 2022-04-01: Balance to execute in Cum; 2022-05-01: Up to pier columns; 2022-06-01: Pier cap
Phase I | A, B, H, C, I & D | 267 | 261 | 13625.5269 | 2022-03-01: 13382.05; 2022-04-01: 243.4769
Phase II | G, J, F, K & E | 279 | 209 | 7929.3387 | 2022-03-01: 13923; 2022-04-01: -5993.6613
|  | 546 | 470 | 21554.8656 | 2022-03-01: 27305.05; 2022-04-01: -5750.1844
In Progress
In Progress

## Rohan- Backup sheet (hidden)
Part Name | Footing | [5 empty] | Pier 1900 |  |  |  |  | Pier 1600 |  |  |  |  | Pier cap |  |  |  |  | h- Beam |  |  | U- Beam |  |  | Solid Without Nose |  |  | Solid With Nose |  |  | Slab
Priority 1 | Total Scope | Hold Qty's | Available front | Comm. achieved | Balance |  | Total Scope | Hold Qty's | Available front | Comm. achieved | Balance | Total Scope | Hold Qty's | Available front | Comm. achieved | Balance | Total Scope | Hold Qty's | Available front | Comm. achieved | Balance | Scope | Comm. achieved | Balance | Scope | Comm. achieved | Balance | Scope | Comm. achieved | Balance | Scope | Comm. achieved | Balance | Scope | Comm. achieved | Balance
A | 40 | 0 | 40 | 40 | 0 |  | 40 | 0 | 40 | 40 | 0 | 40 | 0 | 40 | 40 | 0 | 40 | 0 | 40 | 40 | 0 | 40 | 40 | 0 | 40 | 40 | 0 | 0 | 0 | 0 | 80 | 76 | 4 | 120 | 119 | 1
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 40 |  | 40 | 34 | 6 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
B | 28 | 0 | 28 | 27 | 1 |  | 28 | 0 | 28 | 26 | 2 | 28 | 0 | 28 | 24.75 | 3.25 | 17 | 0 | 17 | 16 | 1 | 28 | 28 | 0 | 14 | 14 | 0 | 48 | 48 | 0 | 46 | 46 | 0 | 54 | 54 | 0
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 6 | 0 | 6 | 6 | 0 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 11 |  | 11 | 3 | 8 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
H | 41 | 0 | 41 | 41 | 0 |  | 52 | 0 | 52 | 52 | 0 | 52 | 0 | 52 | 50 | 2 | 18 | 0 | 18 | 18 | 0 | 32 | 28 | 4 | 19 | 19 | 0 | 106 | 106 | 0 | 42 | 42 | 0 | 33 | 33 | 0
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 3 |  | 3 | 3 | 0 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 15 | 0 | 15 | 15 | 0 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 |  | 0 | [10 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
C | 38 | 6 | 32 | 32 | 0 |  | 40 | 6 | 34 | 34 | 0 | 40 | 6 | 34 | 34 | 0 | 19 | 3 | 16 | 16 | 0 | 32 | 31 | 1 | 32 | 32 | 0 | 30 | 30 | 0 | 63 | 63 | 0 | 27 | 27 | 0
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 6 |  | 6 | 6 | 0 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 12 | 3 | 9 | 9 | 0 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 1 |  | 1 | 1 | 0 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | [10 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
I | 49 | 0 | 49 | 49 | 0 |  | 55 | 0 | 55 | 55 | 0 | 55 | 0 | 55 | 55 | 0 | 35 | 0 | 35 | 35 | 0 | 39 | 38 | 1 | 39 | 39 | 0 | 115 | 115 | 0 | 80 | 80 | 0 | 45 | 28 | 17
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 24 |  | 24 | 24 | 0 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 5 |  | 5 | 5 | 0 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 3 |  | 3 | 3 | 0 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 3 |  | 3 | 3 | 0 | [10 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
D | 54 | 0 | 54 | 54 | 0 |  | 54 | 0 | 54 | 54 | 0 | 54 | 0 | 54 | 54 | 0 | 36 | 0 | 36 | 36 | 0 | 34 | 34 | 0 | 45 | 45 | 0 | 83 | 83 | 0 | 84 | 84 | 0 | 96 | 96 | 0
Single | [16 empty] | 18 | 0 | 18 | 18 | 0
Double | [16 empty] | 18 | 0 | 18 | 18 | 0
Triple | [16 empty] | 0 | 0 | 0 | 0 | 0
Quadruple | [16 empty] | 0 | 0 | 0 | 0 | 0
Quintuble | [16 empty] | 0 | 0 | 0 | 0 | 0
Sextuple | [16 empty] | 0 | 0 | 0 | 0 | 0
Octuple | [16 empty] | 0 | 0 | 0 | 0 | 0
Subtotal | 250 | 6 | 244 | 243 | 1 |  | 269 | 6 | 263 | 261 | 2 | 269 | 6 | 263 | 257.75 | 5.25 | 165 | 3 | 162 | 161 | 1 | 205 | 199 | 6 | 189 | 189 | 0 | 382 | 382 | 0 | 395 | 391 | 4 | 375 | 357 | 18 | 10 | 1171 | 1161
Priority 2
E | 36 | 3 | 33 | 27 | 6 |  | 36 | 3 | 33 | 21 | 12 | 36 | 3 | 33 | 19 | 14 | 18 | 2 | 16 | 4 | 12 | 38 | 4 | 34 | 38 | 1 | 37 | 38 | 38 | 0 | 76 | 17 | 59 | 0 | 0 | 0
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 18 | 2 | 16 | 0 | 16 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
G | 57 | 1 | 56 | 53 | 3 |  | 62 | 1 | 61 | 56 | 5 | 62 | 1 | 61 | 41.5 | 19.5 | 16 | 2 | 14 | 10 | 4 | 28 | 12 | 16 | 12 | 12 | 0 | 55 | 52 | 3 | 41 | 35 | 6 | 39 | 18 | 21
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 1 |  | 1 | 0 | 1 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 15 | 2 | 13 | 0 | 13 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
J | 37 | 0 | 37 | 37 | 0 |  | 43 | 0 | 43 | 43 | 0 | 43 | 0 | 43 | 43.25 | -0.25 | 16 | 0 | 16 | 13 | 3 | 24 | 5 | 19 | 42 | 12 | 30 | 60 | 55 | 5 | 78 | 43 | 35 | 30 | 0 | 30
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 3 | 0 | 3 | 1 | 2 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 6 | 0 | 6 | 1 | 5 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 7 | 0 | 7 | 0 | 7 | [10 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
F | 30 | 0 | 30 | 30 | 0 |  | 30 | 0 | 30 | 30 | 0 | 30 | 0 | 30 | 30 | 0 | 15 | 0 | 15 | 15 | 0 | 18 | 18 | 0 | 15 | 15 | 0 | 73 | 73 | 0 | 37 | 37 | 0 | 39 | 35 | 4
Single |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 5 | 0 | 5 | 3 | 2 | [10 empty] | 0 |  |  | 0
Double |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 5 | 0 | 5 | 0 | 5 | [10 empty] | 0 |  |  | 0
Triple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  | 5 | 0 | 5 | 0 | 5 | [10 empty] | 0 |  |  | 0
Quadruple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Quintuble |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Sextuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
Octuple |  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 |  |  |  | 0 | [12 empty] | 0 |  |  | 0
|  |  |  | 0 | [5 empty] | 0 |  | 0 | 0 |  | 0 | [16 empty] | 0 |  |  | 0
K | 85 | 0 | 85 | 85 | 0 |  | 110 | 0 | 110 | 110 | 0 | 110 | 0 | 110 | 103.5 | 6.5 | 21 | 0 | 21 | 5 | 16 | 37 | 3 | 34 | 106 | 15 | 91 | 199 | 162 | 37 | 134 | 116 | 18 | 102 | 13 | 89
Single | [16 empty] | 0 | 0 | 0 | 0 | 0
Double | [16 empty] | 0 | 0 | 0 | 0 | 0
Triple | [16 empty] | 0 | 0 | 0 | 0 | 0
Quadruple | [16 empty] | 11 |  | 11 | 0 | 11
Quintuble | [16 empty] | 2 |  | 2 | 0 | 2
Sextuple | [16 empty] | 8 |  | 8 | 0 | 8
Octuple | [18 empty] | 0 | 0 | 0
Subtotal | 245 | 4 | 241 | 232 | 9 | 0 | 281 | 4 | 277 | 260 | 17 | 281 | 4 | 277 | 237.25 | 39.75 | 86 | 4 | 82 | 47 | 35 | 145 | 42 | 103 | 213 | 55 | 158 | 425 | 380 | 45 | 366 | 248 | 118 | 210 | 66 | 144 | 424 | 1149 | 725
Total | 495 | 10 | 485 | 475 | 10 |  | 550 | 10 | 540 | 521 | 19 | 550 | 10 | 540 | 495 | 45 | 251 | 7 | 244 | 208 | 36 | 350 | 241 | 109 | 402 | 244 | 158 | 807 | 762 | 45 | 761 | 639 | 122 | 585 | 423 | 162 | 434 | 2320 | 1886
2905
Priority 1 | [21 empty] | Remark
Single | [16 empty] | 97 | 0 | 97 | 91 | 6
Double | [16 empty] | 46 | 3 | 43 | 35 | 8
Triple | [16 empty] | 19 | 0 | 19 | 19 | 0
Quadruple | [16 empty] | 3 | 0 | 3 | 3 | 0
Quintuble | [16 empty] | 0 | 0 | 0 | 0 | 0
Sextuple | [16 empty] | 0 | 0 | 0 | 0 | 0
Octuple | [16 empty] | 0 | 0 | 0 | 0 | 0
Total | [16 empty] | 165 | 3 | 162 | 148 | 14
Priority 2
Single | [16 empty] | 9 | 0 | 9 | 4 | 5
Double | [16 empty] | 44 | 4 | 40 | 1 | 39
Triple | [16 empty] | 5 | 0 | 5 | 0 | 5
Quadruple | [16 empty] | 18 | 0 | 18 | 0 | 18
Quintuble | [16 empty] | 2 | 0 | 2 | 0 | 2
Sextuple | [16 empty] | 8 | 0 | 8 | 0 | 8
Octuple | [16 empty] | 0 | 0 | 0 | 0 | 0
Total | [16 empty] | 86 | 4 | 82 | 5 | 77
Single | [16 empty] | 106 | 0 | 106 | 95 | 11
Double | [16 empty] | 90 | 7 | 83 | 36 | 47
Triple | [16 empty] | 24 | 0 | 24 | 19 | 5
Quadruple | [16 empty] | 21 | 0 | 21 | 3 | 18
Quintuble | [16 empty] | 2 | 0 | 2 | 0 | 2
Sextuple | [16 empty] | 8 | 0 | 8 | 0 | 8
Octuple | [16 empty] | 0 | 0 | 0 | 0 | 0
Total | [16 empty] | 251 | 7 | 244 | 153 | 91

## Daily Concrete Register (hidden)
For the Month of December 2023
Sr. No. | Dates | QTY Planned (Nos.) | QTY Achieved (Nos.) | Difference (Nos.) | Remarks
Pre-cast Yard
1 | 2023-12-01 | 3 | 3 | 0
2 | 2023-12-02 | 7 | 7 | 0
3 | 2023-12-03 |  |  | 0
4 | 2023-12-04 | 4 | 4 | 0
5 | 2023-12-05 | 6 | 6 | 0
6 | 2023-12-06 | 3 | 3 | 0
7 | 2023-12-07 | 5 | 5 | 0
8 | 2023-12-08 | 3 | 3 | 0
9 | 2023-12-09 | 4 | 4 | 0
10 | 2023-12-10 |  |  | 0
11 | 2023-12-11 | 5 | 5 | 0
12 | 2023-12-12 | 4 | 4 | 0
13 | 2023-12-13 | 4 | 4 | 0
14 | 2023-12-14 | 4 | 4 | 0
15 | 2023-12-15 | 4 | 4 | 0
16 | 2023-12-16 | 4 | 4 | 0
17 | 2023-12-17 | 5 | 5 | 0
18 | 2023-12-18 | 5 | 5 | 0
19 | 2023-12-19 |  |  | 0
20 | 2023-12-20 |  |  | 0
21 | 2023-12-21 |  |  | 0
22 | 2023-12-22 |  |  | 0
23 | 2023-12-23 |  |  | 0
24 | 2023-12-24 |  |  | 0
25 | 2023-12-25 |  |  | 0
26 | 2023-12-26 |  |  | 0
27 | 2023-12-27 |  |  | 0
28 | 2023-12-28 |  |  | 0
29 | 2023-12-29 |  |  | 0
30 | 2023-12-30 |  |  | 0
|  | Total (Nos.) |  | 0
|  | Sub- total (Cum) |  | 0
Cast In-Situ
1 | 2023-12-12 | 172 | 65 | 107 | Due to poor quality of concrete
2 | 2023-12-13 | 150 | 93 | 57 | Due to poor quality of concrete
3 | 2023-12-14 | 158 | 84 | 74 | Due to poor quality of concrete and break down of batching plant
4 |  |  |  | 0
5 |  |  |  | 0
6 |  |  |  | 0
7 |  |  |  | 0
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
10 |  |  |  | 0
|  | Sub- total (Cum) |  | 238
|  | Total (Cum) |  | 238
Formulas:
Dates = [Dates, row above]+1

## Manpower (hidden)
| Manpower Deployed |  |  |  | Staff
| 2023-09-14 | Available |  |  | Project Manager | 1
A | Workers |  |  |  | Dy. Project Manager | 1
1 | Unskilled Labour | 32 |  |  | Project Engineer | 1
2 | Scaffolders and Helper | 30 |  |  | Site Engineer | 3
4 | Mason | 12 |  |  | P&M | 1
5 | Carpenter and helper | 60 |  |  | Quality | 1
6 | Fitter and helper | 131 |  |  | Supervisor | 5
7 | Welder & Fabricator | 4 |  |  | Surveyor | 2
8 | Rail Fixing | 7 |  |  | Planning | 1
9 | Erection | 15 |  |  | Billing | 1
| Total (A) | 291 |  |  | Accountant | 1
B | Staff | 27 |  |  | HR | 1
| Total (B) | 27 |  |  | Store | 1
| Total (A+B) | 318 |  |  | Electrician | 1
[5 empty] | Mechanic | 1
[5 empty] | Safety | 2
[5 empty] | Drivers | 3
27
To be updated on daily basis
Sr. No. | Date | Required | Actual | Shortfall | Remarks |  |  | Precast | Cast In-situ | Track Linking | Precast Erection | Total
| 2022-09-01 | 8 | 8 | 8
1 | 2022-09-01 | 6 | 6 |  | M/s. Rohan has aggred to increase the manpower from +170 to 280 Nos. by this month end.
2 | 2022-09-02 | 340 | 160
3 | 2022-09-03 | 340 | 155 | 185
4 | 2022-09-04 | 340 | 15 | 325
5 | 2022-09-05 | 340 | 140 | 200
6 | 2022-09-06 | 340 | 155 | 185
7 | 2022-09-07 | 340 | 158 | 182
8 | 2022-09-08 | 340 | 160 | 180
9 | 2022-09-09 | 340 | 164 | 176
10 | 2022-09-10 | 340 | 160 | 180
11 | 2022-09-11 | 340 | 20 | 320
12 | 2022-09-12 | 340 | 155 | 185
13 | 2022-09-13 | 340 | 166 | 174
14 | 2022-09-14 | 340 | 175 | 165
15 | 2022-09-15 | 340 | 174 | 166
16 | 2022-09-16 | 340 | 174 | 166
17 | 2022-09-17 | 340 | 0 | 340
18 | 2022-09-18 | 340 | 42 | 298
19 | 2022-09-19 | 340 | 169 | 171
20 | 2022-09-20 | 340 | 168 | 172
21 | 2022-09-21 | 340 | 170 | 170
22 | 2022-09-22 | 340 | 167 | 173
23 | 2022-09-23 | 340 | 167 | 173
24 | 2022-09-24 | 340 | 167 | 173
25 | 2022-09-25 | 340 | 0 | 340
26 | 2022-09-26 | 340 | 195 | 145
27 | 2022-09-27 | 340 | 199 | 141
28 | 2022-09-28 | 340 | 199 | 141
29 | 2022-09-29 | 340 | 200 | 140
30 | 2022-09-30 | 340 | 203 | 137
| 2022-10-01 | 340 | 219.2083 | 164.6333
1 | 2022-10-01 | 340 | 203 | 137
2 | 2022-10-02 | 340 |  | 340
3 | 2022-10-03 | 340 | 199 | 141
4 | 2022-10-04 | 340 | 204 | 136
5 | 2022-10-05 | 340 | 157 | 183
6 | 2022-10-06 | 340 | 199 | 141
7 | 2022-10-07 | 340 | 200 | 140
8 | 2022-10-08 | 340 | 228 | 112
9 | 2022-10-09 | 340 |  | 340
10 | 2022-10-10 | 340 | 231 | 109
11 | 2022-10-11 | 340 | 227 | 113
12 | 2022-10-12 | 340 | 228 | 112
13 | 2022-10-13 | 340 | 232 | 108
14 | 2022-10-14 | 340 | 234 | 106
15 | 2022-10-15 | 340 | 231 | 109
16 | 2022-10-16 | 340 |  | 340
17 | 2022-10-17 | 340 | 234 | 106
18 | 2022-10-18 | 340 | 230 | 110
19 | 2022-10-19 | 340 | 229 | 111
20 | 2022-10-20 | 340 | 231 | 109
21 | 2022-10-21 | 340 | 236 | 104
22 | 2022-10-22 | 340 | 235 | 105
23 | 2022-10-23 | 340 |  | 340
24 | 2022-10-24 | 340 |  | 340
25 | 2022-10-25 | 340 | 165 | 175
26 | 2022-10-26 | 340 | 220 | 120
27 | 2022-10-27 | 340 | 235 | 105
28 | 2022-10-28 | 340 | 236 | 104
29 | 2022-10-29 | 340 | 237 | 103
30 | 2022-10-30 | 340 |  | 340
31 | 2022-10-31 | 340 | 236 | 104
| 2022-11-01 | 340 | 263.8077 | 111.3667
1 | 2022-11-01 | 340 | 237 | 103
2 | 2022-11-02 | 340 | 241 | 99
3 | 2022-11-03 | 340 | 238 | 102
4 | 2022-11-04 | 340 | 242 | 98
5 | 2022-11-05 | 340 | 241 | 99
6 | 2022-11-06 | 340 |  | 340
7 | 2022-11-07 | 340 | 239 | 101
8 | 2022-11-08 | 340 | 243 | 97
9 | 2022-11-09 | 340 | 246 | 94
10 | 2022-11-10 | 340 | 245 | 95
11 | 2022-11-11 | 340 | 261 | 79
12 | 2022-11-12 | 340 | 261 | 79
13 | 2022-11-13 | 340 |  | 340
14 | 2022-11-14 | 340 | 269 | 71
15 | 2022-11-15 | 340 | 266 | 74
16 | 2022-11-16 | 340 | 267 | 73
17 | 2022-11-17 | 340 | 270 | 70
18 | 2022-11-18 | 340 | 270 | 70
19 | 2022-11-19 | 340 | 270 | 70
20 | 2022-11-20 | 340 |  | 340
21 | 2022-11-21 | 340 | 270 | 70
22 | 2022-11-22 | 340 | 281 | 59
23 | 2022-11-23 | 340 | 280 | 60
24 | 2022-11-24 | 340 | 279 | 61
25 | 2022-11-25 | 340 | 279 | 61
26 | 2022-11-26 | 340 | 279 | 61
27 | 2022-11-27 | 340 |  | 340
28 | 2022-11-28 | 340 | 279 | 61
29 | 2022-11-29 | 340 | 301 | 39
30 | 2022-11-30 | 340 | 305 | 35
| 2022-12-01 | 340 | 298.8519 | 71.0333
1 | 2022-12-01 | 340 | 306 | 34
2 | 2022-12-02 | 340 | 303 | 37
3 | 2022-12-03 | 340 | 309 | 31
4 | 2022-12-04 | 340 |  | 340
5 | 2022-12-05 | 340 | 310 | 30
6 | 2022-12-06 | 340 | 305 | 35
7 | 2022-12-07 | 340 | 305 | 35
8 | 2022-12-08 | 340 | 306 | 34
9 | 2022-12-09 | 340 | 309 | 31
10 | 2022-12-10 | 340 | 310 | 30
11 | 2022-12-11 | 340 | 150 | 190
12 | 2022-12-12 | 340 | 283 | 57
13 | 2022-12-13 | 340 |  | 340
14 | 2022-12-14 | 340 | 308 | 32
15 | 2022-12-15 | 340 | 310 | 30
16 | 2022-12-16 | 340 | 304 | 36
17 | 2022-12-17 | 340 | 298 | 42
18 | 2022-12-18 | 340 | 302 | 38
19 | 2022-12-19 | 340 | 308 | 32
20 | 2022-12-20 | 340 | 308 | 32
21 | 2022-12-21 | 340 | 309 | 31
22 | 2022-12-22 | 340 | 308 | 32
23 | 2022-12-23 | 340 | 307 | 33
24 | 2022-12-24 | 340 | 310 | 30
25 | 2022-12-25 | 340 |  | 340
26 | 2022-12-26 | 340 | 301 | 39
27 | 2022-12-27 | 340 | 305 | 35
28 | 2022-12-28 | 340 | 297 | 43
29 | 2022-12-29 | 340 | 300 | 40
30 | 2022-12-30 | 340 | 298 | 42
31 | 2022-12-31 | 340 | 301 | 39
| 2023-01-01 | 425 | 308.28 | 168.1
1 | 2023-01-01 | 425 |  | 425
2 | 2023-01-02 | 425 | 290 | 135
3 | 2023-01-03 | 425 | 302 | 123
4 | 2023-01-04 | 425 | 300 | 125
5 | 2023-01-05 | 425 | 305 | 120
6 | 2023-01-06 | 425 | 302 | 123
7 | 2023-01-07 | 425 | 305 | 120
8 | 2023-01-08 | 425 |  | 425
9 | 2023-01-09 | 425 | 311 | 114
10 | 2023-01-10 | 425 | 313 | 112
11 | 2023-01-11 | 425 | 312 | 113
12 | 2023-01-12 | 425 | 310 | 115
13 | 2023-01-13 | 425 | 311 | 114
14 | 2023-01-14 | 425 | 309 | 116
15 | 2023-01-15 | 425 |  | 425
16 | 2023-01-16 | 425 | 303 | 122
17 | 2023-01-17 | 425 | 308 | 117
18 | 2023-01-18 | 425 | 312 | 113
19 | 2023-01-19 | 425 | 310 | 115
20 | 2023-01-20 | 425 | 313 | 112
21 | 2023-01-21 | 425 | 313 | 112
22 | 2023-01-22 | 425 |  | 425
23 | 2023-01-23 | 425 | 305 | 120
24 | 2023-01-24 | 425 | 313 | 112
25 | 2023-01-25 | 425 | 310 | 115
26 | 2023-01-26 | 425 | 310 | 115
27 | 2023-01-27 | 425 | 315 | 110
28 | 2023-01-28 | 425 | 315 | 110
29 | 2023-01-29 | 425 |  | 425
30 | 2023-01-30 | 425 | 310 | 115
31 | 2023-01-31 | 425 | 318 | 107
| 2023-02-01 | 425 | 311.5417 | 157.9643
1 | 2023-02-01 | 425 | 308 | 117
2 | 2023-02-02 | 425 | 318 | 107
3 | 2023-02-03 | 425 | 312 | 113
4 | 2023-02-04 | 425 | 315 | 110
5 | 2023-02-05 | 425 |  | 425
6 | 2023-02-06 | 425 | 307 | 118
7 | 2023-02-07 | 425 | 310 | 115
8 | 2023-02-08 | 425 | 318 | 107
9 | 2023-02-09 | 425 | 315 | 110
10 | 2023-02-10 | 425 | 315 | 110
11 | 2023-02-11 | 425 | 312 | 113
12 | 2023-02-12 | 425 |  | 425
13 | 2023-02-13 | 425 | 310 | 115
14 | 2023-02-14 | 425 | 313 | 112
15 | 2023-02-15 | 425 | 316 | 109
16 | 2023-02-16 | 425 | 319 | 106
17 | 2023-02-17 | 425 | 315 | 110
18 | 2023-02-18 | 425 | 319 | 106
19 | 2023-02-19 | 425 |  | 425
20 | 2023-02-20 | 425 | 308 | 117
21 | 2023-02-21 | 425 | 312 | 113
22 | 2023-02-22 | 425 | 314 | 111
23 | 2023-02-23 | 425 | 315 | 110
24 | 2023-02-24 | 425 | 302 | 123
25 | 2023-02-25 | 425 | 302 | 123
26 | 2023-02-26 | 425 |  | 425
27 | 2023-02-27 | 425 | 303 | 122
28 | 2023-02-28 | 425 | 299 | 126
| 2023-03-01 | 425 | 238.3913 | 229.1786
1 | 2023-03-01 | 425 | 290 | 135
2 | 2023-03-02 | 425 | 285 | 140
3 | 2023-03-03 | 425 | 283 | 142
4 | 2023-03-04 | 425 | 240 | 185 | Due to Holi
5 | 2023-03-05 | 425 |  | 425
6 | 2023-03-06 | 425 | 240 | 185 | Due to Holi
7 | 2023-03-07 | 425 | 230 | 195 | Due to Holi
8 | 2023-03-08 | 425 |  | 425
9 | 2023-03-09 | 425 | 223 | 202 | Due to Holi
10 | 2023-03-10 | 425 | 225 | 200
11 | 2023-03-11 | 425 | 231 | 194
12 | 2023-03-12 | 425 |  | 425
13 | 2023-03-13 | 425 | 231 | 194
14 | 2023-03-14 | 425 | 234 | 191
15 | 2023-03-15 | 425 | 239 | 186
16 | 2023-03-16 | 425 | 232 | 193
17 | 2023-03-17 | 425 | 233 | 192
18 | 2023-03-18 | 425 | 240 | 185
19 | 2023-03-19 | 425 |  | 425
20 | 2023-03-20 | 425 | 232 | 193
21 | 2023-03-21 | 425 | 229 | 196
22 | 2023-03-22 | 425 | 225 | 200
23 | 2023-03-23 | 425 | 230 | 195
24 | 2023-03-24 | 425 | 224 | 201
25 | 2023-03-25 | 425 | 222 | 203
26 | 2023-03-26 | 425 |  | 425
27 | 2023-03-27 | 425 | 231 | 194
28 | 2023-03-28 | 425 | 234 | 191
29 | 2023-03-29 | 425 | 236 | 189
30 | 2023-03-30 | 425 | 235 | 190
31 | 2023-03-31 | 425 | 237 | 188
| 2023-04-01 | 425 | 211.7917 | 243.4643
1 | 2023-04-01 | 425 | 233 | 192
2 | 2023-04-02 | 425 |  | 425
3 | 2023-04-03 | 425 | 236 | 189
4 | 2023-04-04 | 425 | 232 | 193
5 | 2023-04-05 | 425 | 240 | 185
6 | 2023-04-06 | 425 | 243 | 182
7 | 2023-04-07 | 425 | 245 | 180
8 | 2023-04-08 | 425 | 246 | 179
9 | 2023-04-09 | 425 |  | 425
10 | 2023-04-10 | 425 | 237 | 188
11 | 2023-04-11 | 425 | 233 | 192
12 | 2023-04-12 | 425 | 235 | 190
13 | 2023-04-13 | 425 | 232 | 193
14 | 2023-04-14 | 425 | 237 | 188
15 | 2023-04-15 | 425 | 238 | 187
16 | 2023-04-16 | 425 |  | 425
17 | 2023-04-17 | 425 | 225 | 200
18 | 2023-04-18 | 425 | 228 | 197
19 | 2023-04-19 | 425 | 226 | 199
20 | 2023-04-20 | 425 | 224 | 201
21 | 2023-04-21 | 425 | 180 | 245 | Due to Eid
22 | 2023-04-22 | 425 | 160 | 265 | Due to Eid
23 | 2023-04-23 | 425 |  | 425
24 | 2023-04-24 | 425 | 150 | 275 | Due to Eid
25 | 2023-04-25 | 425 | 148 | 277 | Due to Eid
26 | 2023-04-26 | 425 | 151 | 274
27 | 2023-04-27 | 425 | 149 | 276
28 | 2023-04-28 | 425 | 155 | 270
29 | 2023-04-29 | 425 | 158 | 267
30 | 2023-04-30 | 425 |  | 425
| 2023-05-01 | 325 | 159.5 | 176.8929
1 | 2023-05-01 | 325 | 168 | 157
2 | 2023-05-02 | 325 | 169 | 156
3 | 2023-05-03 | 325 | 167 | 158
4 | 2023-05-04 | 325 | 168 | 157
5 | 2023-05-05 | 325 | 169 | 156
6 | 2023-05-06 | 325 | 170 | 155
7 | 2023-05-07 | 325 |  | 325
8 | 2023-05-08 | 325 | 165 | 160
9 | 2023-05-09 | 325 | 172 | 153
10 | 2023-05-10 | 325 | 175 | 150
11 | 2023-05-11 | 325 | 173 | 152
12 | 2023-05-12 | 325 | 125 | 200 | Due to Ban on Mobile, 70 labour are absent
13 | 2023-05-13 | 325 | 140 | 185 | Due to Ban on Mobile, 55 labour are absent
14 | 2023-05-14 | 325 | 130 | 195
15 | 2023-05-15 | 325 | 133 | 192
16 | 2023-05-16 | 325 | 146 | 179
17 | 2023-05-17 | 325 | 152 | 173
18 | 2023-05-18 | 325 | 161 | 164
19 | 2023-05-19 | 325 | 161 | 164
20 | 2023-05-20 | 325 | 157 | 168
21 | 2023-05-21 | 325 | 130 | 195
22 | 2023-05-22 | 325 | 162 | 163
23 | 2023-05-23 | 325 | 164 | 161
24 | 2023-05-24 | 325 | 165 | 160
25 | 2023-05-25 | 325 | 165 | 160
26 | 2023-05-26 | 325 | 169 | 156
27 | 2023-05-27 | 325 | 191 | 134
28 | 2023-05-28 | 325 |  | 325
29 | 2023-05-29 | 325 | 193 | 132
30 | 2023-05-30 | 325 | 198 | 127
31 | 2023-05-31 | 325 | 199 | 126
| 2023-06-01 | 325 | 226.0833 | 131.2143
1 | 2023-06-01 | 325 | 205 | 120
2 | 2023-06-02 | 325 | 210 | 115
3 | 2023-06-03 | 325 | 209 | 116
4 | 2023-06-04 | 325 |  | 325
5 | 2023-06-05 | 325 | 195 | 130
6 | 2023-06-06 | 325 | 211 | 114
7 | 2023-06-07 | 325 | 214 | 111
8 | 2023-06-08 | 325 | 212 | 113
9 | 2023-06-09 | 325 | 213 | 112
10 | 2023-06-10 | 325 | 215 | 110
11 | 2023-06-11 | 325 |  | 325
12 | 2023-06-12 | 325 | 210 | 115
13 | 2023-06-13 | 325 | 211 | 114
14 | 2023-06-14 | 325 | 213 | 112
15 | 2023-06-15 | 325 | 211 | 114
16 | 2023-06-16 | 325 | 214 | 111
17 | 2023-06-17 | 325 | 251 | 74
18 | 2023-06-18 | 325 |  | 325
19 | 2023-06-19 | 325 | 246 | 79
20 | 2023-06-20 | 325 | 248 | 77
21 | 2023-06-21 | 325 | 249 | 76
22 | 2023-06-22 | 325 | 251 | 74
23 | 2023-06-23 | 325 | 249 | 76
24 | 2023-06-24 | 325 | 250 | 75
25 | 2023-06-25 | 325 |  | 325
26 | 2023-06-26 | 325 | 246 | 79
27 | 2023-06-27 | 325 | 245 | 80
28 | 2023-06-28 | 325 | 248 | 77
29 | 2023-06-29 | 325 | 210 | 115 | Due to Eid
30 | 2023-06-30 | 325 | 202 | 123 | Due to Eid
| 2023-07-01 | 325 | 271.8333 | 92
1 | 2023-07-01 | 325 | 220 | 105
2 | 2023-07-02 | 325 |  | 325
3 | 2023-07-03 | 325 | 230 | 95
4 | 2023-07-04 | 325 | 241 | 84
5 | 2023-07-05 | 325 | 245 | 80
6 | 2023-07-06 | 325 | 248 | 77
7 | 2023-07-07 | 325 | 249 | 76
8 | 2023-07-08 | 325 | 247 | 78
9 | 2023-07-09 | 325 |  | 325
10 | 2023-07-10 | 325 | 240 | 85
11 | 2023-07-11 | 325 | 248 | 77
12 | 2023-07-12 | 325 | 259 | 66
13 | 2023-07-13 | 325 | 271 | 54
14 | 2023-07-14 | 325 | 280 | 45
15 | 2023-07-15 | 325 | 285 | 40
16 | 2023-07-16 | 325 |  | 325
17 | 2023-07-17 | 325 | 241 | 84
18 | 2023-07-18 | 325 | 291 | 34
19 | 2023-07-19 | 325 | 300 | 25
20 | 2023-07-20 | 325 | 301 | 24
21 | 2023-07-21 | 325 | 303 | 22
22 | 2023-07-22 | 325 | 301 | 24
23 | 2023-07-23 | 325 |  | 325
24 | 2023-07-24 | 325 | 305 | 20
25 | 2023-07-25 | 325 | 304 | 21
26 | 2023-07-26 | 325 | 303 | 22
27 | 2023-07-27 | 325 | 305 | 20
28 | 2023-07-28 | 325 | 307 | 18
29 | 2023-07-29 | 325 | 304 | 21
30 | 2023-07-30 | 325 |  | 325
31 | 2023-07-31 | 325 | 257 | 68 | Due to Muharram
| 2023-08-01 | 325 | 306.8696 | 72.9286
1 | 2023-07-01 | 325 | 308 | 17
2 | 2023-07-02 | 325 | 309 | 16
3 | 2023-07-03 | 325 | 305 | 20
4 | 2023-07-04 | 325 | 306 | 19
5 | 2023-07-05 | 325 | 303 | 22
6 | 2023-07-06 | 325 |  | 325
7 | 2023-07-07 | 325 | 308 | 17
8 | 2023-07-08 | 325 | 310 | 15
9 | 2023-07-09 | 325 | 311 | 14
10 | 2023-07-10 | 325 | 308 | 17
11 | 2023-07-11 | 325 | 309 | 16
12 | 2023-07-12 | 325 | 307 | 18
13 | 2023-07-13 | 325 |  | 325
14 | 2023-07-14 | 325 | 305 | 20
15 | 2023-07-15 | 325 |  | 325
16 | 2023-07-16 | 325 | 308 | 17
17 | 2023-07-17 | 325 | 309 | 16
18 | 2023-07-18 | 325 | 303 | 22
19 | 2023-07-19 | 325 | 307 | 18
20 | 2023-07-20 | 325 |  | 325
21 | 2023-07-21 | 325 | 300 | 25
22 | 2023-07-22 | 325 | 307 | 18
23 | 2023-07-23 | 325 | 310 | 15
24 | 2023-07-24 | 325 | 306 | 19
25 | 2023-07-25 | 325 | 309 | 16
26 | 2023-07-26 | 325 | 310 | 15
27 | 2023-07-27 | 325 |  | 325
28 | 2023-07-28 | 325 | 300 | 25
29 | 2023-07-29 | 325 | 308 | 17
30 | 2023-07-30 | 325 | 305 | 20
31 | 2023-07-31 | 325 | 307 | 18
| 2023-09-01 | 350 | 313.8077 | 58.6071
1 | 2023-09-01 | 350 | 305 | 45
2 | 2023-09-02 | 350 | 312 | 38
3 | 2023-09-03 | 350 | 250 | 100
4 | 2023-09-04 | 350 | 312 | 38
5 | 2023-09-05 | 350 | 308 | 42
6 | 2023-09-06 | 350 | 315 | 35
7 | 2023-09-07 | 350 | 311 | 39
8 | 2023-09-08 | 350 | 305 | 45
9 | 2023-09-09 | 350 | 316 | 34
10 | 2023-09-10 | 350 | 304 | 46
11 | 2023-09-11 | 350 | 310 | 40
12 | 2023-09-12 | 350 | 314 | 36
13 | 2023-09-13 | 350 | 311 | 39
14 | 2023-09-14 | 350 | 315 | 35
15 | 2023-09-15 | 350 | 312 | 38
16 | 2023-09-16 | 350 | 313 | 37
17 | 2023-09-17 | 350 |  | 350
18 | 2023-09-18 | 350 | 305 | 45
19 | 2023-09-19 | 350 | 318 | 32
20 | 2023-09-20 | 350 | 315 | 35
21 | 2023-09-21 | 350 | 321 | 29
22 | 2023-09-22 | 350 | 325 | 25
23 | 2023-09-23 | 350 | 327 | 23
24 | 2023-09-24 | 350 |  | 350
25 | 2023-09-25 | 350 | 322 | 28
26 | 2023-09-26 | 350 | 327 | 23
27 | 2023-09-27 | 350 | 326 | 24
28 | 2023-09-28 | 350 | 360 | -10
29 | 2023-09-29 | 350 | 370 | -20
30 | 2023-09-30 | 350 | 365 | -15
31 | 2023-10-01 | 350 |  | 350
| 2023-10-01 | 350 | 357.0455 | 69.4643
1 | 2023-10-01 | 350 |  | 350
2 | 2023-10-02 | 350 |  | 350
3 | 2023-10-03 | 350 | 356 | -6
4 | 2023-10-04 | 350 | 359 | -9
5 | 2023-10-05 | 350 | 364 | -14
6 | 2023-10-06 | 350 | 364 | -14
7 | 2023-10-07 | 350 | 367 | -17
8 | 2023-10-08 | 350 |  | 350
9 | 2023-10-09 | 350 | 352 | -2
10 | 2023-10-10 | 350 | 362 | -12
11 | 2023-10-11 | 350 | 358 | -8
12 | 2023-10-12 | 350 | 360 | -10
13 | 2023-10-13 | 350 | 359 | -9
14 | 2023-10-14 | 350 | 356 | -6
15 | 2023-10-15 | 350 |  | 350
16 | 2023-10-16 | 350 | 352 | -2
17 | 2023-10-17 | 350 | 358 | -8
18 | 2023-10-18 | 350 | 362 | -12
19 | 2023-10-19 | 350 | 357 | -7
20 | 2023-10-20 | 350 | 354 | -4
21 | 2023-10-21 | 350 | 351 | -1
22 | 2023-10-22 | 350 |  | 350
23 | 2023-10-23 | 350 | 348 | 2
24 | 2023-10-24 | 350 |  | 350
25 | 2023-10-25 | 350 | 347 | 3
26 | 2023-10-26 | 350 | 357 | -7
27 | 2023-10-27 | 350 | 358 | -8
28 | 2023-10-28 | 350 | 354 | -4
29 | 2023-10-29 | 350 |  | 350
30 | 2023-10-30 | 350 | 358 | -8
31 | 2023-10-31 | 350 | 360 | -10
| 2023-11-01 | 350 | 263.7083 | 133.9643
1 | 2023-11-01 | 350 | 359 | -9
2 | 2023-11-02 | 350 | 358 | -8
3 | 2023-11-03 | 350 | 359 | -9
4 | 2023-11-04 | 350 | 361 | -11
5 | 2023-11-05 | 350 | 154 | 196
6 | 2023-11-06 | 350 |  | 350
7 | 2023-11-07 | 350 | 259 | 91
8 | 2023-11-08 | 350 | 261 | 89
9 | 2023-11-09 | 350 | 241 | 109
10 | 2023-11-10 | 350 | 229 | 121
11 | 2023-11-11 | 350 | 239 | 111
12 | 2023-11-12 | 350 |  | 350
13 | 2023-11-13 | 350 |  | 350
14 | 2023-11-14 | 350 |  | 350
15 | 2023-11-15 | 350 | 230 | 120
16 | 2023-11-16 | 350 | 242 | 108
17 | 2023-11-17 | 350 | 238 | 112
18 | 2023-11-18 | 350 | 246 | 104
19 | 2023-11-19 | 350 | 229 | 121
20 | 2023-11-20 | 350 | 233 | 117
21 | 2023-11-21 | 350 | 239 | 111
22 | 2023-11-22 | 350 | 251 | 99
23 | 2023-11-23 | 350 | 260 | 90
24 | 2023-11-24 | 350 | 265 | 85
25 | 2023-11-25 | 350 | 268 | 82
26 | 2023-11-26 | 350 |  | 350
27 | 2023-11-27 | 350 | 261 | 89
28 | 2023-11-28 | 350 | 267 | 83
29 | 2023-11-29 | 350 | 280 | 70
30 | 2023-11-30 | 350 |  | 350
| 2023-12-01 | 350 | 280.6 | 199.6786 |  |  | 2023-12-01 | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | 0
1 | 2023-12-01 | 350 | 281 | 69 |  |  | 2023-12-01 |  |  |  |  | 0
2 | 2023-12-02 | 350 | 285 | 65 |  |  | 2023-12-02 |  |  |  |  | 0
3 | 2023-12-03 | 350 |  | 350 |  |  | 2023-12-03 |  |  |  |  | 0
4 | 2023-12-04 | 350 | 250 | 100 |  |  | 2023-12-04 |  |  |  |  | 0
5 | 2023-12-05 | 350 | 258 | 92 |  |  | 2023-12-05 |  |  |  |  | 0
6 | 2023-12-06 | 350 | 253 | 97 |  |  | 2023-12-06 |  |  |  |  | 0
7 | 2023-12-07 | 350 | 255 | 95 |  |  | 2023-12-07 |  |  |  |  | 0
8 | 2023-12-08 | 350 | 263 | 87 |  |  | 2023-12-08 |  |  |  |  | 0
9 | 2023-12-09 | 350 | 278 | 72 |  |  | 2023-12-09 |  |  |  |  | 0
10 | 2023-12-10 | 350 |  | 350 |  |  | 2023-12-10 |  |  |  |  | 0
11 | 2023-12-11 | 350 | 259 | 91 |  |  | 2023-12-11 |  |  |  |  | 0
12 | 2023-12-12 | 350 | 289 | 61 |  |  | 2023-12-12 |  |  |  |  | 0
13 | 2023-12-13 | 350 | 298 | 52 |  |  | 2023-12-13 |  |  |  |  | 0
14 | 2023-12-14 | 350 | 305 | 45 |  |  | 2023-12-14 |  |  |  |  | 0
15 | 2023-12-15 | 350 | 309 | 41 |  |  | 2023-12-15 |  |  |  |  | 0
16 | 2023-12-16 | 350 | 315 | 35 |  |  | 2023-12-16 |  |  |  |  | 0
17 | 2023-12-17 | 350 |  | 350 |  |  | 2023-12-17 |  |  |  |  | 0
18 | 2023-12-18 | 350 | 311 | 39 |  |  | 2023-12-18 |  |  |  |  | 0
19 | 2023-12-19 | 350 |  | 350 |  |  | 2023-12-19 |  |  |  |  | 0
20 | 2023-12-20 | 350 |  | 350 |  |  | 2023-12-20 |  |  |  |  | 0
21 | 2023-12-21 | 350 |  | 350 |  |  | 2023-12-21 |  |  |  |  | 0
22 | 2023-12-22 | 350 |  | 350 |  |  | 2023-12-22 |  |  |  |  | 0
23 | 2023-12-23 | 350 |  | 350 |  |  | 2023-12-23 |  |  |  |  | 0
24 | 2023-12-24 | 350 |  | 350 |  |  | 2023-12-24 |  |  |  |  | 0
25 | 2023-12-25 | 350 |  | 350 |  |  | 2023-12-25 |  |  |  |  | 0
26 | 2023-12-26 | 350 |  | 350 |  |  | 2023-12-26 |  |  |  |  | 0
27 | 2023-12-27 | 350 |  | 350 |  |  | 2023-12-27 |  |  |  |  | 0
28 | 2023-12-28 | 350 |  | 350 |  |  | 2023-12-28 |  |  |  |  | 0
29 | 2023-12-29 | 350 |  | 350 |  |  | 2023-12-29 |  |  |  |  | 0
30 | 2023-12-30 | 350 |  | 350 |  |  | 2023-12-30 |  |  |  |  | 0
Formulas:
Workers = [Workers, row above]+1

## Micro (hidden)
Sl. No. | Location | Column details | No's of footings | Completion date | As on date status |  |  |  |  | As on date | Remarks | Responsibility | Hold ftgs |  | RCC Qty
[5 empty] | Excavation | Raft (Up to second layer) | 1900 mm dia | 1600 mm dia | Pier Cap |  |  |  | JSW | Front availability | JSW | Front availability | Completed Quantity | Remark
1 | Part A (1 to 82 No's) | 1 to 42 | 0 | [7 empty] | Scope changed from piers cap to formation line .
|  | 43/44/45/46 | 4 | 15.07.2022 | Completed | Completed | Completed | Completed | Completed | Completed |  | Rohan Builders | 0 | 4 |  |  |  | As per today MOM, Area Cleareance before 10th oct
|  | 47 & 48 | 2 |  | Completed | Completed | Completed | Completed | Completed | Work has not started |  | Rohan Builders | 0 | 2
|  | 49 & 50 | 2 |  | Completed | Completed | Completed | Completed | Completed | Work has not started |  | Rohan Builders | 0 | 2
|  | 51&52 | 2 |  | Completed | Completed | Completed | Completed | Completed | Work has not started |  | Rohan Builders | 0 | 2
|  | 53 to 63 | 12 |  | Completed | Completed | Completed | Completed | Completed | Work has not started |  | Rohan Builders | 0 | 12
|  | 64 to 65 | 2 |  | Completed | Completed | Completed | Completed | Completed | Work started |  | Rohan Builders | 0 | 2
|  | 66 & 67 | 2 |  | Completed | Completed | Completed | Completed | Completed | Completed |  | Rohan Builders | 0 | 2
|  | 68 to 76 | 8 |  | Completed | Completed | Completed | Completed | Completed | Work started |  | Rohan Builders | 0 | 8
|  | 77 to 82 | 6 |  | Completed | Completed | Completed | Completed | Completed | Not started | Required area clearance , need to remove the bulk reception unit to start excavation work . | Rohan Builders | 0 | 6
|  |  | 40 |  | 40 | 40 | 40 | 40 | 40 | 2 |  |  | 0 | 40 | 0 | 2414
2 | Part B (83 to 96 No's) | 83 to 89 | 14 |  | Completed | Completed | Completed | Completed | Completed | Not started | Required area clearance , need to remove the bulk reception unit to start excavation work . | Rohan Builders | 0 | 14
|  | 90 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  | Required area clearance , need to remove the bulk reception unit to start excavation work . | Rohan Builders | 0 | 2
|  | 91 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 2
|  | 92 | 2 |  | Completed | Completed | Completed | Completed | Completed | Completed up to pier (1900 mm dia) |  | Rohan Builders | 0 | 2
|  | 93 | 2 |  | Completed | Completed | Completed | Completed | Completed | Completed up to pier (1900 mm dia) |  | Rohan Builders | 0 | 2
|  | 94 | 2 | 26.08.2022 | Completed | Completed | Completed | Completed | Completed | Completed |  | Rohan Builders | 0 | 2
|  | 95 | 2 |  | Completed | Completed | Completed | Completed | Completed | Completed up to pier (1900 mm dia) |  | Rohan Builders | 0 | 2
|  | 96 | 2 |  | Completed | Completed | Completed | Completed | Completed | Completed up to pier (1900 mm dia) |  | Rohan Builders | 0 | 2
|  |  | 28 |  | 26 | 26 | 26 | 26 | 26 |  |  |  | 0 | 28 | 0 | 1408
3 | Part H(H 1 to H 20) | H1 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  | H2 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  | H3 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  | H4 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  | H5 | 3 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 3
|  | H6 | 3 |  | Completed | Completed | Completed | Completed | Completed | PCC completed |  | Rohan Builders | 0 | 3
|  | H7 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  | H8 to H 9 | 6 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 6
|  | H10 to H 11 | 6 |  | Completed | Completed | Completed | Completed | Completed | Started |  | Rohan Builders | 0 | 6
|  | H12 | 1 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 1
|  | H 13 | 3 |  | Completed | Completed | Completed | Completed | Completed | Not stared |  | Rohan Builders | 0 | 3
|  | H 14 | 1 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 1
|  | H 15 | 3 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 3
|  | H 16 | 1 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 1
|  | 17 to 19 | 6 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 6
|  | H 18 | 1 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 1
|  | H 20 | 1 |  | Completed | Completed | Completed | Completed | In progress | Not started | Hold By MECON | MECON | 0 | 1
|  |  | 50 |  | 50 | 50 | 50 | 50 | 49 | 0 |  |  | 0 | 50 | 0 | 2073.0769
4 | Part G (1 to 30) | G1 | 2 |  | Completed | Completed | Completed | Completed | Completed | Not started | Excavation permitt due to plants and electric | Rohan Builders | 0 | 2
|  | G2 | 2 |  | Completed | In Progress | In Progress | In progress | Not started | Not started | Footing is falling below Conveyor Belt footing | Rohan Builders | 1 | 1
|  | G3 | 2 |  | Completed | Completed | Completed | Completed | Completed |  | Required road clearance near at BRM 2 internal road | Rohan Builders | 0 | 2
|  | G4 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  |  | Rohan Builders | 2
|  | G5 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  |  | Rohan Builders | 2
|  | G6 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G7 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G8 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G9 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G10 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G11 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G12 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G13 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 2
|  | G14 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 2
|  | G15 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 2
|  | G16 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | G17 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | MECON | 2
|  | G18 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | MECON | 2
|  | G19 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | MECON | 2
|  | G20 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | MECON | 2
|  | G21 | 2 |  | Completed | In Progress | In Progress | In progress | Not started |  | Hold By MECON | MECON | 2
|  | G22 | 2 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 2
|  | G23 | 2 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 3
|  | G24 | 2 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 2
|  | G25 | 2 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 3
|  | G26 | 2 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 3
|  | G27 | 2 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 2
|  | G28 | 3 |  | Completed | Completed | Completed | Not started | Not started |  | Hold By MECON | MECON | 3
|  | G29 | 1 |  | Completed | Completed | Completed | Completed | In progress |  | Hold By MECON | MECON | 1
|  | G30 | 2 |  | Completed | Completed | In Progress | Not started | Not started |  | Hold By MECON | MECON | 2
|  |  | 60 |  | 56 | 52 | 50 | 35 | 20 |  |  |  | 36 | 27 | 2836.4516 | 2127.3387
5 | Part C | C1 | 3 |  | Completed | Completed | Completed | Completed | Completed | Not started | In progress | Rohan Builders | 0 | 2
|  | C2 | 2 |  | Completed | Completed | Completed | Completed | Completed | Excavation completed |  | Rohan Builders | 0 | 2
|  | C3 | 2 |  | Completed | Completed | Completed | Completed | Completed | Steel fixing completed. |  | Rohan Builders | 0 | 2
|  | C4 | 2 |  | Completed | Completed | Completed | Completed | Completed | Raft completed. |  | Rohan Builders | 0 | 2
|  | C5 | 2 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 2
|  | C6 | 2 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders |  | 2
|  | C7 | 2 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 2
|  | C8 | 2 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 2
|  | C9 | 2 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 2
|  | C10 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | C11 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | C12 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  | Cable Gallery footing obsticle | JSW | 2
|  | C13 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  | NALA | JSW | 2
|  | C14 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  |  | JSW | 2
|  | C15 | 2 |  | Completed | Completed | Completed | Completed | Completed |  | Front available hold by MECON | MECON |  | 2
|  | C16 | 2 |  | Completed | Completed | Completed | Completed | Completed |  | Front available hold by MECON | MECON |  | 2
|  | C17 | 2 |  | Completed | Completed | Completed | Completed | Completed |  | Front available hold by MECON | MECON |  | 2
|  | C18 | 1 |  | Completed | Completed | Completed | Completed | Completed |  | Front available hold by MECON | MECON |  | 2
|  | C19 | 2 |  | Completed | Completed | Completed | Completed | Completed |  | Front available hold by MECON | MECON |  | 2
|  | C20 | 2 |  | Completed | Completed | Completed | Completed | Completed |  | Work Under Progress | Rohan Builders |  | 2
|  |  | 40 |  | 34 | 34 | 34 | 34 | 34 |  |  |  | 6 | 34 | 515.55 | 2921.45
6 | Part I | I1 to 3 | 9 |  | Completed | Completed | Completed | Completed | Completed | Raft completed. |  | Rohan Builders | 0 | 9
|  | I4 to 9 | 20 |  | Completed | Completed | Completed | Completed | Completed | Back filling completed up tp 1900mm pier |  | Rohan Builders | 0 | 20
|  | I10 | 4 |  | Completed | Completed | Completed | Completed | Completed | 1Footing completed |  | Rohan Builders | 0 | 4
|  | I11&12 | 4 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 4
|  | I13 | 2 |  | Completed | Completed | Completed | Completed | Completed | Excavation completed |  | Rohan Builders | 0 | 2
|  | I14&15 | 4 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 4
|  | I16 | 2 |  | Completed | Completed | Completed | Completed | Completed | 1Footing completed out of 2 |  | Rohan Builders | 0 | 2
|  | I17/18/19 | 6 |  | Completed | Completed | Completed | Completed | Completed | Excavation Started |  | Rohan Builders | 0 | 6
|  | I20&21 | 4 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 4
|  |  | 55 |  | 55 | 55 | 55 | 55 | 55 |  |  |  | 0 | 55 | 0 | 2141
7 | Part D | D1 to 5 | 0 | [6 empty] | Not started |  |  | 0 | 0
|  | D6 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | D7 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  | D8 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1/3 Started. |  | Rohan Builders | 0 | 3
|  | D9 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1/3 Started. |  | Rohan Builders | 0 | 3
|  | D10 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1/3 Started. |  | Rohan Builders | 0 | 3
|  | D11 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm Pier completed. |  | Rohan Builders | 0 | 3
|  | D12 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm Pier completed. |  | Rohan Builders | 0 | 3
|  | D13 TO 16 | 12 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 12
|  | D17 to 22 | 18 |  | Completed | Completed | Completed | Completed | Completed | Not started |  | Rohan Builders | 0 | 18
|  | D23 | 3 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 3
|  |  | 54 |  | 54 | 54 | 54 | 54 | 54 |  |  |  | 0 | 54 | 0 | 2668
8 | Part F | F1 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | F2 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | F3 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | F4 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1900mm pier completed |  | Rohan Builders | 0 | 3
|  | F5 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm 1st lift column completed |  | Rohan Builders | 0 | 3
|  | F6 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm 1st lift column completed | pier cap pending. | Rohan Builders | 0 | 3
|  | F7 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm 1st lift column completed | pier cap pending. | Rohan Builders | 0 | 3
|  | F8 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm 1st lift column completed | pier cap pending. | Rohan Builders | 0 | 3
|  | F9 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm 1st lift column completed | pier cap pending. | Rohan Builders | 0 | 3
|  | F10 | 3 |  | Completed | Completed | Completed | Completed | Completed | 1600mm column completed | pier cap pending. | Rohan Builders | 0 | 3
|  |  | 30 |  | 30 | 30 | 30 | 30 | 30 | 0 |  |  | 0 | 30 | 0 | 2442
9 | Part J | J1 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | J2 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | J3 | 3 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 3
|  | J4 | 4 |  | Completed | Completed | Completed | Completed | Completed | Completd up to 1900mm pier |  | Rohan Builders | 0 | 4
|  | J5 to J6 | 8 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders | 0 | 8
|  | J7 to J9 | 8 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders | 0 | 8
|  | J10 to J11 | 8 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders | 0 | 8
|  | J12 | 6 |  | Completed | Completed | Completed | Completed | Completed | Not started. |  | Rohan Builders | 0 | 6
|  |  | 43 |  | 43 | 43 | 43 | 43 | 27 |  |  |  | 0 | 43 | 0 | 2580
10 | Part E | E1 | 2 |  | In Progress | Not started | Not started | Not started | Not started |  | Cable Gallery footing obsticle | JSW | 2 |  |  | 0
|  | E2 | 2 |  | In Progress | In Progress | In Progress | In progress | Not started |  | Cable Gallery footing obsticle | Rohan Builders | 1 | 1
|  | E3 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | E4 | 2 |  | Completed | In Progress | Not started | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E5 | 2 |  | Completed | In Progress | Not started | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E6 | 2 |  | Completed | Not started | Not started | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E7 | 2 |  | Completed | In Progress | Not started | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E8 | 2 |  | Completed | In Progress | Not started | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E9 | 2 |  | Completed | Completed | In Progress | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E10 | 2 |  | Completed | Completed | In Progress | Not started | Not started |  | Road Diversion to be done by SMS#4 Team | JSW | 2
|  | E11 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | E12 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 2
|  | E13 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 2
|  | E14 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 2
|  | E15 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 2
|  | E16 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | MECON |  | 2
|  | E17 | 2 |  | Completed | Completed | Completed | Completed | In progress |  |  | MECON |  | 2
|  | E18 | 2 |  | Completed | Completed | Completed | Completed | Completed |  |  | MECON |  | 2
|  |  | 36 |  | 24 | 20 | 16 | 16 | 6 |  |  |  | 17 | 19 | 697 | 780
11 | Part K | K1 | 8 |  | Completed | Completed | Completed | Completed | Not started |  | Structural Material SMS4 Vendor | JSW | 8
|  | K2 | 8 |  | Completed | Completed | Completed | In progress | Not started |  | Structural Material SMS4 Vendor | JSW | 8
|  | K3 | 8 |  | Completed | Completed | Completed | In progress | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K4 | 8 |  | Completed | Completed | Completed | In progress | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K5 | 6 |  | Completed | Completed | Completed | In progress | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K6 | 6 |  | Completed | Completed | Completed | In progress | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K7 | 6 |  | Completed | Completed | Completed | Completed | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K8 | 6 |  | Completed | Completed | Completed | Completed | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K9 | 6 |  | Completed | Completed | Completed | Completed | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K10 | 6 |  | Completed | Completed | Completed | Completed | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K11 | 6 |  | Completed | Completed | Completed | Completed | Not started |  | Structural Material SMS4 Vendor | Rohan Builders |  | 6
|  | K12 | 6 |  | Completed | Completed | Completed | Completed | Not started |  |  | Rohan Builders |  | 6
|  | K13 | 5 |  | Completed | Completed | Completed | Completed | Not started |  |  | Rohan Builders |  | 5
|  | K14 | 5 |  | Completed | Completed | Completed | Completed | In progress |  |  | Rohan Builders |  | 5
|  | K15 | 4 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 4
|  | K16 | 4 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 4
|  | K17 | 4 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 4
|  | K18 | 4 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 4
|  | K19 | 4 |  | Completed | Completed | Completed | Completed | Completed |  |  | Rohan Builders |  | 4
|  |  | 110 |  | 110 | 110 | 110 | 74 | 20 |  |  |  | 16 | 90 | 1496.4444 | 0
| Grand Total |  | 546 |  | 522 | 514 | 508 | 457 | 361 |  |  |  | 75 | 470 | 5545.4461 | 21554.8656
| TOTAL RCC QUANTITIES |  | 546 |  |  | 12686 | 3097 | 3660 | 4758
76
54

## Trapezoidal- Girder Update (hidden)
Precast girder casting- Trapezoidal
Sr. No. | PART | Scope | Scope |  | Trapezoidal Girders- Casted |  |  |  |  | Balance
|  |  | Straight | Trapezoidal | Track Beam with Nose |  | Track Beam without Nose | h - Section Beam | U - Section Beam
1 | A | 266 | 266 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | B | 190 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3 | C | 232 | 120 | 112 | 46 | 0 | 20 | 22 | 23 | 1
4 | D | 184 | 184 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | E | 319 | 147 | 172 | 8 | 0 | 32 | 3 | 1 | 128
6 | F | 342 | 342 | 0 | 0 | 0 | 1 | 0 | 0 | -1
7 | G | 190 | 185 | 5 | 0 | 0 | 3 | 0 | 1 | 1
8 | H | 231 | 205 | 26 | 4 | 0 | 0 | 12 | 1 | 9
9 | I | 234 | 159 | 75 | 22 | 0 | 13 | 8 | 12 | 20
10 | J | 182 | 33 | 149 | 22 | 0 | 18 | 0 | 0 | 109
11 | K | 576 | 480 | 96 | 4 | 0 | 13 | 0 | 1 | 78
| Total | 2946 | 2311 | 635 | 106 | 0 | 100 | 45 | 39 | 345
BF Route |  | 1337 | 1124 | 213 | 72 | 0 | 33 | 42 | 36 | 30
SMS Route |  | 1290 | 1040 | 250 | 26 | 0 | 35 | 0 | 2 | 187
Link Route |  | 319 | 147 | 172 | 8 | 0 | 32 | 3 | 1 | 128
|  | 2946 | 2311 | 635 | 106 | 0 | 100 | 45 | 39 | 345
Balance to be casted | [9 empty] | 345
Up to Sep-23 |  |  |  |  | 58 | 0 | 36 | 4 | 5 | 103
Up to Oct-23 |  |  |  |  | 84 | 0 | 67 | 11 | 21 | 183
Up to Nov-23 |  |  |  |  | 100 | 0 | 98 | 32 | 39 | 269
2023-12-01 |  |  |  |  | 6 | 0 | 2 | 13 | 0 | 21
Balance for Dec-23 |  |  |  |  | 14 | 12 |  | 3 | 21 | 50

## Mat&Equip (hidden)
M/s. Rohan Builders - Resource details - Elevated Hot Metal Track
Sr. No. | Category | Particulars | UOM | Availability | Required | Shortfall | Remarks
1 | Precast molds | 1900 mm pier cap set | NO | 4 | 4 | 0
2 |  | 1600 mm dia pier cap set | NO | 27 | 12 | -15 | 2.5 mtr/19, 1.8 mtr/2, 1.25mtr/3, 0.6mtr/3 available.
3 |  | Pier cap sets | NO | 19 | 10 | -9 | 5 single Pier Cap, 8 Double Pier Cap, 5 Triple Pier Cap, 1 Quadraple Pier Cap available
4 |  | Track beam with side nose | NO | 3 | 3 | 0
5 |  | Track beam with out nose | NO | 5 | 3 | -2
6 |  | H - Beams | NO | 3 | 2 | -1
7 |  | U - Beams | NO | 3 | 2 | -1
8 |  | Solid with face nose | NO | 3 | 2 | -1
9 |  | Precast slab | NO | 5 | 3 | -2
10 | Equipments | 230 T Crane | NO | 1 | 1 | 0
|  | 80 T Crane | NO | 1 | 1 | 0
11 |  | Hydra | NO | 6 | 2 | -4 | 4 at site, 2 at Pre-cast yard
|  | Gantry | NO | 1 | 1 | 0 | Pre-cast Yard
12 |  | Trailer | NO | 5 | 2 | -3 | 1 at site, 3 at Pre-cast yard +1 Hired for steel lifting
13 |  | JCB | NO | 1 | 1 | 0
14 |  | Excavator | NO | 1 | 1 | 0
15 |  | Boom placer | NO | 2 | 1 | -1 | 1 own boom placer
16 |  | Mobile Crane | NO | 1 | 1 | 0
|  | Particulars | UOM | Availability | Required | Shortfall
|  | Track beam with side nose | nos. | 3 | 3 | 0
|  | Track beam with out nose | nos. | 5 | 3 | -2
|  | H - Beams | nos. | 3 | 2 | -1
|  | U - Beams | nos. | 3 | 2 | -1
|  | Solid with face nose | nos. | 3 | 2 | -1
|  | Precast slab | nos. | 5 | 3 | -2
|  | Total | nos. | 22 | 15 | -7

## Apr-23 Plan- OLD (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 |  |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 30 | 30 | 13 | 15 | 19 | 16 | 24 |  |  | Track beam with nose |  | 1140 | 95 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 90 | 260 | 75 | 114 | 80 | 535 | 1154 |  | Track beam without nose |  | 960 | 80
Part A | Nos. | 6 | 6 | 3 | 5 | 9 | 14 | 8 |  |  | h-section beam |  | 336 | 28
| Qty |  | 18 | 60 | 25 | 54 | 70 | 80 | 307 |  | U-section beam |  | 336 | 28
Part B | Nos. | 14 | 14 | [6 empty] | As front is not available 6 Pier Cap can be Achieved | Pre-cast Slab |  | 38 | 76
| Qty |  | 42 | 0 | 0 | 0 | 0 | 0 | 42 |  | Total: |  | 2810 | 307
Part H | Nos. | [6 empty] | 9 | [9 empty] | Month Plan | Interim
| Qty |  | 0 | 0 | 0 | 0 | 0 | 315 | 315 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 216 | 104.7085
Part C | Nos. | 10 | 10 | 10 | 10 | 10 | 2 | 6 |  | Clearence to be given by MECON for 10 footings by 7th Feb 2023 |  |  | A | 307 | 255.4545 | 562.4545 | RCC Foundation | 1100 | 533.2379
| Qty |  | 30 | 200 | 50 | 60 | 10 | 120 | 470 |  |  |  | B | 42 | 255.4545 | 297.4545 | Step Footing | 160 | 77.5619
Part I | Nos. | [11 empty] | C | 470 | 255.4545 | 725.4545 | Pier 1900 mm | 330 | 159.9714
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | D | 20 | 255.4545 | 275.4545 | Pier 1600 mm | 505 | 244.8047
Part D | Nos. | [6 empty] | 1 |  |  |  |  | E | 593 | 255.4545 | 848.4545 | Pier Cap | 535 | 259.3475
| Qty |  | 0 | 0 | 0 | 0 | 0 | 20 | 20 |  |  |  | F | 150 | 255.4545 | 405.4545 | Track Beam with Nose | 1140 | 552.6284
Priority Section-2 | Nos. | 42 | 42 | 42 | 17 | 36 | 85 | 0 |  |  |  |  | G | 110 | 255.4545 | 365.4545 | Track Beam without Nose | 960 | 465.3713
| Qty | 0 | 126 | 840 | 85 | 216 | 425 | 0 | 1692 |  |  |  | H | 315 | 255.4545 | 570.4545 | H - Section Beam | 336 | 162.8799
Part E | Nos. | 17 | 17 | 17 | 17 | 17 | 3 | [5 empty] | I | 0 | 255.4545 | 255.4545 | U - Section Beam | 336 | 162.8799
| Qty |  | 51 | 340 | 85 | 102 | 15 | 0 | 593 |  |  |  | J | 150 | 255.4545 | 405.4545 | Pre-cast Slab | 38 | 18.4209
Part F | Nos. | [5 empty] | 30 | [5 empty] | K | 689 | 255.4545 | 944.4545
| Qty |  | 0 | 0 | 0 | 0 | 150 | 0 | 150 |  |  |  |  | 2846 | 2810 | 5656
Part G | Nos. | [5 empty] | 22
| Qty |  | 0 | 0 | 0 | 0 | 110 | 0 | 110
Part J | Nos. | [5 empty] | 30
| Qty |  | 0 | 0 | 0 | 0 | 150 | 0 | 150
Part K | Nos. | 25 | 25 | 25 |  | 19 |  |  |  | Clearence to be given by 10th Feb 2023 from JSW.
| Qty |  | 75 | 500 | 0 | 114 | 0 | 0 | 689
Total | Nos. | 72 | 72 | 55 | 32 | 55 | 101 | 24
| Qty | 0 | 216 | 1100 | 160 | 330 | 505 | 535 | 2846
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 673.1397 | 23.96%
[10 empty] | Week 2 (9 to 16) | 703.2161 | 25.03%
[10 empty] | Week 3 (17 to 24) | 703.2161 | 25.03%
[10 empty] | Week 4 (25 to 31) | 730.4281 | 25.99%
[10 empty] | Total | 2810
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 597.374 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 767.901 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 767.901 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 712.824 | 25.05% | 25.52%
[10 empty] | Total | 2846
[10 empty] | Monthly Concreting Target | 5656 | cum
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 27 | 112 | 14 | 4 | 9 | 166 | [10 empty] | Month Plan | Interim
| Qty | 324 | 1344 | 168 | 48 | 108 | 1992 | [9 empty] | Track beam with nose | 27 | 8.1
Part A | Nos. | [5 empty] | 0 | [6 empty] | A | 0 |  | Track beam without nose | 112 | 33.6
| Qty | [5 empty] | 0 | [6 empty] | B | 0 |  | h-section beam | 14 | 4.2
Part B | Nos. | [5 empty] | 0 | [6 empty] | C | 0 |  | U-section beam | 4 | 1.2
| Qty | [5 empty] | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 9 | 2.7
Part H | Nos. | 13 | 62 | 8 | 4 | 9 | 96 | [6 empty] | E | 0
| Qty | 156 | 744 | 96 | 48 | 108 | 1152 | [6 empty] | F | 0
Part C | Nos. | [5 empty] | 0 | [6 empty] | G | 0
| Qty | [5 empty] | 0 | [6 empty] | H | 96
Part I | Nos. | 14 | 50 | 6 |  |  | 70 | [6 empty] | I | 70
| Qty | 168 | 600 | 72 | 0 | 0 | 840 | [6 empty] | J | 0
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | [5 empty] | 0 | [7 empty] | 166
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 16.6 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 33.2 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 58.1 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 58.1 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 166
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 27 | 112 | 14 | 4 | 9 | 166
| Qty | 324 | 1344 | 168 | 48 | 108 | 1992
FTM
Track Linking
A |  | 0
B |  | 0
C |  | 0
D |  | 300
E |  | 0
F |  | 0
G |  | 0
H |  | 0
I |  | 0
J |  | 0
K |  | 0

## Concerns (hidden)
Rohan Builders (I) Pvt Ltd
Project- JSW Bellary
Decision & Concern
Sr.No. | Date of Concern Raised | Concern | Date of Action Taken | Date of Closure | Remarks
1 | 2022-03-01 | 3 Set of A-1 Size hard copies of GFC yet to be issued by client | 2022-03-07 | 2022-04-05 | Received Only for Part A,B,D & F
2 | 2022-03-23 | Not Able to Raise requirement in Material requisition system app | 2022-03-23 | 2022-03-26 | -
3 | 2022-04-17 | The access for Part B (Pier No 91 to 95 ) have been blocked due to excavated foundation pit by other agency | 2022-04-18 | 2022-05-07
4 | 2022-04-16 | Site Clearance of Part D on South side of the excavated pit. | 2022-05-16 | 2022-06-07 | Cleared by Rohan Builders
5 | 2022-05-30 | Reinforcement of Pier Cap was submitted on 30th May 2022, reinforcement is not received till date, work is getting delayed | 2022-06-17 | 2022-06-27 | Reinforcement of 2 Pier Caps received on 20/06/2022, 2 Pier Caps reinforcement still remaining.Remaining reinforcement received on 27/06/2022
6 | 2022-06-20 | Concrete for Pre-cast not received as the mix desing was not tested by the JSW batching Plant. | 2022-06-20 | 2022-06-29
7 | 2022-06-21 | Reinforcement of Part D 12 footing was submitted on 15th June 2022 and priority date was given 20th June 2022, reinforcement is not received completely till date, work is getting delayed | 2022-06-21 | 2022-06-26 | 3 footing reinforcement was received in the evening of 21/06/2022, 3 footing received on 22/06/2022, reeived 6 footing reinforcement on 28/06/2022
8 | 2022-06-24 | Pier Cap work on hold, due to change in RL( nearly 500 mm), will resume the work after receiving revised drawings | 2022-06-24 | 2022-06-24 | Drawings received, have started de-shuttering and reinforcement unfixing
9 | 2022-07-09 | Complete set of drawings are not received, also revised drawing released by Mecon are not received | 2022-07-10 | 2022-07-13 | Revised Drawings are received
10 | 2022-07-09 | Concrete for Pre-cast segment(M-40) is having poor quality, can't used for concreting | 2022-07-19 | 2022-07-21 | Strength is achieved but workability is very low
11 | 2022-07-15 | Reinforcement of Part I 12 footing was submitted on 7th July 2022 and Priority date was given 15th June 2022, reinforcement is not received completely till date , work is getting delay, manpower becoming idle. | 2022-07-21 | 2022-07-23 | Cutting bending was given in RBIPL's scope
12 | 2022-07-16 | Reinforcement of Part I and J footing was submitted on 16th July 2022 and Priority date was given 20th July 2022, reinforcement fabrication not started yet, work is getting delay, manpower becoming idle. | 2022-07-21 | 2022-07-23 | Cutting bending was given in RBIPL's scope
13 | 2022-07-20 | Reinforcement of Part D Pier Cap was submitted on 08th July 2022 and Priority date was given 20th July 2022, reinforcement fabrication not started yet, work is getting delay, manpower becoming idle. | 2022-07-21 | 2022-07-23 | Cutting bending was given in RBIPL's scope
14 | 2022-07-25 | As per MOM, reinforcement fabrication of 100 Nos. of Pier Cap and 100 Nos. of Footing is in our scope but the raw steel of 20 mm dia and 12 mm dia straight bar is not availble with JSW agency, fabrication of reinforcement for a single structure is getting affected and work is getting delayed. | 2022-07-28 | 2022-07-29 | We have received 4 MT of 12 mm Steel on 29-7-22, 59 MT on 08-08-2022 and 7 MT on 12-8-2022. 21 MT of 20 mm steel was recived on 29-07-2022, 34 MT on 04-08-2022, 29 MT on 05-08-2022, 50 MT on 08-08-2022, 22 MT on 11-08-2022
15 | 2022-08-02 | Site Clearance of Part D ( Refactory bricks are not removed) and Part H (MS Pipes are not removed) is not available, excavation is getting delayed. | 2022-08-11 | 2022-08-20 | Part H Pipes are shifted but Part D refactory bricks are pending
16 | 2022-08-02 | In Part A, PC 69- PC 74 excavtion was started but removal of hard rock is pending as the concrete curb is to be removed by JSW (Scope of JSW) so that ramp can be made and movement of machinery is possible. |  |  | Pending
17 | 2022-08-01 | Site Clearance in Part H, Part D and Part A is not done, monthly target might be affected. | 2022-08-11 | 2022-08-20 | Part H Pipes are shifted but Part D refactory bricks are pending, Part A curb demolition is pending.
18 | 2022-08-18 | Full Length Reinforcement of 32 mm and 25 mm is not available with JSW, labour will get idle. | 2022-08-20 | 2022-08-24 | We have started receiving 25 mm and 32 mm dia steel from 24-08-2022, work has resumed again.
19 | 2022-08-21 | OPC Cement for M40 grade of Concrete not available. | 2022-08-24 | 2022-08-27 | Cement was made available on 27/08/2022, concreting was carried out on the same date.
20 | 2022-08-21 | We are unable to carry out the excavation in Part G (which is in priority) due to clearance from Horticulture and Utility Department | 2022-08-25 |  | Cleareance from Horticulture is given but Utility clearance is pending.
21 | 2022-08-25 | The coordinates in Part G, C, I, J,E where the footings are skewed (in the curved portion) are of only centre point. We are not able to carry-out excavation or any of the work in these area. Kindly provide AutoCAD drawing or revise the drawing with coordinates with corner point. | 2022-08-25 | 2022-08-31 | AutoCAD Drawings are received on 31-8-2022
22 | 2022-08-25 | Sectional Drawings are not available in Part G,C,I,J,E of Pier Cap, as they contain Trapezoidal Pier Cap also. And also, shuttering details for the same, as these shuttering fabrication is a time consuming activity. | 2022-08-25 |  | Part H sectional drawings are received, rest of the parts mention are still pending
23 | 2022-08-25 | Pre-cast Drawings of Part C, E, H, G, K is also required for the Priority area erection and casting activity
24 | 2022-08-25 | Reinforcement drawing are not revised Part-wise for Pier Cap except typical reinforcement drawing. We are starting the combined Pier Cap in Part-D, but the reinforcement drawing is not revised. The section drawing does not match the reinforcement drawing, so we are unable to proceed with the BBS of combined Pier Cap of Part D, as our erection plan starts in Part D. | 2022-08-25 | 2022-08-29 | We are informed to follow the reinforcement drawing for Part D, we have to refer Reinforcement drawing of Part F
25 | 2022-08-20 | Reinforcement of 25mm and 32mm dia is not available in Pre-cast yard as well as in Hot Metal Elevated Track site, work is getting delayed and manpower is becoming idle. | 2022-08-20 | 2022-08-24 | We have started receiving 25 mm and 32 mm dia steel from 24-08-2022, work has resumed again.
26 | 2022-10-03 | Concrete for Pre-cast not available due shortage of OPC cement in the bayching Plant | 2022-10-04 | 2022-10-06
27 | 2022-10-14 | Concrete was not issued from batching plant due breakdown of batching plant and cement was not available. | 2022-10-14 | 2022-10-15
27 | 2022-10-18 | Concrete was not issued from batching plant due to OPC cement was not available. | 2022-10-18 | 2022-10-19
28 | 2022-11-19 | Concrete was not issued from batching plant due to OPC cement was not available. Monthly target hampered | 2022-11-19 | 2022-11-21
29 | 2022-12-05 | Concrete was not issued from batching plant due to OPC cement was not available. Monthly target hampered | 2022-12-05 | 2022-12-13
30 | 2022-12-23 | Concrete was not issued from batching plant due to M-sand not available at batching plant. Monthly target hampered | 2022-12-23 | 2022-12-26
31 | 2022-12-28 | Concrete was not issued from batching plant due to OPC cement was not available. Monthly target hampered | 2022-12-28 | 2022-12-30
31 | 2022-12-30 | Concrete was not issued from batching plant due to M-sand not available at batching plant. Monthly target hampered | 2022-12-30 | 2023-12-31
32 | 2023-01-06 | Due to Poor Quality of concrete from JSW batching plant, concreting was not done. | 2023-01-06 | 2023-01-08
33 | 2023-01-10 | 10 mm aggregate is not available at JSW batching plant, concreting was not done. | 2023-01-10 | 2023-01-12
34 | 2023-01-12 | Concrete was not issued from batching plant due to OPC cement was not available. Monthly target hampered | 2023-01-12 | 2023-01-12
35 | 2023-01-13 | Concrete was not issued from batching plant due to shortage of admixture was not available. Monthly target hampered | 2023-01-13
36 | 2023-01-21 | Concrete was not issued from batching plant due to OPC cement was not available. Other batching plant was under maintainance | 2023-01-21 | 2023-01-23
37 | 2023-01-28 | 12 mm and 20 mm aggregate not available at JSW batching Plant. | 2023-01-28 | 2023-02-01
38 | 2023-02-14 | Due to Poor Quality of concrete from JSW batching plant, concreting was hampered | 2023-02-18 | 2023-02-20
39 | 2023-02-20 | 12 mm aggregate not available at JSW batching Plant. | 2023-02-20 | 2023-02-22
40 | 2023-05-12 | Due to Ban on Mobile, 60 Labour are absent | 2023-05-12
41 | 2023-05-29 | Reinforcement of 10 mm and 20 mm not availble for lifting. | 2023-05-29 | 2023-06-10
42 | 2023-06-01 | OPC Cement for M40 grade of Concrete not available for Pre-cast | 2023-06-03 | 2023-06-07
43 | 2023-06-07 | JSW batching Plant under breakdown, alternate option not available | 2023-06-08 | 2023-06-08
44 | 2023-06-17 | 12 mm aggregate not available at JSW Pre-cast batching Plant. | 2023-06-18 | 2023-06-18
45 | 2023-06-24 | Reinforcement of 25 mm and 32 mm not availble for lifting. | 2023-06-25 | 2023-07-10 | 25 mm reinforcement released on 26/06/2023, 32 mm reinforcement released on 10/07/2023
46 | 2023-07-14 | M-sand not available at JSW batching Plant, Pre-cast work hampered. | 2023-07-14 | 2023-07-14
47 | 2023-07-20 | Reinforcement of 32 mm lifting is not possible due Credits blocked by JVML | 2023-07-23 | 2023-07-24
48 | 2023-08-24 | Poor Quality of Concrete from JSW batching plant for Pre-cast Girders, work has been hampered. | 2023-08-26 | 2023-08-28
49 | 2023-08-28 | TMT bar of 12 mm, 20 mm and 32 mm not available at JSW lifting point. | 2023-09-06 | 2023-09-15 | 20 mm and 32 mm received partially
50 | 2023-09-16 | BBS Given to BRM-1 is pending from more than a month | 2023-09-20 | 2023-09-20 | BRM-1 has given regret for BBS
51 | 2023-10-07 | OPC and PSC cement not available at JSW batching Plant | 2023-10-11 | 2023-10-12
52 | 2023-10-07 | Unable to lift the raw reinforcement due budget issues in JSW, HMET PO | 2023-10-12 | 2023-10-14
53 | 2023-11-30 | BBS Given to BRM-1 is pending from more than 25 days, work is been delayed | 2023-12-02 | 2023-12-11

## Constraints (hidden)
# | Concerns | Status | Remarks as on 18-Apr-22 | Responsibility | Time Frame | Status
A | Formation work hindrances
1 | Rerouting of underground pipe line at entrance of BF 4 | Under Progress | Budget issued to utility department. | Mr. Veershekhar | 2022-09-01 | Work under progress
2 | Shifting of safety office | Under Progress | New office under constructions | Mr. Raj Kiran | 2022-12-01 | Expected for relocat by March 23.
3 | BF5 area -from Tarpedo maintenmabve bay to Part D. | Not started | Informed to concerns persons for area clearance . | Mr. Prasad | 2022-10-01 | For formation,work required to remove the unloaded equipments and materials and also required to level the area to start the formation work.
B | Elevated track hindrances
1 | Cable gallery at 3 location | Under Progress | Scheme & Estimation prepared. Budget proposed 31 Crs. | Mr. Gururaj Guptha | to be worked out
2 | Drawing from M/s Mecon to be expedite | Under Progress | 546 footing drawing received / 546 | Mecon | 2022-09-01 | Closed in April 2023
3 | Bulk Receiption Unit (BRU) | Under Progress | 22 footings under Hold | JSW |  | Closed on 28th August 2023
4 | Structural Material to be lifted in Part K | Under Progress | 33 footings under Hold | JSW |  | Closed on 19th August 2023. 12 Footings to be cleared.
5 | Reinforcement details and liftiing arrangement for Trapezoidal pre-cast segment not available. | Under Progress | 683 No. of Precast segments cannot be casted due to non-availability of details | MECON |  | Closed on 20th July 2023.

## Drawing Register (hidden)
Drawing Register
Sr. No. | Drg. No. | Description | Type | Planned released of drawing | Drawing Receipt & Revision Date
[5 empty] | R0 |  |  | R1 |  |  | R2 |  |  | R3 |  |  | R4 |  |  | R5 |  |  | R6
|  |  | Civil / Struct. |  | Mail Copy Date | Hard Copy Date | Remarks | Mail Copy Date | Hard Copy Date | Remarks | Mail Copy Date | Hard Copy Date | Remarks | Mail Copy Date | Hard Copy Date | Remarks | Mail Copy Date | Hard Copy Date | Remarks | Mail Copy Date | Hard Copy Date | Remarks | Mail Copy Date | Hard Copy Date | Remarks
ELEVATED HOT METAL TRACK
PART A
1 | Q7GS-4101 R-1-1 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22
2 | Q7GS-4102 R-6 |  | CIVIL |  |  |  | R-0 Not Received |  |  | R-1 Not Received | 2022-02-22 |  |  |  |  | Not Received |  |  | Not Received |  |  | Not Received | 2023-02-19
3 | Q7GS-4103 R-4 |  | CIVIL |  |  |  | R-0 Not Received |  |  | R-1 Not Received | 2022-02-22 | [5 empty] | 2023-02-19
4 | Q7GS-4104 R-3 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 | [5 empty] | 2023-02-19
5 | Q7GS-4105 R-3 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 | [5 empty] | 2023-02-19
6 | Q7GS-4106 R-3 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 | [5 empty] | 2023-02-19
7 | Q7GS-4107 R-2 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22
8 | Q7GS-4108 R-6 |  | CIVIL |  |  |  | R-0 Not Received |  |  | R-1 Not Received | 2022-02-22 |  |  | 2022-06-30 |  |  | 2022-07-20 |  | Not Received |  |  | Not Received | 2023-02-19
9 | Q7GS-4109 R-6 |  | CIVIL |  |  |  | R-0 Not Received |  |  | R-1 Not Received | 2022-02-22 |  |  |  |  | Not received | 2022-06-26 |  |  |  |  | Not Received | 2023-02-19
10 | Q7GS-4110 R-4 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 | [8 empty] | 2023-02-19
11 | Q7GS-4111 R-2 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 |  |  | 2023-02-19
12 | Q7GS-4112 R-2 |  | CIVIL |  | 2022-02-22 | [5 empty] | 2022-10-01
13 | Q7GS-4113 R-3 |  | CIVIL |  | 2022-03-11 |  |  | 2022-05-25 |  |  | 2022-07-13 |  |  | 2022-07-22
14 | Q7GS-4270 (Sh 1of 3) R-1 | Abutment | CIVIL |  | 2023-04-19 |  |  | 2023-07-12
15 | Q7GS-4270 (Sh 2of 3) R-1 | Abutment | CIVIL |  | 2023-04-19 |  |  | 2023-07-12
16 | Q7GS-4270 (Sh 3of 3) R-1 | Abutment | CIVIL |  | 2023-04-19 |  |  | 2023-07-12
17 | Q7LZ-4556 (Sh 1of 3) R-0 | Abutment | CIVIL |  | 2023-10-04
18 | Q7LZ-4556 (Sh 2of 3) R-0 | Abutment | CIVIL |  | 2023-10-04
19 | Q7LZ-4556 (Sh 3of 3) R-0 | Abutment | CIVIL |  | 2023-10-04
20 | Q7LZ-4570 R-0 | Abutment | CIVIL |  | 2023-11-10
PART B
1 | Q7GS-4114 R-2 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 |  |  | 2022-10-18
2 | Q7GS-4115 R-2 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 |  |  | 2022-10-18
3 | Q7GS-4116 (Sh 1 of 2) R-4 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 |  |  | 2022-05-14 | [5 empty] | 2022-10-18
4 | Q7GS-4116 (Sh 2 of 2) R-0 |  | CIVIL |  | 2022-10-18
5 | Q7GS-4117 R-4 |  | CIVIL |  |  |  | R-0 Not Received | 2022-02-22 |  |  | 2022-05-14 | [5 empty] | 2022-10-18
6 | Q7GS-4118 R-0 |  | CIVIL |  | 2022-05-14
7 | Q7GS-4119 R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-05-14
8 | Q7GS-4120 R-3 |  | CIVIL |  | 2022-02-22 |  |  | 2022-05-14 |  |  | 2022-07-13 |  |  | 2022-10-18
9 | Q7GS-4121 R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-13
10 | Q7GS-4122 R-4 |  | CIVIL |  | 2022-02-22 |  |  |  |  | Not Received | 2022-05-14 |  |  | 2022-07-13 |  |  | 2023-02-19
PART C and G
1 | Q7GS-4229 R-0
2 | Q7GS-4230 R-3 |  | CIVIL |  | 2022-08-10 |  |  | 2022-12-15 | [5 empty] | 2022-12-31
3 | Q7GS-4231 R-5 |  | CIVIL |  | 2022-08-10 |  |  | 2022-11-12 |  |  | 2022-12-15 |  |  | 2023-02-02 |  |  | 2023-03-28 |  |  | 2023-05-04
4 | Q7GS-4232 R-0 |  | CIVIL |  | 2022-08-10
5 | Q7GS-4233 (Sh 1 of 4) R-2 |  | CIVIL |  | 2022-08-10 |  |  | 2023-03-28 |  |  | 2023-05-04
6 | Q7GS-4233 (Sh 2 of 4) R-3 |  | CIVIL |  | 2022-08-10 |  |  | 2022-12-15 |  |  | 2022-12-31 |  |  | 2023-03-28
7 | Q7GS-4233 (Sh 3 of 4) R-3 |  | CIVIL |  | 2022-08-10 |  |  | 2022-12-15 |  |  | 2022-12-31 |  |  | 2023-03-28
8 | Q7GS-4233 (Sh 3 of 4) R-1 |  | CIVIL |  | 2022-08-10 |  |  | 2023-03-28
9 | Q7GS-4234 R-2 |  | CIVIL |  | 2023-01-20 |  |  | Not received |  |  | 2023-05-30
10 | Q7GS-4235 R-0 |  | CIVIL |  | 2023-01-20
11 | Q7GS-4236 R-0 |  | CIVIL |  | 2023-01-20
12 | Q7GS-4237 R-0 |  | CIVIL |  | 2023-01-20
13 | Q7GS-4238 R-1 |  | CIVIL |  | 2023-01-20 |  |  | 2023-06-23
14 | Q7GS-4239 R-0 |  | CIVIL |  | 2023-01-20
15 | Q7GS-4240 R-3 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23 |  |  | 2023-07-08 |  |  | 2023-07-11
16 | Q7GS-4241 R-2 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23 |  |  | 2023-07-11
17 | Q7GS-4242 R-4 |  | CIVIL |  | 2022-09-30 |  |  | 2023-01-20 |  |  | 2023-06-23 |  |  | 2023-07-08 |  |  | 2023-07-11
18 | Q7GS-4243 R-1 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23
19 | Q7GS-4244 R-1 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23
20 | Q7GS-4245 R-2 |  | CIVIL |  | 2022-09-30 |  |  | 2023-01-20 |  |  | 2023-06-23
21 | Q7GS-4246 R-1 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23
22 | Q7GS-4247 R-2 |  | CIVIL |  | 2022-09-30 |  |  | 2023-01-20 |  |  | 2023-06-23
23 | Q7GS-4248 R-1 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23
24 | Q7GS-4249 (Sh 1 of 2) R-0 |  | CIVIL |  | 2022-09-30
25 | Q7GS-4249 (Sh 2 of 2) R-0 |  | CIVIL |  | 2022-09-30
26 | Q7GS-4250 (Sh 1 of 2) R-3 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23 |  |  | 2023-07-08 |  |  | 2023-07-11
27 | Q7GS-4250 (Sh 2 of 2) R-3 |  | CIVIL |  | 2022-09-30 |  |  | 2023-06-23 |  |  | 2023-07-08 |  |  | 2023-07-11
28 | Q7GS-4251 R-2 |  | CIVIL |  | 2023-01-20 |  |  | 2023-05-30 |  |  | 2023-06-23
29 | Q7GS-4252 R-0 |  | CIVIL |  | 2022-12-31
30 | Q7GS-4253 R-0 |  | CIVIL |  | 2022-12-31
31 | Q7GS-4254 R-0 |  | CIVIL |  | 2022-12-31
32 | Q7GS-4255 R-0 |  | CIVIL |  | 2022-12-31
33 | Q7GS-4256 R-0 |  | CIVIL |  | 2022-12-31
34 | Q7GS-4257 R-0 |  | CIVIL |  | 2022-12-31
35 | Q7GS-4258 R-0 |  | CIVIL |  | 2022-12-31
36 | Q7GS-4260 R-0 |  | CIVIL |  | 2022-12-31
37 | Q7GS-4261 R-0 |  | CIVIL |  | 2022-12-31
38 | Q7GS-4262 (Sh 1 of 2) R-0 |  | CIVIL |  | 2022-12-31
39 | Q7GS-4262 (Sh 2 of 2) R-0 |  | CIVIL |  | 2022-12-31
40 | Q7GS-4263 R-2 |  | CIVIL |  | 2022-12-31 |  |  | Not Received |  |  | 2023-07-08
41 | Q7GS-4264 R-0 |  | CIVIL |  | 2022-12-31
42 | Q7GS-4265 R-0 |  | CIVIL |  | 2022-12-31
43 | Q7GS-4266 R-0 |  | CIVIL |  | 2022-12-31
44 | Q7GS-4267 (Sh 1 of 3) R-0 |  | CIVIL |  | 2023-04-12
45 | Q7GS-4267 (Sh 2 of 3) R-0 |  | CIVIL |  | 2023-04-12
46 | Q7GS-4267 (Sh 3 of 3) R-0 |  | CIVIL |  | 2023-04-12
47 | Q7GS-4268 (Sh 1 of 2) R-0 |  | CIVIL |  | 2023-04-12
48 | Q7GS-4268 (Sh 2 of 2) R-0 |  | CIVIL |  | 2023-04-12
49 | Q7GS-4269 (Sh 1 of 5) R-0 |  | CIVIL |  | 2023-05-30
50 | Q7GS-4269 (Sh 2 of 5) R-0 |  | CIVIL |  | 2023-05-30
51 | Q7GS-4269 (Sh 3 of 5) R-0 |  | CIVIL |  | 2023-05-30
52 | Q7GS-4269 (Sh 4 of 5) R-0 |  | CIVIL |  | 2023-05-30
53 | Q7GS-4269 (Sh 5 of 5) R-0 |  | CIVIL |  | 2023-05-30
54 | QlZ-4227 (Sh 1 of 4) R-2 | Revised Footings | CIVIL |  | 2023-06-29 | [5 empty] | 2023-09-21
55 | QlZ-4227 (Sh 2 of 4) R-1 | Revised Footings | CIVIL |  | 2023-08-07 | [5 empty] | 2023-09-21
56 | QlZ-4227 (Sh 3 of 4) R-0 | Revised Footings | CIVIL |  | 2023-08-07
57 | QlZ-4227 (Sh 4 of 4) R-0 | Revised Footings | CIVIL |  | 2023-08-07
58 | Q7lZ-4540 (Sh 1 of2) R-0 | PCC- 18, 19 Reinforcement | CIVIL |  | 2023-07-22
59 | Q7lZ-4540 (Sh 2 of2) R-0 | PCC- 18, 19 Reinforcement | CIVIL |  | 2023-07-22
60 | Q7lZ-4541 R-0 | Revised Slab Drawing | CIVIL |  | 2023-11-04
61 | Q7lZ-4542 R-0 | Revised Slab Drawing | CIVIL |  | 2023-11-04
62 | Q7lZ-4543 R-0 (Sh 1of 2) | Revised Slab Drawing | CIVIL |  | 2023-11-04
63 | Q7lZ-4544 R-0 (Sh 1of 2) | Revised Slab Drawing | CIVIL |  | 2023-11-04
64 | Q7lZ-4523 R-1 | Revised Slab Drawing | CIVIL |  | - |  |  | 2023-09-26
65 | Q7lZ-4522 R-0 | Revised Slab Reinforcement | CIVIL |  | 2023-11-10
66 | Q7lZ-4563 (Sh 1 of 2) - R-1 | Weigh Bridge | CIVIL |  | 2023-11-04 |  |  | 2023-12-09
67 | Q7lZ-4563 (Sh 2 of 2) - R-0 | Weigh Bridge | CIVIL |  | 2023-11-04
68 | Q7lZ-4564 (Sh 1 of 4) - R-0 | Weigh Bridge | CIVIL |  | 2023-12-09
69 | Q7lZ-4564 (Sh 2 of 4) - R-0 | Weigh Bridge | CIVIL |  | 2023-12-09
70 | Q7lZ-4564 (Sh 3 of 4) - R-0 | Weigh Bridge | CIVIL |  | 2023-12-09
71 | Q7lZ-4564 (Sh 4 of 4) - R-0 | Weigh Bridge | CIVIL |  | 2023-12-09
72 | Q7lZ-4545 (Sh 1 of 4) - R-0 | Revised Slab Drawing | CIVIL |  | 2023-12-08
73 | Q7lZ-4545 (Sh 2 of 4) - R-0 | Revised Slab Drawing | CIVIL |  | 2023-12-08
74 | Q7lZ-4545 (Sh 3 of 4) - R-0 | Revised Slab Drawing | CIVIL |  | 2023-12-08
75 | Q7lZ-4545 (Sh 4 of 4) - R-0 | Revised Slab Drawing | CIVIL |  | 2023-12-08
76 | Q7lZ-4546 - R-0 | Revised Slab Drawing | CIVIL |  | 2023-12-08
77 | Q7lZ-Foundation R-0 | Revised Footings | CIVIL |  | 2023-12-08
PART D
1 | Q7GS-4123 R-2 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-02 |  |  | 2022-11-18
2 | Q7GS-4124 R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-11-18
3 | Q7GS-4125 R-3 |  | CIVIL |  | 2022-02-22 |  |  | Not received |  |  | 2022-07-02 |  |  | 2022-11-18
4 | Q7GS-4126 R-3 |  | CIVIL |  | 2022-02-22 |  |  | Not received |  |  | 2022-07-02 |  |  | 2022-11-18
5 | Q7GS-4127 R-4 |  | CIVIL |  | 2022-02-22 |  |  | Not received |  |  | Not received |  |  | 2022-07-02 |  |  | 2022-11-18
6 | Q7GS-4128 (SH-1)R-3 |  | CIVIL |  | 2022-02-22 |  |  | 2022-06-28 |  |  | 2022-11-18 |  |  | 2023-01-20
7 | Q7GS-4128 (SH-2)R-0 |  | CIVIL |  | 2023-01-20
8 | Q7GS-4128 (SH-3)R-0 |  | CIVIL |  | 2023-01-20
9 | Q7GS-4129 R-2 |  | CIVIL |  | 2022-02-22 |  |  | Not received |  |  | 2022-11-18
10 | Q7GS-4130 R-0 |  | CIVIL |  | 2022-02-22
11 | Q7GS-4131 R-0 |  | CIVIL |  | 2022-02-22
12 | Q7GS-4132 R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-01
13 | Q7GS-4133 R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-11-18
14 | Q7GS-4134 R-2 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-02 |  |  | 2023-02-19
15 | Q7GS-4135 (SH.-1) R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-10-18
16 | Q7GS-4135 (SH.-2) R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-10-18
17 | Q7GS-4135 (SH.-3) R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-10-18
18 | Q7GS-4271 R-1 | Superceeded Abutment | CIVIL |  | Not received |  |  | 2023-03-18
19 | Q7GS-4272 R-1 | Superceeded Abutment | CIVIL |  | Not received |  |  | 2023-03-18
20 | Q7GS-4273 R-1 | Superceeded Abutment | CIVIL |  | Not received |  |  | 2023-03-18
21 | Q7GS-4274 R-0 | Superceeded Abutment | CIVIL |  | Not received |  |  | 2023-03-18
22 | Q7LZ-4228 (Sh 1 of 4) R-0 | Abutment | CIVIL |  | 2023-07-03
23 | Q7LZ-4228 (Sh 2 of 4) R-0 | Abutment | CIVIL |  | 2023-07-03
24 | Q7LZ-4228 (Sh 3 of 4) R-0 | Abutment | CIVIL |  | 2023-07-03
25 | Q7LZ-4228 (Sh 4 of 4) R-0 | Abutment | CIVIL |  | 2023-07-03
26 | Q7LZ-4228 (Sh 5of 5) R-0 | Abutment | CIVIL |  | 2023-10-07
PART E
1 | Q7GS-4173 R-3 |  | CIVIL |  | not received |  |  | 2022-07-13 |  |  | 2023-11-12 |  |  | 2023-03-28
2 | Q7GS-4174 R-4 |  | CIVIL |  | not received |  |  | 2022-07-13 |  |  | Not Received |  |  | 2023-11-12 |  |  | 2023-03-28
3 | Q7GS-4175 R-0 |  | CIVIL |  | 2022-10-01
4 | Q7GS-4176 R-0 |  | CIVIL |  | 2022-10-01
5 | Q7GS-4177 R-1 |  | CIVIL |  | 2022-10-01 |  |  | 2023-02-19
6 | Q7GS-4178 R-1 |  | CIVIL |  | not received |  |  | 2022-06-28
7 | Q7GS-4179 R-0 |  | CIVIL |  | 2022-09-29
8 | Q7GS-4180 R-0 |  | CIVIL |  | 2022-09-29
9 | Q7GS-4181 (SH-1) R-1 |  | CIVIL |  | 2022-09-29 |  |  | 2023-03-28
9 | Q7GS-4181 (SH-2) R-0 |  | CIVIL |  | 2023-03-28
10 | Q7GS-4182 R-0 |  | CIVIL |  | 2022-09-29
11 | Q7GS-4183 R-0 |  | CIVIL |  | 2022-09-29
12 | Q7GS-4184 R-0 |  | CIVIL |  | 2022-09-29
13 | Q7GS-4185 R-0 |  | CIVIL |  | 2022-09-29
14 | Q7GS-4186 R-0 |  | CIVIL |  | 2022-09-29
15 | Q7GS-4187 (Sh 1 of 5) R-0 |  | CIVIL |  | 2022-10-01
16 | Q7GS-4187 (Sh 2 of 5) R-0 |  | CIVIL |  | 2022-10-01
17 | Q7GS-4187 (Sh 3 of 5) R-0 |  | CIVIL |  | 2022-10-01
18 | Q7GS-4187 (Sh 4 of 5) R-0 |  | CIVIL |  | 2022-10-01
19 | Q7GS-4187 (Sh 5 of 5) R-0 |  | CIVIL |  | 2022-10-18
PART F
1 | Q7GS-4136 R-2 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-02 |  |  | 2022-09-11
2 | Q7GS-4137 R-2 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-13 |  |  | 2022-09-11
3 | Q7GS-4138 R-2 |  | CIVIL |  | 2022-02-22 |  |  | 2022-06-28 |  |  | 2022-09-11
4 | Q7GS-4139 R-1 |  | CIVIL |  | 2022-02-22 |  |  | 2022-07-13
5 | Q7GS-4140 R-0 |  | CIVIL |  | 2022-02-22
6 | Q7GS-4141 R-0 |  | CIVIL |  | 2022-02-22
7 | Q7GS-4142 R-1 |  | CIVIL |  | 2022-04-20 |  |  | 2022-10-18
8 | Q7GS-4143 R-1 |  | CIVIL |  | 2022-04-20 |  |  | 2022-10-18
9 | Q7GS-4144 R-1 |  | CIVIL |  | 2022-04-20 |  |  | 2022-10-18
10 | Q7GS-4145 R-1 |  | CIVIL |  | 2022-04-20 |  |  | 2022-07-02
11 | Q7GS-4146 R-1 |  | CIVIL |  | 2022-04-20 |  |  | 2022-07-02
PART G
PART H
1 | Q7GS- 4216 R-1 |  | CIVIL |  | 2022-07-21 |  |  | 2022-07-28
2 | Q7GS- 4217 (sh 1 of 2) R-2 |  | CIVIL |  | 2022-07-28 |  |  | Not received |  |  | 2022-12-15
3 | Q7GS- 4217 (sh 2 of 2) R-0 |  | CIVIL |  | 2022-07-28
4 | Q7GS- 4218 R-3 |  | CIVIL |  | 2022-08-31 |  |  | 2022-09-30 |  |  | 2022-10-18 |  |  | 2023-01-20
5 | Q7GS- 4219 R-2 |  | CIVIL |  | 2022-08-31 |  |  | 2022-10-18 |  |  | 2023-01-20
6 | Q7GS- 4220 R-2 |  | CIVIL |  | 2022-08-31 |  |  | 2022-10-18 |  |  | 2023-01-20
7 | Q7GS- 4221 (sh 1 of 3) R-3 |  | CIVIL |  | 2022-08-31 |  |  | 2022-09-30 | [5 empty] | 2022-10-20
8 | Q7GS- 4221 (sh 2 of 3) R-2 |  | CIVIL |  | 2022-08-31 |  |  | 2022-09-30 |  |  | 2022-10-18
9 | Q7GS- 4221 (sh 3 of 3) R-2 |  | CIVIL |  | 2022-08-31 |  |  | 2022-09-30 |  |  | 2022-10-18
10 | Q7GS- 4222 (sh 1 of 2) R-0 |  | CIVIL |  | 2022-10-20
11 | Q7GS- 4222 (sh 2 of 2) R-0 |  | CIVIL |  | 2022-10-20
12 | Q7GS- 4223 (sh 1 of 2) R-0 |  | CIVIL |  | 2022-10-20
13 | Q7GS- 4223 (sh 2 of 2) R-0 |  | CIVIL |  | 2022-10-20
14 | Q7GS- 4224 (sh 1 of 3) R-0 |  | CIVIL |  | 2023-02-19
15 | Q7GS- 4224 (sh 2 of 3) R-0 |  | CIVIL |  | 2023-02-19
16 | Q7GS- 4224 (sh 3 of 3) R-0 |  | CIVIL |  | 2023-02-19
17 | Q7GS- 4225 (sh 1 of 6) R-0 |  | CIVIL |  | 2022-11-04
18 | Q7GS- 4225 (sh 2 of 6) R-0 |  | CIVIL |  | 2022-11-04
19 | Q7GS- 4225 (sh 3 of 6) R-0 |  | CIVIL |  | 2022-11-04
20 | Q7GS- 4225 (sh 4 of 6) R-0 |  | CIVIL |  | 2022-11-04
21 | Q7GS- 4225 (sh 5 of 6) R-0 |  | CIVIL |  | 2022-11-04
22 | Q7GS- 4225 (sh 6 of 6) R-0 |  | CIVIL |  | 2022-11-04
PART I
1 | Q7GS-4147 R-1 |  | CIVIL |  | 2022-04-26 |  |  | 2023-11-12
2 | Q7GS-4148 R-0 |  | CIVIL |  | 2022-04-26
3 | Q7GS-4149 R-2 |  | CIVIL |  | 2022-04-26 |  |  | 2023-09-21 |  |  | 2023-04-01
4 | Q7GS-4150 R-0 |  | CIVIL |  | 2022-04-26
5 | Q7GS-4151 R-1 |  | CIVIL |  | 2022-04-26 |  |  | 2022-06-28
6 | Q7GS-4152 R-1 |  | CIVIL |  | 2022-06-04 |  |  | 2023-09-21
7 | Q7GS-4153 R-1 |  | CIVIL |  | 2022-06-04 |  |  | 2023-09-21
8 | Q7GS-4154 R-0 |  | CIVIL |  | 2022-06-04
9 | Q7GS-4155 R-0 |  | CIVIL |  | 2022-06-04
10 | Q7GS-4156 R-0 |  | CIVIL |  | 2022-06-04
11 | Q7GS-4158 (Sheet 1 of 4) R-2 |  | CIVIL |  | 2022-07-25 |  |  | 2023-01-20 |  |  | 2023-04-01
12 | Q7GS-4158 (Sheet 2 of 4) R-1 |  | CIVIL |  | 2022-07-25 |  |  | 2023-04-01
13 | Q7GS-4158 (Sheet 3 of 4) R-1 |  | CIVIL |  | 2022-07-25 |  |  | 2023-04-01
14 | Q7GS-4158 (Sheet 4 of 4) R-1 |  | CIVIL |  | 2022-07-25 |  |  | 2023-04-01
15 | Q7GS-4159 (Sheet 1 of 2) R-0 |  | CIVIL |  | 2023-09-17
16 | Q7GS-4159 (Sheet 2 of 2) R-0 |  | CIVIL |  | 2023-09-17
17 | Q7GS-4160 R-0 |  | CIVIL |  | 2023-09-17
18 | Q7GS-4161 R-0 |  | CIVIL |  | 2023-09-17
PART J
1 | Q7GS-4162 R-1 |  | CIVIL |  | 2022-04-27 |  |  | 2022-11-22
2 | Q7GS-4163 R-1 |  | CIVIL |  | 2022-04-27 |  |  | 2023-01-20
3 | Q7GS-4164 R-0 |  | CIVIL |  | 2022-04-27
4 | Q7GS-4165 (SH-1) R-4 |  | CIVIL |  | 2022-04-27 |  |  | 2022-07-02 |  |  |  |  | Not Received | 2023-02-19 |  |  | 2023-10-06
5 | Q7GS-4165 (SH-2) R-0 |  | CIVIL |  | 2023-01-20
6 | Q7GS-4165 (SH-3) R-0 |  | CIVIL |  | 2023-01-20
7 | Q7GS-4166 R-3 |  | CIVIL |  | 2022-04-27 |  |  | 2022-07-02 |  |  | 2023-01-20 |  |  | 2023-10-06
8 | Q7GS-4167 R-1 |  | CIVIL |  | 2022-05-25 |  |  | 2022-08-01
9 | Q7GS-4168 R1 |  | CIVIL |  | 2022-05-25 |  |  | 2023-01-20
10 | Q7GS-4169, R1 |  | CIVIL |  | 2022-05-25 |  |  | 2023-01-20
11 | Q7GS-4170 R1 |  | CIVIL |  | 2022-05-25 |  |  | 2023-01-20
12 | Q7GS-4171 (Sheet 1 of 5) R-1 |  | CIVIL |  | 2022-08-12 |  |  | 2023-01-20
13 | Q7GS-4171 (Sheet 2 of 5) R-0 |  | CIVIL |  | 2022-08-12
14 | Q7GS-4171 (Sheet 3 of 5) R-0 |  | CIVIL |  | 2022-08-12
15 | Q7GS-4171 (Sheet 4 of 5) R-0 |  | CIVIL |  | 2022-08-12
16 | Q7GS-4171 (Sheet 5 of 5) R-1 |  | CIVIL |  | 2022-08-12 |  |  | 2023-01-20
17 | Q7GS-4172 (Sheet 1 of 4) R-0 |  | CIVIL |  | 2022-08-20
18 | Q7GS-4172 (Sheet 2 of 4) R-0 |  | CIVIL |  | 2022-08-20
19 | Q7GS-4172 (Sheet 3 of 4) R-0 |  | CIVIL |  | 2022-08-20
20 | Q7GS-4172 (Sheet 4 of 4) R-0 |  | CIVIL |  | 2022-08-20
21 | Q7LZ-4172 (Sheet 5 of 6) R-0 |  | CIVIL |  | 2023-07-18
22 | Q7LZ-4172 (Sheet 6 of 6) R-0 |  | CIVIL |  | 2023-07-18
PART K
1 | Q7GS-4188 R-0 | Excavation Drawing (Superceeded) | CIVIL |  | 2022-07-16
2 | Q7GS-4189 R-2 |  | CIVIL |  | 2022-08-06 |  |  | 2022-09-11 |  |  | 2023-03-24
3 | Q7GS-4190 R-1 |  | CIVIL |  | 2022-08-06 |  |  | 2022-09-11
4 | Q7GS-4191 R-1 |  | CIVIL |  | 2022-08-06 |  |  | 2022-09-11
5 | Q7GS-4192 R-2 |  | CIVIL |  | 2022-08-06 |  |  | 2022-09-11 |  |  | 2023-03-24
6 | Q7GS-4193 R-1 |  | CIVIL |  | 2022-08-27 |  |  | 2023-03-24
7 | Q7GS-4194 R-1 |  | CIVIL |  | 2022-08-27 |  |  | 2023-03-24
8 | Q7GS-4195 R-0 |  | CIVIL |  | 2022-08-27
9 | Q7GS-4196 R-4 |  | CIVIL |  | 2022-09-11 |  |  | 2023-03-24 |  |  | 2023-12-09 |  | Not Received | 2023-10-06 |  |  | 2023-11-29
10 | Q7GS-4197 R-1 |  | CIVIL |  | 2022-09-11 |  |  | 2023-12-09
11 | Q7GS-4198 (Sheet 1 of 3) R-3 |  | CIVIL |  | 2022-09-11 |  |  | 2023-03-24 |  |  |  |  | Not Received | 2023-10-06
12 | Q7GS-4198 (Sheet 2 of 3) R-2 |  | CIVIL |  | 2022-09-11 |  |  | 2023-12-09 |  |  | 2023-11-29
13 | Q7GS-4198 (Sheet 3 of 3) R-2 |  | CIVIL |  | 2022-09-11 |  |  | 2023-12-09 |  |  | 2023-11-29
14 | Q7GS-4199 R-1 |  | CIVIL |  | 2022-09-11 |  |  | 2023-12-09
15 | Q7GS-4200 (SH 1) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
16 | Q7GS-4200 (SH 2) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
17 | Q7GS-4200 (SH 3) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
18 | Q7GS-4200 (SH 4) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
19 | Q7GS-4200 (SH 5) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
20 | Q7GS-4200 (SH 6) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
21 | Q7GS-4200 (SH 7) R-1 |  | CIVIL |  | Not Received |  | Not Received | 2023-02-19
22 | Q7GS-4201 (Sheet 1 of 3) R-0 |  | CIVIL |  | 2022-11-22
23 | Q7GS-4201 (Sheet 2 of 3) R-0 |  | CIVIL |  | 2022-11-22
24 | Q7GS-4201 (Sheet 3 of 3) R-0 |  | CIVIL |  | 2022-11-22
25 | Q7GS-4202 (Sheet 1 of 4) R-0 |  | CIVIL |  | 2022-11-05
26 | Q7GS-4202 (Sheet 2 of 4) R-0 |  | CIVIL |  | 2022-11-05
27 | Q7GS-4202 (Sheet 3 of 4) R-0 |  | CIVIL |  | 2022-11-05
28 | Q7GS-4202 (Sheet 4 of 4) R-0 |  | CIVIL |  | 2022-11-05
29 | Q7LZ- 4510 R-0 |  | CIVIL |  | 2023-12-09
30 | Q7LZ- 4511 R-0 |  | CIVIL |  | 2023-12-09
31 | Q7LZ- 4512 R-0 |  | CIVIL |  | 2023-12-09
32 | Q7LZ- 4513 R-0 |  | CIVIL |  | 2023-12-09
33 | Q7LZ- 4514 R-0 |  | CIVIL |  | 2023-12-09
34 | Q7LZ- 4515 R-0 |  | CIVIL |  | 2023-12-09
35 | Q7LZ- 4516 R-0 |  | CIVIL |  | 2023-12-09
36 | Q7LZ- 4517 R-0 |  | CIVIL |  | 2023-12-09
37 | Q7LZ- 4525 R-0 |  | CIVIL |  | 2023-07-22
38 | Q7LZ- 4526 R-0 |  | CIVIL |  | 2023-07-22
39 | Q7LZ- 4527 R-0 |  | CIVIL |  | 2023-07-22
40 | Q7LZ- 4528 R-0 |  | CIVIL |  | 2023-07-22
41 | Q7LZ- 4529 R-0 |  | CIVIL |  | 2023-07-22
42 | Q7LZ- 4530 R-0 |  | CIVIL |  | 2023-07-22
43 | Q7LZ- 4531 R-0 |  | CIVIL |  | 2023-07-22
44 | Q7LZ- 4532 R-0 |  | CIVIL |  | 2023-07-22
45 | Q7LZ- 4533 R-0 |  | CIVIL |  | 2023-07-22
46 | Q7LZ- 4534 R-0 |  | CIVIL |  | 2023-07-22
47 | Q7LZ- 4535 R-0 |  | CIVIL |  | 2023-07-22

## Info Register (hidden)
Date | Descprition | Remark | Photos
2022-05-18 | Work Stopped due to heavy rain
2022-05-20 | Work hampered due to rain.
2022-05-25 | JSW Plant Broke down | received only 12 cum
2022-06-02 | No concrete done due to HEAVY RAIN.
2022-06-13 | No concrete received from JSW Batching Plant | due to mass concretiing of Ray And LNT
2022-10-03 | Concrete for Pre-cast not available due shortage of OPC cement in the bayching Plant
2022-10-12 | Work was Hampered due to heavy rain, concrete was not available at batching plant
2022-10-14 | Concrete was not issued from batching plant due breakdown of batching plant and cement was not available.
2022-10-18 | Concrete for Pre-cast not available due shortage of OPC cement in the bayching Plant
2022-11-12 | Concrete delayed due other agency mass concrete. Pre-cast concrete hampered
2022-11-16 | 20 mm aggregate was not available at the batching plant, work was hampered
2022-11-19 | Concrete for Pre-cast not available due shortage of OPC cement in the batching Plant, 7 Girders ready.
2022-12-05 | Concrete for Pre-cast not available due shortage of OPC cement in the batching Plant, 7 Girders ready.
2022-12-12 | Work hampered due to rain. (Mandose- Cyclone effect) from 10-Dec-22 to 12-Dec-22
2022-12-23 | Concrete was not issued due to non-availablity of M-sand
2022-12-28 | Concrete for Pre-cast not available due shortage of OPC cement in the batching Plant
2022-12-30 | Concrete was not issued due to non-availablity of M-sand
2023-01-06 | Due to Poor Quality of concrete from JSW batching plant, concreting was not done.
2023-01-10 | 10 mm aggregate is not available at JSW batching plant, concreting was not done.
2023-01-12 | Concrete for Pre-cast not available due shortage of OPC cement in the batching Plant.
2023-01-13 | Concrete for Pre-cast not available due shortage of admixture in the batching Plant.
2023-01-28 | 12 mm and 20 mm aggregate not available at JSW batching Plant.

## Graphs Data (hidden)
Construction |  |  |  | Civil Progress | Plan | Actual | 600
Sr No | Scope | Remaining Scope | Achieved | 2022-03-01 | 12 | 21 | 21 | 621
Civil Works | 62550 | 8461.45 | 54088.55 | 2022-04-01 | 1402 | 955 | 976 | 1576
|  |  |  | 2022-05-01 | 1265 | 754 | 1730 | 2330
Engineering |  |  |  | 2022-06-01 | 1235 | 952 | 2682 | 3282
Sr No | Remaining Scope |  | Achieved | 2022-07-01 | 2438 | 1023 | 3705 | 4305
Civil Works | 0 |  | 62550 | 2022-08-01 | 2970 | 1440 | 5145 | 5745
|  |  |  | 2022-09-01 | 3856 | 2085 | 7230 | 7830
|  |  |  | 2022-10-01 | 3386 | 2807 | 10037 | 10637
|  |  |  | 2022-11-01 | 4272 | 3981 | 14018 | 14618
|  |  |  | 2022-12-01 | 4972 | 3138 | 17156 | 17756
|  |  |  | 2023-01-01 | 5498 | 3198 | 20354 | 20954
|  |  |  | 2023-02-01 | 5483 | 3482 | 23836 | 24436
|  |  |  | 2023-03-01 | 4649 | 3252 | 27088 | 27688
|  |  |  | 2023-04-01 | 5656 | 2982 | 30070 | 30670
|  |  |  | 2023-05-01 | 4133 | 1620 | 31690 | 32290
|  |  |  | 2023-06-01 | 4552 | 2934.5 | 34624.5 | 35224.5
|  |  |  | 2023-07-01 | 4404 | 2693 | 37317.5 | 37917.5
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
|  |  |  | Engineering | Plan | Actual |  | 32.2
|  |  |  | 2022-03-01 | 6000 | 3500 |  |  | 3500
|  |  |  | 2022-04-01 | 9000 | 5500 |  |  | 9000
|  |  |  | 2022-05-01 | 13000 | 6500 |  |  | 15500
|  |  |  | 2022-06-01 | 14500 | 7500 |  |  | 23000
|  |  |  | 2022-07-01 | 8250 | 7912 |  | 7912 | 30912
|  |  |  | 2022-08-01 | 28088 | 8801 |  |  | 39713
|  |  |  | 2022-09-01 | 19337 | 4287 |  | 4287 | 44000
|  |  |  | 2022-10-01 | 8000 | 2157 |  |  | 46157
|  |  |  | 2022-11-01 | 12893 | 0 |  |  | 46157
|  |  |  | 2022-12-01 | 12893 | 4911 |  |  | 51068
|  |  |  | 2023-01-01 | 4788 | 0 |  |  | 51068
|  |  |  | 2023-02-01 | 4788 | 0 |  |  | 51068
|  |  |  | 2023-03-01 | 4788 | 0 |  |  | 51068
|  |  |  | 2023-04-01 | 4788 | 0 |  |  | 51068
|  |  |  | 2023-05-01 | 4788 | 0 |  |  | 51068
|  |  |  | 2023-06-01 | 8208 | 8208 |  |  | 59276
|  |  |  | 2023-07-01 | 0 | 0 |  |  | 59276
2023-08-01
2023-09-01
2023-10-01
2023-11-01
2023-12-01
2024-01-01
2024-02-01
[5 empty] | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
|  |  |  | Engineering Actual | 3500 | 9000 | 15500 | 23000 | 30912 | 39713 | 44000 | 46157 | 46157 | 51068 | 51068 | 51068 | 51068 | 51068 | 51068 | 59276 | 59276 | 59276 | 59276 | 59276 | 59276 | 59276 | 59276 | 59276
|  |  |  | Workfront Non-Availability | 2023-07-01: 6123
|  |  |  | Construction Actual | 621 | 1576 | 2332 | 3288 | 4297 | 5656 | 7693 | 10037 | 14018 | 17156 | 20354 | 23836 | 27088 | 30070 | 30670 | 35224.5 | 37917.5 | 0

## Civil S-curve (hidden)
|  | Activity | Conc per footing |  | Completed till date (nos.) | Area | Footings (nos.) |  |  |  | Completed till date (%) |  | A | B | C | D | E | F | G | H | I | J | K
|  | PCC | 3.5 |  | 339.7071 | A | 40 |  |  |  | 37.36% |  | 140 | 98 | 140 | 189 | 126 | 105 | 210 | 175 | 192.5 | 150.5 | 385
|  | RCC Foundation | 24 |  | 151 | B | 28 |  |  |  | 16.61% |  | 960 | 672 | 960 | 1296 | 864 | 720 | 1440 | 1200 | 1320 | 1032 | 2640
|  | Step Footing | 5.5 |  | 147 | C | 40 |  |  |  | 16.17% |  | 220 | 154 | 220 | 297 | 198 | 165 | 330 | 275 | 302.5 | 236.5 | 605
|  | Pier 1900 mm | 6 |  | 136 | D | 54 |  |  |  | 14.96% |  | 240 | 168 | 240 | 324 | 216 | 180 | 360 | 300 | 330 | 258 | 660
|  | Pier 1600 mm | 6 |  | 50.59 | E | 36 |  |  |  | 5.563% |  | 240 | 168 | 240 | 324 | 216 | 180 | 360 | 300 | 330 | 258 | 660
|  | Pier Cap | 9 |  | 18 | F | 30 |  |  |  | 1.979% |  | 360 | 252 | 360 | 486 | 324 | 270 | 540 | 450 | 495 | 387 | 990
|  | Track Beam with Nose | 12 |  | 11.0526 | G | 60 |  |  |  | 1.215% |  | 480 | 336 | 480 | 648 | 432 | 360 | 720 | 600 | 660 | 516 | 1320
|  | Track Beam without Nose | 12 |  | 36.7213 | H | 50 |  |  |  | 4.038% |  | 480 | 336 | 480 | 648 | 432 | 360 | 720 | 600 | 660 | 516 | 1320
|  | h - Section Beam | 12 |  | 3.2787 | I | 55 |  |  |  | 0.3606% |  | 480 | 336 | 480 | 648 | 432 | 360 | 720 | 600 | 660 | 516 | 1320
|  | U - Section Beam | 12 |  | 15.9962 | J | 43 |  |  |  | 1.759% |  | 480 | 336 | 480 | 648 | 432 | 360 | 720 | 600 | 660 | 516 | 1320
|  | P-way |  |  |  | K | 110 | [5 empty] | 4080 | 2856 | 4080 | 5508 | 3672 | 3060 | 6120 | 5100 | 5610 | 4386 | 11220
|  | Electrical | [10 empty] | 0.95662 | 1.0942 | 0.99436 | 1.0356 | 1.204 | 1.1693 | 0.94069 | 1.0094 | 1.0501 | 1.1202 | 1.1114
|  |  | 102 |  | 909.3459 |  | 546
|  | Plan |  |  |  | 2022-09-24 |  | Till
| # | Area | Total Footings (nos.) | UoM | Concreting Scope | Completed Till Date | Balance | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
7.326% | 1 | A | 40 |  | 3903 | 3983.5 | -90.5 | 60 | 100 | 150 | 180 | 225 | 330 | 410 | 473 | 490 | 449 | 385 | 274 | 212 | 129 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3903 | 0 |  | 2418
| a | PCC |  | cum | 119 | 129 | -10 | 10 | 10 | 20 | 20 | 20 | A: 20; B: 10; C: 9 | [10 empty] | 119 | 0
| b | RCC Foundation |  | cum | 770 | 800 | -30 | 50 | 70 | 90 | 100 | 100 | A: 100; B: 80; C: 80; D: 80; E: 20 | [10 empty] | 770 | 0
| c | Step Footing |  | cum | 189 | 190 | -1 |  | 20 | 20 | 20 | 40 | A: 30; B: 20; C: 25; D: 10; E: 4 | [10 empty] | 189 | 0
| d | Pier 1900 mm |  | cum | 227 | 243 | -16 |  |  | 20 | 20 | 25 | A: 25; B: 30; C: 33; D: 30; E: 30; F: 14 | [10 empty] | 227 | 0
| e | Pier 1600 mm |  | cum | 238 | 194.5 | 43.5 |  |  |  | 20 | 20 | 25 | 25 | 35 | 34 | 45 | 25 | 9 | [14 empty] | 238 | 0
| f | Pier Cap |  | cum | 529 | 531 | -2 |  |  |  |  | 20 | 50 | 80 | 80 | 70 | 70 | 80 | 50 | 29 | [13 empty] | 529 | 0
| g | Track Beam with Nose |  | cum | 892 | 911 | -19 | [5 empty] | 50 | 100 | 130 | 160 | 140 | 110 | 80 | 70 | 52 | [12 empty] | 892 | 0
| h | Track Beam without Nose |  | cum | 0 | 0 | 0 | [26 empty] | 0 | 0 | bar: I
| i | h - Section Beam |  | cum | 476 | 478 | -2 | [5 empty] | 30 | 35 | 40 | 60 | 80 | 80 | 65 | 55 | 31 | [12 empty] | 476 | 0
| j | U - Section Beam |  | cum | 401 | 455 | -54 | [6 empty] | 30 | 35 | 40 | 50 | 60 | 60 | 50 | 40 | 36 | [11 empty] | 401 | 0
| k | Pre-cast Slab |  | cum | 62 | 52 | [8 empty] | 6 | 6 | 10 | 16 | 10 | 8 | 6 | [12 empty] | 62 | 0
5.128% | 2 | B | 28 |  | 3125 | 3109.75 | -4.25 | 80 | 115 | 165 | 230 | 345 | 403 | 404 | 423 | 329 | 225 | 207 | 82 | 68 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3125 | 0 |  | 2494
| a | PCC |  | cum | 83 | 100 | -17 | 15 | 15 | 15 | 10 | 10 | A: 18 | [10 empty] | 83 | 0 |  | 83
| b | RCC Foundation |  | cum | 539 | 536.75 | 2.25 | 50 | 80 | 100 | 120 | 80 | A: 60; B: 49 | [10 empty] | 539 | 0 |  | 539
| c | Step Footing |  | cum | 132 | 139 | -7 | 15 | 10 | 10 | 15 | 20 | A: 30; B: 32 | [10 empty] | 132 | 0 |  | 132
| d | Pier 1900 mm |  | cum | 159 | 155 | 4 |  | 10 | 20 | 25 | 25 | A: 30; B: 28; C: 21 | [10 empty] | 159 | 0 |  | 159
| e | Pier 1600 mm |  | cum | 143 | 118.5 | 24.5 |  |  | 20 | 20 | 30 | A: 30; B: 20; C: 23 | [10 empty] | 143 | 0 |  | 143
| f | Pier Cap |  | cum | 436 | 451 | -15 |  |  |  | 40 | 60 | A: 60; B: 80; C: 120; D: 76 | [10 empty] | 436 | 0 |  | 436
| g | Track Beam with Nose |  | cum | 532 | 529 | 3 |  |  |  |  | 60 | A: 60; B: 80; C: 100; D: 90; E: 80; F: 62 | [10 empty] | 532 | 0 |  | 390
| h | Track Beam without Nose |  | cum | 571 | 552 | 19 |  |  |  |  | 60 | A: 80; B: 80; C: 120; D: 100; E: 80; F: 51 | [10 empty] | 571 | 0 |  | 440
| i | h - Section Beam |  | cum | 346 | 342 | 4 | [5 empty] | 35 | 35 | 35 | 35 | 35 | 50 | 50 | 40 | 31 | [12 empty] | 346 | 0 |  | 140
| j | U - Section Beam |  | cum | 146 | 168 | -22 | [5 empty] | D: 24; E: 24; F: 36; G: 24; H: 24; I: 14 | [10 empty] | 146 | 0 |  | 24
| k | Pre-cast Slab |  | cum | 38 | 18.5 | [8 empty] | 4 | 4 | 6 | 8 | 8 | 4 | 4 | [12 empty] | 38 | 0 |  | 8
7.326% | 3 | C | 40 |  | 4057 | 3881 | 174 | 15 | 160 | 165 | 200 | 270 | 420 | 470 | 488 | 516 | 442 | 357 | 279 | 220 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4057 | 0 |  | 2704
| a | PCC |  | cum | 128 | 125 | 3 | 15 | 15 | 15 | 20 | 20 | A: 15; B: 15; C: 13 | [10 empty] | 128 | 0 |  | 128
| b | RCC Foundation |  | cum | 896 | 770 | 126 |  | 130 | 120 | 120 | 120 | A: 110; B: 100; C: 100; D: 96 | [10 empty] | 896 | 0 |  | 896
| c | Step Footing |  | cum | 195 | 161 | 34 |  | 15 | 20 | 20 | 25 | A: 25; B: 30; C: 25; D: 15; E: 20 | [10 empty] | 195 | 0 |  | 175
| d | Pier 1900 mm |  | cum | 227 | 202 | 25 |  |  | 10 | 20 | 30 | A: 40; B: 35; C: 30; D: 28; E: 15; F: 19 | [10 empty] | 227 | 0 |  | 193
| e | Pier 1600 mm |  | cum | 321 | 260 | 61 |  |  |  | 20 | 30 | 35 | 40 | 40 | 50 | 55 | 31 | 20 | [14 empty] | 321 | 0 |  | 215
| f | Pier Cap |  | cum | 519 | 479 | 40 |  |  |  |  | 45 | 55 | 55 | 65 | 80 | 70 | 60 | 50 | 39 | [13 empty] | 519 | 0 |  | 300
| g | Track Beam with Nose |  | cum | 699 | 756 | -57 | [5 empty] | 80 | 90 | 100 | 110 | 95 | 85 | 75 | 64 | [13 empty] | 699 | 0 |  | 380
| h | Track Beam without Nose |  | cum | 365 | 360 | 5 | [5 empty] | 20 | 40 | 40 | 45 | 65 | 65 | 50 | 40 | [13 empty] | 365 | 0 |  | 145
| i | h - Section Beam |  | cum | 378 | 372 | 6 | [5 empty] | 20 | 30 | 40 | 50 | 70 | 55 | 45 | 45 | 23 | [12 empty] | 378 | 0 |  | 140
| j | U - Section Beam |  | cum | 315 | 384 | -69 | [5 empty] | 20 | 35 | 35 | 40 | 50 | 40 | 35 | 30 | 30 | [12 empty] | 315 | 0 |  | 130
| k | Pre-cast Slab |  | cum | 14 | 12 | [6 empty] | D: 2; E: 2; F: 2; G: 4; H: 2; I: 2 | [10 empty] | 14 | 0 |  | 2
9.89% | 4 | D | 54 |  | 5704 | 5826.6 | -124.6 | 80 | 115 | 135 | 160 | 385 | 440 | 520 | 620 | 722 | 641 | 458 | 402 | 326 | 244 | 256 | 111 | 53 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5704 | 0 |  | 3177
| a | PCC |  | cum | 181 | 199 | -18 | 15 | 20 | 20 | 20 | 25 | A: 25; B: 20; C: 20; D: 16 | [10 empty] | 181 | 0 |  | 181
| b | RCC Foundation |  | cum | 1040 | 1075 | -35 | 50 | 70 | 70 | 90 | 130 | A: 130; B: 130; C: 130; D: 130; E: 110 | [10 empty] | 1040 | 0 |  | 930
| c | Step Footing |  | cum | 255 | 274 | -19 | 15 | 25 | 30 | 30 | 30 | A: 30; B: 35; C: 20; D: 20; E: 20 | [10 empty] | 255 | 0 |  | 235
| d | Pier 1900 mm |  | cum | 307 | 320.6 | -13.6 |  |  | 15 | 20 | 35 | 35 | 35 | 50 | 50 | 25 | 20 | 12 | 10 | [13 empty] | 307 | 0 |  | 240
| e | Pier 1600 mm |  | cum | 160 | 160 | 0 | [5 empty] | 10 | 10 | 20 | 30 | 30 | 20 | 20 | 10 | 10 | [12 empty] | 160 | 0 |  | 70
| f | Pier Cap |  | cum | 818 | 784 | 34 |  |  |  |  | 45 | 50 | 70 | 90 | 100 | 120 | 110 | 80 | 60 | 50 | 43 | [11 empty] | 818 | 0 |  | 355
| g | Track Beam with Nose |  | cum | 986 | 1008 | -22 |  |  |  |  | 60 | 80 | 100 | 120 | 140 | 120 | 100 | 80 | 60 | 40 | 70 | 16 | [10 empty] | 986 | 0 |  | 500
| h | Track Beam without Nose |  | cum | 1002 | 1008 | -6 |  |  |  |  | 60 | 80 | 100 | 120 | 140 | 120 | 100 | 80 | 60 | 40 | 70 | 32 | [10 empty] | 1002 | 0 |  | 500
| i | h - Section Beam |  | cum | 432 | 408 | 24 | [7 empty] | 20 | 40 | 40 | 40 | 60 | 80 | 50 | 30 | 30 | 30 | 12 | [8 empty] | 432 | 0 |  | 60
| j | U - Section Beam |  | cum | 471 | 540 | -69 | [6 empty] | 20 | 30 | 50 | 50 | 60 | 60 | 40 | 50 | 40 | 30 | 20 | 21 | [8 empty] | 471 | 0 |  | 100
| k | Pre-cast Slab |  | cum | 52 | 50 | [9 empty] | 6 | 6 | 8 | 10 | 6 | 4 | 3 | 3 | 3 | 3 | [8 empty] | 52 | 0 |  | 6
6.593% | 5 | E | 36 |  | 4421 | 1865 | 2556 | 0 | 0 | 60 | 90 | 105 | 200 | 305 | 520 | 560 | 573 | 566 | 451 | 371 | 255 | 264 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4421 | 0 |  | 1840
| a | PCC |  | cum | 113 | 91 | 22 |  |  | 10 | 10 | 10 | A: 15; B: 20; C: 15; D: 15; E: 18 | [10 empty] | 113 | 0 |  | 95
| b | RCC Foundation |  | cum | 732 | 540 | 192 |  |  | 50 | 70 | 80 | A: 100; B: 100; C: 90; D: 90; E: 80; F: 72 | [10 empty] | 732 | 0 |  | 580
| c | Step Footing |  | cum | 179 | 135 | 44 |  |  |  | 10 | 15 | A: 15; B: 20; C: 30; D: 30; E: 35; F: 24 | [10 empty] | 179 | 0 |  | 120
| d | Pier 1900 mm |  | cum | 216 | 126 | 90 | [5 empty] | 20 | 35 | 35 | 35 | 30 | 30 | 31 | [14 empty] | 216 | 0 |  | 125
| e | Pier 1600 mm |  | cum | 426 | 142 | 284 | [5 empty] | 50 | 50 | 50 | 40 | 60 | 70 | 60 | 46 | [13 empty] | 426 | 0 |  | 190
| f | Pier Cap |  | cum | 590 | 137 | 453 | [6 empty] | 80 | 100 | 100 | 100 | 80 | 70 | 60 | [13 empty] | 590 | 0 |  | 280
| g | Track Beam with Nose |  | cum | 847 | 202 | 645 | [7 empty] | 120 | 120 | 100 | 120 | 120 | 100 | 80 | 87 | [11 empty] | 847 | 0 |  | 240
| h | Track Beam without Nose |  | cum | 467 | 432 | 35 | [7 empty] | 50 | 60 | 60 | 70 | 60 | 50 | 60 | 57 | [11 empty] | 467 | 0 |  | 110
| i | h - Section Beam |  | cum | 449 | 48 | 401 | [7 empty] | 30 | 40 | 40 | 50 | 60 | 60 | 60 | 60 | 49 | [10 empty] | 449 | 0 |  | 70
| j | U - Section Beam |  | cum | 402 | 12 | 390 | [8 empty] | 30 | 50 | 50 | 50 | 55 | 55 | 60 | 52 | [10 empty] | 402 | 0 |  | 30
| k | Pre-cast Slab |  | cum |  | 0 | [27 empty] | 0 | 0 |  | 0 | bar: K
5.495% | 6 | F | 30 |  | 3578 | 3712.5 | -132.5 | 0 | 0 | 0 | 115 | 235 | 375 | 435 | 465 | 526 | 426 | 293 | 292 | 230 | 156 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3578 | 0 |  | 2151
| a | PCC |  | cum | 89 | 94 | -5 |  |  |  | 15 | 15 | A: 15; B: 15; C: 15; D: 14 | [10 empty] | 89 | 0 |  | 89
| b | RCC Foundation |  | cum | 578 | 596 | -18 |  |  |  | 100 | 100 | A: 130; B: 100; C: 80; D: 68 | [10 empty] | 578 | 0 |  | 578
| c | Step Footing |  | cum | 142 | 122 | 20 |  |  |  |  | 20 | A: 20; B: 30; C: 30; D: 30; E: 12 | [10 empty] | 142 | 0 |  | 130
| d | Pier 1900 mm |  | cum | 171 | 179 | -8 |  |  |  |  | 20 | A: 20; B: 30; C: 30; D: 30; E: 30; F: 11 | [10 empty] | 171 | 0 |  | 130
| e | Pier 1600 mm |  | cum | 519 | 465.5 | 53.5 |  |  |  |  | 40 | 60 | 100 | 120 | 80 | 60 | 37 | 22 | [14 empty] | 519 | 0 |  | 400
| f | Pier Cap |  | cum | 481 | 554 | -73 |  |  |  |  | 40 | 40 | 50 | 70 | 100 | 80 | 41 | 30 | 30 | [13 empty] | 481 | 0 |  | 300
| g | Track Beam with Nose |  | cum | 412 | 432 | -20 | [5 empty] | 30 | 30 | 40 | 50 | 60 | 60 | 50 | 50 | 42 | [12 empty] | 412 | 0 |  | 150
| h | Track Beam without Nose |  | cum | 807 | 864 | -57 | [5 empty] | 60 | 80 | 80 | 120 | 140 | 100 | 120 | 60 | 47 | [12 empty] | 807 | 0 |  | 340
| i | h - Section Beam |  | cum | 212 | 204 | 8 | [8 empty] | 20 | 30 | 30 | 30 | 50 | 40 | 12 | [11 empty] | 212 | 0 |  | 20
| j | U - Section Beam |  | cum | 147 | 180 | -33 | [8 empty] | 12 | 12 | 12 | 36 | 36 | 24 | 15 | [11 empty] | 147 | 0 |  | 12
| k | Pre-cast Slab |  | cum | 20 | 22 | [9 empty] | 2 | 2 | 2 | 4 | 4 | 3 | 3 | [11 empty] | 20 | 0 |  | 2
10.99% | 7 | G | 60 |  | 5757 | 4929 | 797 | 0 | 0 | 0 | 190 | 275 | 350 | 398 | 415 | 560 | 632 | 644 | 668 | 535 | 457 | 344 | 224 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5757 |  |  | 2188
| a | PCC |  | cum | 199 | 295 | -96 |  |  |  | 10 | 20 | 20 | 23 | 25 | 25 | 25 | 25 | 26 | [14 empty] | 199 | 0 |  | 123
| b | RCC Foundation |  | cum | 1273 | 1750 | -477 |  |  |  | 120 | 140 | 160 | 180 | 160 | 140 | 140 | 120 | 113 | [14 empty] | 1273 | 0 |  | 900
| c | Step Footing |  | cum | 292 | 288 | 4 |  |  |  | 10 | 10 | 20 | 25 | 25 | 30 | 38 | 50 | 50 | 34 | [13 empty] | 292 | 0 |  | 120
| d | Pier 1900 mm |  | cum | 516 | 553 | -37 |  |  |  | 30 | 35 | 40 | 50 | 55 | 55 | 65 | 55 | 45 | 45 | 41 | [12 empty] | 516 | 0 |  | 265
| e | Pier 1600 mm |  | cum | 678 | 355 | 323 |  |  |  | 20 | 20 | 30 | 30 | 50 | 50 | 70 | 80 | 80 | 100 | 80 | 68 | [11 empty] | 678 | 0 |  | 200
| f | Pier Cap |  | cum | 676 | 352 | 324 |  |  |  |  | 30 | 50 | 50 | 50 | 60 | 60 | 60 | 70 | 70 | 70 | 60 | 46 | [10 empty] | 676 | 0 |  | 240
| g | Track Beam with Nose |  | cum | 709 | 418 | 291 |  |  |  |  | 20 | 30 | 40 | 50 | 70 | 80 | 80 | 100 | 90 | 60 | 40 | 49 | [10 empty] | 709 | 0 |  | 210
| h | Track Beam without Nose |  | cum | 665 | 623 | 42 | [8 empty] | 90 | 90 | 90 | 90 | 90 | 80 | 80 | 55 | [10 empty] | 665 | 0 |  | 90
| i | h - Section Beam |  | cum | 478 | 144 | 334 | [8 empty] | 40 | 60 | 60 | 60 | 70 | 70 | 50 | 40 | 28 | [9 empty] | 478 | 0 |  | 40
| j | U - Section Beam |  | cum | 233 | 144 | 89 | [5 empty] | F: 20; G: 30; H: 30; I: 50; J: 40; K: 30 | 33 | [9 empty] | 233 | 0 |  | 0
| k | Pre-cast Slab |  | cum | 38 | 7 | [10 empty] | 4 | 4 | 4 | 6 | 6 | 6 | 4 | 4 | [9 empty] | 38 | 0 |  | 0
9.158% | 8 | H | 50 |  | 5148 | 5098.5 | 43 | 90 | 115 | 175 | 220 | 300 | 460 | 524 | 580 | 628 | 582 | 454 | 392 | 339 | 217 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5148 |  |  | 3092
| a | PCC |  | cum | 134 | 182 | -48 | 10 | 15 | 20 | 35 | 20 | A: 20; B: 14 | [10 empty] | 134 | 0 |  | 134
| b | RCC Foundation |  | cum | 875 | 980 | -105 | 80 | 80 | 100 | 100 | 120 | A: 120; B: 100; C: 80; D: 95 | [10 empty] | 875 | 0 |  | 875
| c | Step Footing |  | cum | 238 | 265 | -27 |  | 20 | 30 | 35 | 40 | A: 30; B: 30; C: 30; D: 23 | [10 empty] | 238 | 0 |  | 238
| d | Pier 1900 mm |  | cum | 284 | 340 | -56 |  |  | 25 | 25 | 35 | A: 35; B: 35; C: 35; D: 40; E: 40; F: 14 | [10 empty] | 284 | 0 |  | 230
| e | Pier 1600 mm |  | cum | 293 | 276 | 17 |  |  |  | 25 | 25 | 25 | 35 | 35 | 40 | 40 | 38 | 30 | [14 empty] | 293 | 0 |  | 185
| f | Pier Cap |  | cum | 685 | 670 | 15 |  |  |  |  | 60 | 60 | 100 | 120 | 100 | 80 | 60 | 50 | 55 | [13 empty] | 685 | 0 |  | 440
| g | Track Beam with Nose |  | cum | 589 | 552 | 37 | [5 empty] | 50 | 50 | 70 | 70 | 80 | 80 | 80 | 80 | 29 | [12 empty] | 589 | 0 |  | 240
| h | Track Beam without Nose |  | cum | 1334 | 1258 | 76 | [5 empty] | 120 | 160 | 160 | 200 | 240 | 140 | 120 | 100 | 94 | [12 empty] | 1334 | 0 |  | 640
| i | h - Section Beam |  | cum | 495 | 336 | 159 | [7 empty] | 50 | 60 | 60 | 70 | 70 | 70 | 60 | 55 | [11 empty] | 495 | 0 |  | 110
| j | U - Section Beam |  | cum | 203 | 228 | -25 | [5 empty] | E: 40; F: 50; G: 40; H: 30; I: 30; J: 13 | [10 empty] | 203 | 0 |  | 0
| k | Pre-cast Slab |  | cum | 18 | 11.5 | [6 empty] | E: 2; F: 2; G: 2; H: 4; I: 4; J: 4 | [10 empty] | 18 | 0 |  | 0
10.07% | 9 | I | 55 |  | 5891 | 6473 | -589 | 0 | 0 | 90 | 185 | 285 | 445 | 560 | 557 | 535 | 566 | 520 | 498 | 459 | 374 | 336 | 265 | 156 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5891 |  |  | 2657
| a | PCC |  | cum | 132 | 177 | -45 |  |  | 20 | 20 | 20 | A: 20; B: 30; C: 22 | [10 empty] | 132 | 0 |  | 132
| b | RCC Foundation |  | cum | 860 | 1098 | -238 |  |  | 50 | 100 | 120 | A: 140; B: 160; C: 120; D: 100; E: 70 | [10 empty] | 860 | 0 |  | 790
| c | Step Footing |  | cum | 226 | 286 | -60 |  |  | 20 | 25 | 30 | A: 30; B: 30; C: 20; D: 20; E: 31; F: 20 | [10 empty] | 226 | 0 |  | 175
| d | Pier 1900 mm |  | cum | 312 | 312 | 0 |  |  |  | 20 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 25 | 22 | [13 empty] | 312 | 0 |  | 195
| e | Pier 1600 mm |  | cum | 455 | 455 | 0 |  |  |  | 20 | 30 | 30 | 50 | 60 | 60 | 50 | 35 | 43 | 25 | 20 | 32 | [11 empty] | 455 | 0 |  | 250
| f | Pier Cap |  | cum | 820 | 855 | -35 |  |  |  |  | 50 | 70 | 90 | 100 | 80 | 100 | 80 | 70 | 60 | 50 | 40 | 30 | [10 empty] | 820 | 0 |  | 390
| g | Track Beam with Nose |  | cum | 866 | 996 | -130 | [5 empty] | 40 | 45 | 50 | 60 | 70 | 80 | 100 | 120 | 100 | 80 | 80 | 41 | [9 empty] | 866 | 0 |  | 195
| h | Track Beam without Nose |  | cum | 1362 | 1371 | -9 | [5 empty] | 80 | 80 | 100 | 120 | 140 | 180 | 160 | 140 | 120 | 100 | 90 | 52 | [9 empty] | 1362 | 0 |  | 380
| i | h - Section Beam |  | cum | 470 | 447.5 | 22.5 | [6 empty] | 20 | 30 | 40 | 40 | 60 | 50 | 50 | 45 | 45 | 30 | 30 | 30 | [8 empty] | 470 | 0 |  | 90
| j | U - Section Beam |  | cum | 367 | 461.5 | -94.5 | [6 empty] | 20 | 20 | 20 | 30 | 30 | 50 | 40 | 35 | 35 | 30 | 30 | 27 | [8 empty] | 367 | 0 |  | 60
| k | Pre-cast Slab |  | cum | 21 | 14 | [6 empty] | H: 2; I: 4; J: 4; K: 5 | 3 | 3 | [8 empty] | 21 | 0 |  | 0
7.875% | 10 | J | 43 |  | 4913 | 3950.5 | 933.5 | 0 | 0 | 0 | 110 | 320 | 470 | 570 | 640 | 692 | 571 | 383 | 366 | 316 | 237 | 181 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4913 | 0 |  | 2802
| a | PCC |  | cum | 122 | 126 | -4 |  |  |  | 10 | 20 | A: 30; B: 20; C: 20; D: 22 | [10 empty] | 122 | 0 |  | 122
| b | RCC Foundation |  | cum | 794 | 810 | -16 |  |  |  | 100 | 130 | A: 130; B: 130; C: 130; D: 120; E: 54 | [10 empty] | 794 | 0 |  | 740
| c | Step Footing |  | cum | 207 | 206 | 1 |  |  |  |  | 30 | A: 40; B: 40; C: 40; D: 30; E: 27 | [10 empty] | 207 | 0 |  | 180
| d | Pier 1900 mm |  | cum | 250 | 253 | -3 |  |  |  |  | 30 | 30 | 40 | 40 | 40 | 30 | 30 | 10 | [14 empty] | 250 | 0 |  | 180
| e | Pier 1600 mm |  | cum | 650 | 656.5 | -6.5 |  |  |  |  | 30 | 50 | 100 | 100 | 120 | 100 | 60 | 50 | 40 | [13 empty] | 650 | 0 |  | 400
| f | Pier Cap |  | cum | 681 | 519 | 162 |  |  |  |  | 30 | 70 | 100 | 100 | 120 | 80 | 50 | 50 | 40 | 41 | [12 empty] | 681 | 0 |  | 420
| g | Track Beam with Nose |  | cum | 818 | 516 | 302 |  |  |  |  | 30 | 60 | 80 | 90 | 110 | 100 | 80 | 80 | 80 | 60 | 48 | [11 empty] | 818 | 0 |  | 370
| h | Track Beam without Nose |  | cum | 689 | 660 | 29 |  |  |  |  | 20 | 60 | 60 | 70 | 80 | 100 | 80 | 60 | 50 | 50 | 59 | [11 empty] | 689 | 0 |  | 290
| i | h - Section Beam |  | cum | 284 | 60 | 224 | [7 empty] | 20 | 20 | 30 | 30 | 50 | 50 | 30 | 30 | 24 | [10 empty] | 284 | 0 |  | 40
| j | U - Section Beam |  | cum | 389 | 144 | 245 | [7 empty] | 30 | 30 | 50 | 50 | 60 | 50 | 50 | 40 | 29 | [10 empty] | 389 | 0 |  | 60
| k | Pre-cast Slab |  | cum | 29 | 0 | [6 empty] | F: 3; G: 6; H: 6; I: 6; J: 4; K: 4 | [10 empty] | 29 | 0 |  | 0
20.15% | 11 | K | 110 |  | 12470 | 9044.5 | 3425.5 | 0 | 0 | 10 | 95 | 375 | 450 | 925 | 1140 | 1240 | 1450 | 1360 | 1280 | 1140 | 990 | 904 | 554 | 483 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12470 | 0 |  | 4235
| a | PCC |  | cum | 355 | 322 | 33 |  |  | 10 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 35 | 25 | 25 | 15 | [12 empty] | 355 | 0
| b | RCC Foundation |  | cum | 1854 | 2067 | -213 |  |  |  | 60 | 100 | 100 | 120 | 160 | 160 | 180 | 200 | 200 | 200 | 200 | 174 | [11 empty] | 1854 | 0
| c | Step Footing |  | cum | 495 | 540 | -45 |  |  |  |  | 20 | 30 | 50 | 60 | 60 | 50 | 50 | 50 | 50 | 50 | 25 | [11 empty] | 495 | 0
| d | Pier 1900 mm |  | cum | 601 | 660 | -59 |  |  |  |  | 20 | 25 | 50 | 50 | 60 | 60 | 60 | 60 | 60 | 60 | 50 | 46 | [10 empty] | 601 | 0
| e | Pier 1600 mm |  | cum | 1663 | 1589 | 74 |  |  |  |  | 100 | 130 | 150 | 150 | 180 | 240 | 180 | 160 | 120 | 80 | 70 | 53 | 50 | [9 empty] | 1663 | 0
| f | Pier Cap |  | cum | 1840 | 328 | 1512 |  |  |  |  | 100 | 130 | 150 | 150 | 180 | 240 | 200 | 180 | 140 | 100 | 120 | 80 | 70 | [9 empty] | 1840 | 0
| g | Track Beam with Nose |  | cum | 1631 | 1372 | 259 | [6 empty] | 150 | 160 | 180 | 240 | 200 | 180 | 140 | 100 | 120 | 80 | 81 | [9 empty] | 1631 | 0
| h | Track Beam without Nose |  | cum | 2323 | 1941 | 382 | [6 empty] | 220 | 250 | 260 | 270 | 260 | 220 | 200 | 200 | 180 | 140 | 123 | [9 empty] | 2323 | 0
| i | h - Section Beam |  | cum | 463 | 36 | 427 | [7 empty] | 20 | 20 | 30 | 50 | 80 | 80 | 60 | 40 | 30 | 30 | 23 | [8 empty] | 463 | 0
| j | U - Section Beam |  | cum | 1186 | 180 | 1006 | [7 empty] | 100 | 100 | 100 | 120 | 120 | 120 | 120 | 120 | 120 | 120 | 46 | [8 empty] | 1186 | 0
| k | Pre-cast Slab |  | cum | 59 | 9.5 | 49.5 | [7 empty] | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 9 | 5 | [8 empty] | 59 | 0
| 12 | Abutment wall- PART-A | 0 |  | 491 | 673 | -182 | [17 empty] | 491 | [8 empty] | 491 | 0 |  | 0
| 13 | Abutment wall- PART-D | 0 |  | 830 | 595 | 235 | [17 empty] | 830 | [8 empty] | 830 | 0
| 14 | Cast In-situ slab- 1- PART-G | 0 |  | 471 | 0 | 471 | [18 empty] | 471 | [7 empty] | 471 | 0
| 15 | Cast In-situ slab- 2- PART-G | 0 |  | 1141 | 0 | 1141 | [18 empty] | 1141 | [7 empty] | 1141 | 0
| 16 | Cast In-situ slab- PART-C | 0 |  | 650 | 862 | -212 | [17 empty] | 650 | [8 empty] | 650 | 0
|  | Planned Total: | 546 |  | 62550 | 54003.85 | 8441.15 | 325 | 605 | 950 | 1775 | 3120 | 4343 | 5521 | 6321 | 6798 | 6557 | 5627 | 4984 | 4216 | 3163 | 2423 | 1312 | 757 | 2141 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 62550
|  |  | Upto Feb-22 |  | PCC | 600
[5 empty] | Total | 54603.85
|  | Actual |  |  |  | 2022-09-24 |  | Till
| # | Area | Total Footings (nos.) | UoM | Concreting Scope | Completed Till Date | Balance | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 |  | -84.7
7.326% | 1 | A | 40 |  | 3903 | 3983.5 | -90.5 | 21 | 264 | 24 | 0 | 92 | 29.7 | 114 | 216 | 161 | 14.5 | 140 | 502.5 | 717 | 427.5 | 369.5 | 564.5 | 0 | 4.5 | 195 | 125 | 0 | 2.5 | 0 | 0 | 0 | 0 | 3984.2 | -0.7 | 102.1% |  | 3657.2
| a | PCC | 0 | cum | 119 | 129 | -10 | 21 | 8 | 0 | 0 | 0 | 0 | 34 | 0 | 0 | 0 | 16 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 129 |  | 108.4%
| b | RCC Foundation | 0 | cum | 770 | 800 | -30 | 0 | 160 | 0 | 0 | 0 | 0 | 40 | 120 | 0 | 0 | 80 | 0 | 100 | 180 | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 |  | 103.9%
| c | Step Footing | 0 | cum | 189 | 190 | -1 | 0 | 48 | 0 | 0 | 0 | 0 | 12 | 25 | 0 | 0 | 20 | 0 | 25 | 35 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 190 |  | 100.5%
| d | Pier 1900 mm | 0 | cum | 227 | 243 | -16 | 0 | 48 | 0 | 0 | 0 | 0.7 | 0 | 51 | 0 | 0 | 0 | 24 | 30 | 54 | 0 | 0 | 0 | 0 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 243.7 |  | 107.4%
| e | Pier 1600 mm | 0 | cum | 238 | 194.5 | 43.5 | 0 | 0 | 24 | 0 | 14 | 0 | 0 | 8 | 7 | 0 | 0 | 0 | 40 | 0 | 71.5 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 194.5 |  | 81.72%
| f | Pier Cap | 0 | cum | 529 | 531 | -2 | 0 | 0 | 0 | 0 | 54 | 29 | 28 | 12 | 94 | 0 | 0 | 0 | 0 | 48 | 65 | 118 | 0 | 0 | 0 | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 531 |  | 100.4%
| g | Track Beam with Nose | 0 | cum | 892 | 911 | -19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 215 | 276 | 108 | 96 | 216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 911 |  | 102.1%
| h | Track Beam without Nose | 0 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
| i | h - Section Beam | 0 | cum | 476 | 478 | -2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 71 | 84 | 0 | 119 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 478 |  | 100.4%
| j | U - Section Beam | 0 | cum | 401 | 455 | -54 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 60 | 12 | 0 | 167 | 132 | 0 | 12 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455 |  | 113.5%
| k | Pre-cast Slab | 0 | cum | 62 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 | 7.5 | 24 | 2.5 | 6 | 2.5 | 0 | 4.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 52 |  | 83.87%
5.128% | 2 | B | 28 |  | 3125 | 3109.75 | -4.25 | 0 | 0 | 29 | 313.75 | 20 | 59 | 44 | 14 | 288 | 277 | 24 | 91 | 144 | 396 | 167.5 | 143.5 | 97 | 37 | 146 | 425 | 296 | 110 | 0 | 0 | 0 | 0 | 3121.75 | -12 | 99.9% |  | 2107.75
| a | PCC | 0 | cum | 83 | 100 | -17 | 0 | 0 | 29 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 12 | 36 | 0 | 10 | 0 | 0 | 0 | 0 | 100 |  | 120.5%
| b | RCC Foundation | 0 | cum | 539 | 536.75 | 2.25 | 0 | 0 | 0 | 196.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 0 | 0 | 100 | 180 | 20 | 0 | 0 | 0 | 0 | 0 | 536.75 |  | 99.58%
| c | Step Footing | 0 | cum | 132 | 139 | -7 | 0 | 0 | 0 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 20 | 55 | 5 | 0 | 0 | 0 | 0 | 0 | 139 |  | 105.3%
| d | Pier 1900 mm | 0 | cum | 159 | 155 | 4 | 0 | 0 | 0 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 72 | 12 | 0 | 0 | 0 | 0 | 0 | 155 |  | 97.48%
| e | Pier 1600 mm | 0 | cum | 143 | 118.5 | 24.5 | 0 | 0 | 0 | 0 | 20 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 | 8 | 0 | 0 | 0 | 10 | 56 | 0 | 0 | 0 | 0 | 0 | 118.5 |  | 82.87%
| f | Pier Cap | 0 | cum | 436 | 451 | -15 | 0 | 0 | 0 | 0 | 0 | 22 | 44 | 14 | 0 | 0 | 0 | 67 | 0 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 203 | 64 | 0 | 0 | 0 | 0 | 451 |  | 103.4%
| g | Track Beam with Nose | 0 | cum | 532 | 529 | 3 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 181 | 0 | 0 | 36 | 228 | 12 | 24 | 0 | 12 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 541 |  | 101.7%
| h | Track Beam without Nose | 0 | cum | 571 | 552 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | 60 | 0 | 0 | 96 | 108 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 552 |  | 96.67%
| i | h - Section Beam | 0 | cum | 346 | 342 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 | 12 | 36 | 78 | 60 | 60 | 0 | 0 | 12 | 0 | 36 | 0 | 0 | 0 | 0 | 342 |  | 98.84%
| j | U - Section Beam | 0 | cum | 146 | 168 | -22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 0 | 0 | 0 | 24 | 0 | 12 | 24 | 12 | 12 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 168 |  | 115.1%
| k | Pre-cast Slab | 0 | cum | 38 | 18.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 13 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.5 |  | 48.68%
7.326% | 3 | C | 40 |  | 4057 | 3881 | 174 | 0 | 0 | 0 | 0 | 0 | 12 | 150 | 465 | 133 | 81 | 43 | 164 | 116 | 255 | 292 | 52 | 362 | 305 | 573 | 422 | 384 | 72 | 0 | 0 | 0 | 0 | 3881 | 0 | 95.66% |  | 2125
| a | PCC | 0 | cum | 128 | 125 | 3 | 0 | 0 | 0 | 0 | 0 | 12 | 50 | 17 | 25 | 6 | 6 | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 |  | 97.66%
| b | RCC Foundation | 0 | cum | 896 | 770 | 126 | 0 | 0 | 0 | 0 | 0 | 0 | 80 | 298 | 60 | 40 | 20 | 0 | 54 | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 770 |  | 85.94%
| c | Step Footing | 0 | cum | 195 | 161 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 78 | 0 | 5 | 17 | 0 | 10 | 25 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 161 |  | 82.56%
| d | Pier 1900 mm | 0 | cum | 227 | 202 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 48 | 30 | 0 | 0 | 6 | 12 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 202 |  | 88.99%
| e | Pier 1600 mm | 0 | cum | 321 | 260 | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 110 | 10 | 0 | 60 | 52 | 0 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 260 |  | 81%
| f | Pier Cap | 0 | cum | 519 | 479 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 27 | 0 | 192 | 0 | 206 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 479 |  | 92.29%
| g | Track Beam with Nose | 0 | cum | 699 | 756 | -57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 120 | 396 | 180 | 12 | 0 | 0 | 0 | 0 | 0 | 756 |  | 108.2%
| h | Track Beam without Nose | 0 | cum | 365 | 360 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 48 | 168 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 360 |  | 98.63%
| i | h - Section Beam | 0 | cum | 378 | 372 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 60 | 0 | 36 | 168 | 72 | 0 | 0 | 0 | 0 | 372 |  | 98.41%
| j | U - Section Beam | 0 | cum | 315 | 384 | -69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 132 | 204 | 0 | 0 | 0 | 0 | 0 | 384 |  | 121.9%
| k | Pre-cast Slab | 0 | cum | 14 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 12 |  | 85.71%
9.89% | 4 | D | 54 |  | 5704 | 5826.6 | -124.6 | 0 | 0 | 391 | 629.6 | 211 | 364 | 680 | 1038 | 1238 | 704.5 | 322.5 | 162 | 28 | 35 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 5826.6 | 0 | 102.1% |  | 5806.1
| a | PCC | 0 | cum | 181 | 199 | -18 | 0 | 0 | 64 | 35 | 0 | 0 | 9 | 0 | 51 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 199 |  | 109.9%
| b | RCC Foundation | 0 | cum | 1040 | 1075 | -35 | 0 | 0 | 258 | 357 | 40 | 0 | 60 | 0 | 240 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1075 |  | 103.4%
| c | Step Footing | 0 | cum | 255 | 274 | -19 | 0 | 0 | 57 | 102 | 0 | 0 | 0 | 15 | 55 | 35 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 274 |  | 107.5%
| d | Pier 1900 mm | 0 | cum | 307 | 320.6 | -13.6 | 0 | 0 | 12 | 110.6 | 72 | 0 | 0 | 18 | 48 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 320.6 |  | 104.4%
| e | Pier 1600 mm | 0 | cum | 160 | 160 | 0 | 0 | 0 | 0 | 25 | 25 | 0 | 4 | 28 | 0 | 42 | 18 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 |  | 100%
| f | Pier Cap | 0 | cum | 818 | 784 | 34 | 0 | 0 | 0 | 0 | 14 | 40 | 55 | 77 | 100 | 180 | 251 | 32 | 0 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 784 |  | 95.84%
| g | Track Beam with Nose | 0 | cum | 986 | 1008 | -22 | 0 | 0 | 0 | 0 | 0 | 12 | 120 | 168 | 468 | 216 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008 |  | 102.2%
| h | Track Beam without Nose | 0 | cum | 1002 | 1008 | -6 | 0 | 0 | 0 | 0 | 60 | 228 | 228 | 480 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1008 |  | 100.6%
| i | h - Section Beam | 0 | cum | 432 | 408 | 24 | 0 | 0 | 0 | 0 | 0 | 36 | 48 | 36 | 144 | 24 | 12 | 108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 408 |  | 94.44%
| j | U - Section Beam | 0 | cum | 471 | 540 | -69 | 0 | 0 | 0 | 0 | 0 | 48 | 156 | 216 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 540 |  | 114.6%
| k | Pre-cast Slab | 0 | cum | 52 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5 | 17.5 | 22 | 0 | 0 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 |  | 96.15%
6.593% | 5 | E | 36 |  | 4421 | 1865 | 2556 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 299 | 90 | 58 | 47 | 22 | 16 | 0 | 0 | 36 | 346 | 144 | 462 | 0 | 0 | 0 | 0 | 1865 | 0 | 42.19% |  | 877
| a | PCC | 0 | cum | 113 | 91 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 39 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44 | 0 | 0 | 0 | 0 | 91 |  | 80.53%
| b | RCC Foundation | 0 | cum | 732 | 540 | 192 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 140 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 160 | 0 | 0 | 0 | 0 | 540 |  | 73.77%
| c | Step Footing | 0 | cum | 179 | 135 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 55 | 10 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 0 | 0 | 0 | 0 | 135 |  | 75.42%
| d | Pier 1900 mm | 0 | cum | 216 | 126 | 90 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 54 | 0 | 18 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 126 |  | 58.33%
| e | Pier 1600 mm | 0 | cum | 426 | 142 | 284 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 20 | 35 | 41 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 142 |  | 33.33%
| f | Pier Cap | 0 | cum | 590 | 137 | 453 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 0 | 67 | 0 | 0 | 0 | 0 | 137 |  | 23.22%
| g | Track Beam with Nose | 0 | cum | 847 | 202 | 645 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 12 | 0 | 0 | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 36 | 72 | 0 | 0 | 0 | 0 | 202 |  | 23.85%
| h | Track Beam without Nose | 0 | cum | 467 | 432 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 264 | 108 | 24 | 0 | 0 | 0 | 0 | 432 |  | 92.51%
| i | h - Section Beam | 0 | cum | 449 | 48 | 401 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 0 | 0 | 0 | 0 | 48 |  | 10.69%
| j | U - Section Beam | 0 | cum | 402 | 12 | 390 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 |  | 2.985%
| k | Pre-cast Slab | 0 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | #DIV/0!
5.495% | 6 | F | 30 |  | 3578 | 3712.5 | -132.5 | 0 | 691 | 310 | 0 | 0 | 76 | 56 | 0 | 168 | 72 | 36 | 48 | 40 | 111 | 82 | 228 | 356.5 | 868 | 375.5 | 218.5 | 0 | 0 | 0 | 0 | 0 | 0 | 3736.5 | -24 | 104.4% |  | 2274.5
| a | PCC | 0 | cum | 89 | 94 | -5 | 0 | 94 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 |  | 105.6%
| b | RCC Foundation | 0 | cum | 578 | 596 | -18 | 0 | 456 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 596 |  | 103.1%
| c | Step Footing | 0 | cum | 142 | 122 | 20 | 0 | 81 | 41 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 122 |  | 85.92%
| d | Pier 1900 mm | 0 | cum | 171 | 179 | -8 | 0 | 60 | 119 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 179 |  | 104.7%
| e | Pier 1600 mm | 0 | cum | 519 | 465.5 | 53.5 | 0 | 0 | 10 | 0 | 0 | 76 | 56 | 0 | 0 | 0 | 0 | 0 | 40 | 39 | 34 | 36 | 77.5 | 93 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465.5 |  | 89.69%
| f | Pier Cap | 0 | cum | 481 | 554 | -73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 212 | 255 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 554 |  | 115.2%
| g | Track Beam with Nose | 0 | cum | 412 | 432 | -20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 0 | 0 | 0 | 60 | 96 | 168 | 36 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 444 |  | 107.8%
| h | Track Beam without Nose | 0 | cum | 807 | 864 | -57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 48 | 0 | 0 | 0 | 12 | 48 | 132 | 48 | 300 | 36 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 864 |  | 107.1%
| i | h - Section Beam | 0 | cum | 212 | 204 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 108 | 48 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 216 |  | 101.9%
| j | U - Section Beam | 0 | cum | 147 | 180 | -33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48 | 24 | 0 | 12 | 0 | 36 | 0 | 0 | 0 | 36 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 180 |  | 122.4%
| k | Pre-cast Slab | 0 | cum | 20 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 8.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 22 |  | 110%
10.99% | 7 | G | 60 |  | 5757 | 4929 | 797 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 228 | 416 | 760 | 223 | 126 | 189 | 508 | 252 | 124 | 771 | 298 | 450 | 390 | 0 | 0 | 0 | 0 | 4929 | 0 | 85.62% |  | 2896
| a | PCC | 0 | cum | 199 | 295 | -96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 22 | 37 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 39 | 30 | 0 | 0 | 0 | 0 | 295 |  | 148.2%
| b | RCC Foundation | 0 | cum | 1273 | 1750 | -477 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 120 | 256 | 416 | 54 | 0 | 0 | 0 | 0 | 0 | 109 | 79 | 325 | 266 | 0 | 0 | 0 | 0 | 1750 |  | 137.5%
| c | Step Footing | 0 | cum | 292 | 288 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 50 | 45 | 65 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 30 | 33 | 0 | 0 | 0 | 0 | 288 |  | 98.63%
| d | Pier 1900 mm | 0 | cum | 516 | 553 | -37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 78 | 132 | 144 | 35 | 0 | 0 | 0 | 0 | 0 | 48 | 36 | 44 | 0 | 0 | 0 | 0 | 553 |  | 107.2%
| e | Pier 1600 mm | 0 | cum | 678 | 355 | 323 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 15 | 90 | 72 | 62 | 0 | 0 | 19 | 19 | 8 | 5 | 0 | 0 | 0 | 0 | 355 |  | 52.36%
| f | Pier Cap | 0 | cum | 676 | 352 | 324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 243 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 352 |  | 52.07%
| g | Track Beam with Nose | 0 | cum | 709 | 418 | 291 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 70 | 60 | 48 | 12 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 418 |  | 58.96%
| h | Track Beam without Nose | 0 | cum | 665 | 623 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 384 | 132 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 623 |  | 93.68%
| i | h - Section Beam | 0 | cum | 478 | 144 | 334 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 48 | 36 | 12 | 12 | 0 | 0 | 0 | 0 | 144 |  | 30.13%
| j | U - Section Beam | 0 | cum | 233 | 144 | 89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 36 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 144 |  | 61.8%
| k | Pre-cast Slab | 0 | cum | 38 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 |  | 18.42%
9.158% | 8 | H | 50 |  | 5148 | 5098.5 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 628 | 566 | 318 | 230 | 613 | 358 | 573.5 | 952 | 117 | 192 | 84 | 180 | 16 | 82 | 36 | 153 | 0 | 0 | 0 | 0 | 5098.5 | 0 | 99.04% |  | 4631.5
| a | PCC | 0 | cum | 134 | 182 | -48 | 0 | 0 | 0 | 0 | 0 | 0 | 81 | 44 | 0 | 14 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 182 |  | 135.8%
| b | RCC Foundation | 0 | cum | 875 | 980 | -105 | 0 | 0 | 0 | 0 | 0 | 0 | 357 | 342 | 60 | 80 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 45 | 0 | 50 | 0 | 0 | 0 | 0 | 980 |  | 112%
| c | Step Footing | 0 | cum | 238 | 265 | -27 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 75 | 41 | 20 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 12 | 0 | 0 | 0 | 0 | 265 |  | 111.3%
| d | Pier 1900 mm | 0 | cum | 284 | 340 | -56 | 0 | 0 | 0 | 0 | 0 | 0 | 90 | 93 | 97 | 30 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 12 | 0 | 0 | 0 | 0 | 340 |  | 119.7%
| e | Pier 1600 mm | 0 | cum | 293 | 276 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 86 | 45 | 20 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 276 |  | 94.2%
| f | Pier Cap | 0 | cum | 685 | 670 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 194 | 343 | 35 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 670 |  | 97.81%
| g | Track Beam with Nose | 0 | cum | 589 | 552 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 156 | 96 | 156 | 0 | 36 | 36 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 552 |  | 93.72%
| h | Track Beam without Nose | 0 | cum | 1334 | 1258 | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 168 | 228 | 252 | 70 | 12 | 12 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1258 |  | 94.3%
| i | h - Section Beam | 0 | cum | 495 | 336 | 159 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 132 | 0 | 0 | 12 | 48 | 0 | 12 | 36 | 72 | 0 | 0 | 0 | 0 | 336 |  | 67.88%
| j | U - Section Beam | 0 | cum | 203 | 228 | -25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 60 | 12 | 60 | 24 | 36 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 228 |  | 112.3%
| k | Pre-cast Slab | 0 | cum | 18 | 11.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5 |  | 63.89%
10.07% | 9 | I | 55 |  | 5891 | 6473 | -589 | 0 | 0 | 0 | 9 | 586 | 578 | 413 | 178 | 463 | 791 | 1223 | 833.5 | 621.5 | 0 | 12 | 0 | 48 | 288 | 264.5 | 140 | 48.5 | 12 | 0 | 0 | 0 | 0 | 6509 | -36 | 110.5% |  | 5756
| a | PCC | 0 | cum | 132 | 177 | -45 | 0 | 0 | 0 | 9 | 64 | 46 | 37 | 0 | 5 | 3 | 10 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177 |  | 134.1%
| b | RCC Foundation | 0 | cum | 860 | 1098 | -238 | 0 | 0 | 0 | 0 | 350 | 354 | 250 | 0 | 40 | 0 | 84 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1098 |  | 127.7%
| c | Step Footing | 0 | cum | 226 | 286 | -60 | 0 | 0 | 0 | 0 | 88 | 94 | 72 | 0 | 10 | 0 | 17 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 286 |  | 126.5%
| d | Pier 1900 mm | 0 | cum | 312 | 312 | 0 | 0 | 0 | 0 | 0 | 84 | 84 | 42 | 0 | 72 | 0 | 24 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 312 |  | 100%
| e | Pier 1600 mm | 0 | cum | 455 | 455 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 136 | 58 | 110 | 52 | 52 | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455 |  | 100%
| f | Pier Cap | 0 | cum | 820 | 855 | -35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 42 | 134 | 78 | 124 | 217 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 855 |  | 104.3%
| g | Track Beam with Nose | 0 | cum | 866 | 996 | -130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 456 | 168 | 84 | 0 | 0 | 0 | 48 | 144 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 996 |  | 115%
| h | Track Beam without Nose | 0 | cum | 1362 | 1371 | -9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 | 351 | 156 | 348 | 216 | 0 | 0 | 0 | 0 | 108 | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1407 |  | 103.3%
| i | h - Section Beam | 0 | cum | 470 | 447.5 | 22.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 135.5 | 144 | 12 | 24 | 0 | 12 | 0 | 0 | 12 | 0 | 60 | 36 | 12 | 0 | 0 | 0 | 0 | 447.5 |  | 95.21%
| j | U - Section Beam | 0 | cum | 367 | 461.5 | -94.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 113.5 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 84 | 72 | 12 | 0 | 0 | 0 | 0 | 0 | 461.5 |  | 125.7%
| k | Pre-cast Slab | 0 | cum | 21 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0.5 | 8 | 0.5 | 0 | 0 | 0 | 0 | 0 | 14 |  | 66.67%
7.875% | 10 | J | 43 |  | 4913 | 3950.5 | 933.5 | 0 | 0 | 0 | 0 | 114 | 321 | 0 | 0 | 816 | 246 | 60 | 84 | 262 | 168 | 0 | 36 | 238.5 | 447 | 168 | 381 | 520 | 89 | 0 | 0 | 0 | 0 | 3950.5 | 0 | 80.41% |  | 2345.5
| a | PCC | 0 | cum | 122 | 126 | -4 | 0 | 0 | 0 | 0 | 39 | 6 | 0 | 0 | 67 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 126 |  | 103.3%
| b | RCC Foundation | 0 | cum | 794 | 810 | -16 | 0 | 0 | 0 | 0 | 60 | 188 | 0 | 0 | 485 | 77 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 810 |  | 102%
| c | Step Footing | 0 | cum | 207 | 206 | 1 | 0 | 0 | 0 | 0 | 15 | 49 | 0 | 0 | 119 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 206 |  | 99.52%
| d | Pier 1900 mm | 0 | cum | 250 | 253 | -3 | 0 | 0 | 0 | 0 | 0 | 78 | 0 | 0 | 145 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 253 |  | 101.2%
| e | Pier 1600 mm | 0 | cum | 650 | 656.5 | -6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | 0 | 250 | 156 | 0 | 0 | 70.5 | 0 | 120 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 656.5 |  | 101%
| f | Pier Cap | 0 | cum | 681 | 519 | 162 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 147 | 0 | 171 | 136 | 65 | 0 | 0 | 0 | 0 | 519 |  | 76.21%
| g | Track Beam with Nose | 0 | cum | 818 | 516 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 36 | 48 | 96 | 0 | 132 | 156 | 24 | 0 | 0 | 0 | 0 | 516 |  | 63.08%
| h | Track Beam without Nose | 0 | cum | 689 | 660 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 36 | 0 | 12 | 0 | 0 | 0 | 60 | 168 | 36 | 48 | 228 | 0 | 0 | 0 | 0 | 0 | 660 |  | 95.79%
| i | h - Section Beam | 0 | cum | 284 | 60 | 224 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 |  | 21.13%
| j | U - Section Beam | 0 | cum | 389 | 144 | 245 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 60 | 0 | 12 | 0 | 0 | 36 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 144 |  | 37.02%
| k | Pre-cast Slab | 0 | cum | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0%
20.15% | 11 | K | 110 |  | 12470 | 9044.5 | 3425.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 202 | 156 | 21 | 390 | 469 | 464 | 369 | 1192 | 1255 | 660 | 994.5 | 846 | 1121 | 587 | 0 | 0 | 0 | 0 | 9056.5 | -12 | 72.63% |  | 4848
| a | PCC | 0 | cum | 355 | 322 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 47 | 10 | 0 | 3 | 35 | 0 | 0 | 6 | 95 | 34 | 22 | 50 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 322
| b | RCC Foundation | 0 | cum | 1854 | 2067 | -213 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 246 | 88 | 0 | 0 | 275 | 0 | 0 | 0 | 613 | 222 | 55 | 348 | 165 | 55 | 0 | 0 | 0 | 0 | 0 | 2067
| c | Step Footing | 0 | cum | 495 | 540 | -45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 32 | 0 | 0 | 56 | 13 | 0 | 0 | 90 | 80 | 70 | 101 | 46 | 15 | 0 | 0 | 0 | 0 | 0 | 540
| d | Pier 1900 mm | 0 | cum | 601 | 660 | -59 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 18 | 12 | 0 | 120 | 18 | 84 | 108 | 72 | 66 | 42 | 60 | 0 | 0 | 0 | 0 | 0 | 660
| e | Pier 1600 mm | 0 | cum | 1663 | 1589 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 56 | 0 | 190 | 79 | 345 | 224 | 87 | 381 | 167 | 0 | 0 | 0 | 0 | 1589
| f | Pier Cap | 0 | cum | 1840 | 328 | 1512 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 198 | 130 | 0 | 0 | 0 | 0 | 0 | 328
| g | Track Beam with Nose | 0 | cum | 1631 | 1372 | 259 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 180 | 96 | 172 | 60 | 84 | 0 | 168 | 168 | 288 | 168 | 0 | 0 | 0 | 0 | 1384
| h | Track Beam without Nose | 0 | cum | 2323 | 1941 | 382 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 96 | 0 | 12 | 216 | 120 | 129 | 60 | 648 | 96 | 24 | 108 | 180 | 180 | 0 | 0 | 0 | 0 | 1941
| i | h - Section Beam | 0 | cum | 463 | 36 | 427 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 36
| j | U - Section Beam | 0 | cum | 1186 | 180 | 1006 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72 | 36 | 0 | 0 | 0 | 12 | 12 | 12 | 36 | 0 | 0 | 0 | 0 | 180
| k | Pre-cast Slab | 0 | cum | 59 | 9.5 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5
| 12 | Abutment wall- PART-A | 0 |  | 491 | 673 | -182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 49 | 53 | 224 | 82 | 0 | 0 | 0 | 0 | 673 |  |  |  | 0
| 13 | Abutment wall- PART-D | 0 |  | 830 | 595 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 559 | 0 | 0 | 0 | 0 | 0 | 0 | 595 |  |  |  | 0
| 14 | Cast In-situ slab- 1- PART-G | 0 |  | 471 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 15 | Cast In-situ slab- 2- PART-G | 0 |  | 1141 | 0 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
| 16 | Cast In-situ slab- PART-C | 0 |  | 650 | 862 | -212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 844 | 0 | 0 | 0 | 0 | 0 | 862 |  |  |  | 0
|  | Actual Total: | 546 |  | 62550 | 54003.85 | 8441.15 | 21 | 955 | 754 | 952.35 | 1023 | 1439.7 | 2085 | 2807 | 3981 | 3145 | 3197.5 | 3483 | 3252 | 2981.5 | 1620 | 2934.5 | 2693 | 3217 | 3606.5 | 3895.5 | 4067.5 | 1977.5 |  |  |  |  | 54088.55
|  |  | Upto Feb-22 |  | PCC | 600
[5 empty] | Total | 54603.85 | [9 empty] | 1748.8833 | 2393.9938 | 3083.0643 | 3847.075 | 4809.29 | 6056.9875 | 4171.825 | 3901.4083 | 3578.7417 | 5099.1125
[16 empty] | 15739.95 | 19151.95 | 21581.45 | 23082.45 | 24046.45 | 24227.95 | 25030.95 | 23408.45 | 21472.45 | 20396.45
[7 empty] | Quantity | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
[7 empty] | Plan | 325 | 605 | 950 | 1775 | 3120 | 4343 | 5521 | 6321 | 6798 | 6557 | 5627 | 4984 | 4216 | 3163 | 2423 | 1312 | 757 | 2141 | 1612 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Cum Plan | 325 | 930 | 1880 | 3655 | 6775 | 11118 | 16639 | 22960 | 29758 | 36315 | 41942 | 46926 | 51142 | 54305 | 56728 | 58040 | 58797 | 60938 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550
[7 empty] | Actual | 21 | 955 | 754 | 952.35 | 1023 | 1439.7 | 2085 | 2807 | 3981 | 3145 | 3197.5 | 3483 | 3252 | 2981.5 | 1620 | 2934.5 | 2693 | 3217 | 3606.5 | 3895.5 | 4067.5 | 1977.5
[7 empty] | Cum Actual | 21 | 976 | 1730 | 2682.35 | 3705.35 | 5145.05 | 7230.05 | 10037.05 | 14018.05 | 17163.05 | 20360.55 | 23843.55 | 27095.55 | 30077.05 | 31697.05 | 34631.55 | 37324.55 | 40541.55 | 44148.05 | 48043.55 | 52111.05 | 54088.55
[7 empty] | Revised Plan |  | 2023-03-01: 3252; 2023-04-01: 2982; 2023-05-01: 1620; 2023-06-01: 2935; 2023-07-01: 2693; 2023-08-01: 3216; 2023-09-01: 4639; 2023-10-01: 5099.1125; 2023-11-01: 5099.1125; 2023-12-01: 7171.225; 2024-01-01: 0; 2024-02-01: 0; 2024-03-01: 0; 2024-04-01: 0
[7 empty] | Revised Cum Plan |  | 2023-03-01: 27095.55; 2023-04-01: 30077.55; 2023-05-01: 31697.55; 2023-06-01: 34632.55; 2023-07-01: 37325.55; 2023-08-01: 40541.55; 2023-09-01: 45180.55; 2023-10-01: 50279.6625; 2023-11-01: 55378.775; 2023-12-01: 62550; 2024-01-01: 62550; 2024-02-01: 62550; 2024-03-01: 62550; 2024-04-01: 62550
[20 empty] | 3135.7857 |  |  | -23407.45
[7 empty] | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
[7 empty] | Plan | 0.51958 | 0.96723 | 1.5188 | 2.8377 | 4.988 | 6.9432 | 8.8265 | 10.1055 | 10.8681 | 10.4828 | 8.996 | 7.968 | 6.7402 | 5.0568 | 3.8737 | 2.0975 | 1.2102 | 3.4229 | 2.5771 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Cum Plan | 0.51958 | 1.4868 | 3.0056 | 5.8433 | 10.8313 | 17.7746 | 26.6011 | 36.7066 | 47.5747 | 58.0576 | 67.0536 | 75.0216 | 81.7618 | 86.8185 | 90.6922 | 92.7898 | 94 | 97.4229 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[7 empty] | Actual | 0.033573 | 1.5268 | 1.2054 | 1.5225 | 1.6355 | 2.3017 | 3.3333 | 4.4876 | 6.3645 | 5.028 | 5.1119 | 5.5683 | 5.199 | 4.7666 | 2.5899 | 4.6914 | 4.3054 | 5.1431 | 5.7658 | 6.2278 | 6.5028 | 3.1615
[7 empty] | Cum Actual | 0.033573 | 1.5604 | 2.7658 | 4.2883 | 5.9238 | 8.2255 | 11.5588 | 16.0464 | 22.411 | 27.4389 | 32.5508 | 38.1192 | 43.3182 | 48.0848 | 50.6747 | 55.3662 | 59.6715 | 64.8146 | 70.5804 | 76.8082 | 83.311 | 86.4725
Plan
| # | Activity | Total Footings (nos.) |  | Concreting Scope (cum) | Completed Till Date (cum) | Balance (cum) | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
| 1 | PCC |  |  | 1655 | 1840 | -185 | 65 | 75 | 130 | 205 | 215 | 233 | 202 | 174 | 127 | 78 | 60 | 51 | 25 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 1655
| 2 | RCC Foundation |  |  | 10211 | 11022.75 | -811.75 | 230 | 430 | 580 | 1080 | 1220 | 1280 | 1249 | 1130 | 1079 | 654 | 392 | 313 | 200 | 200 | 174 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 10211
| 3 | Step Footing |  |  | 2550 | 2606 | -56 | 30 | 90 | 130 | 165 | 280 | 300 | 342 | 305 | 268 | 237 | 144 | 100 | 84 | 50 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 2550
| 4 | Pier 1900 mm |  |  | 3270 | 3343.6 | -73.6 | 0 | 10 | 90 | 160 | 290 | 335 | 403 | 414 | 403 | 360 | 288 | 183 | 137 | 101 | 50 | 46 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 3270
| 5 | Pier 1600 mm |  |  | 5546 | 4672 | 874 | 0 | 0 | 20 | 125 | 325 | 475 | 610 | 683 | 684 | 750 | 576 | 494 | 341 | 190 | 170 | 53 | 50 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 5546
| 6 | Pier Cap |  |  | 8075 | 5660 | 2415 | 0 | 0 | 0 | 40 | 480 | 635 | 905 | 1045 | 1066 | 1000 | 821 | 700 | 583 | 311 | 263 | 156 | 70 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 8075
| 7 | Track Beam with Nose |  |  | 8981 | 7692 | 1289 | 0 | 0 | 0 | 0 | 170 | 480 | 765 | 1030 | 1160 | 1165 | 1057 | 945 | 854 | 563 | 445 | 225 | 122 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 8981
| 8 | Track Beam without Nose |  |  | 9585 | 9069 | 516 | 0 | 0 | 0 | 0 | 140 | 500 | 820 | 990 | 1215 | 1305 | 1136 | 960 | 790 | 691 | 546 | 317 | 175 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9585
| 9 | h - Section Beam |  |  | 4483 | 2875.5 | 1607.5 | 0 | 0 | 0 | 0 | 0 | 85 | 120 | 285 | 425 | 515 | 575 | 620 | 650 | 500 | 322 | 203 | 118 | 65 | 0 | 0 | 0 | 0 | [5 empty] | 4418
| 10 | U - Section Beam |  |  | 4260 | 2896.5 | 1363.5 | 0 | 0 | 0 | 0 | 0 | 20 | 105 | 250 | 346 | 456 | 528 | 565 | 505 | 498 | 399 | 291 | 203 | 94 | 0 | 0 | 0 | 0 | [5 empty] | 4166
| 11 | Pre-cast Slab |  |  | 351 | 196.5 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 25 | 37 | 50 | 53 | 47 | 44 | 29 | 21 | 19 | 11 | 0 | 0 | 0 | 0 | [5 empty] | 340
| 12 | Abutment wall- PART-A |  |  | 491 | 673 | -182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491 | 0 | 0 | 0 | 0
| 13 | Abutment wall- PART-D |  |  | 830 | 595 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 0 | 0 | 0 | 0
| 14 | Cast In-situ slab- 1- PART-G |  |  | 471 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0
| 15 | Cast In-situ slab- 2- PART-G |  |  | 1141 | 0 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 0 | 0 | 0
| 16 | Cast In-situ slab- PART-C |  |  | 650 | 862 | -212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0
|  | Planned Total: |  |  | 62550 | 54003.85 | 8441.15 | 325 | 605 | 950 | 1775 | 3120 | 4343 | 5521 | 6321 | 6798 | 6557 | 5627 | 4984 | 4216 | 3163 | 2423 | 1312 | 757 | 2141 | 1612 | 0 | 0 | 0
Actual
| # | Activity | Total Footings (nos.) |  | Concreting Scope (cum) | Completed Till Date (cum) | Balance (cum) | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
| 1 | PCC |  |  | 1655 | 1840 | -185 | 21 | 102 | 93 | 51 | 103 | 64 | 211 | 108 | 217 | 120 | 100 | 138 | 15 | 0 | 12 | 95 | 34 | 22 | 130 | 56 | 39 | 109 | [5 empty] | 1840
| 2 | RCC Foundation |  |  | 10211 | 11022.75 | -811.75 | 0 | 616 | 398 | 553.75 | 450 | 542 | 787 | 1006 | 1098 | 617 | 626 | 771 | 208 | 398 | 40 | 613 | 222 | 55 | 677 | 469 | 400 | 476 | [5 empty] | 11022.75
| 3 | Step Footing |  |  | 2550 | 2606 | -56 | 0 | 129 | 98 | 151 | 103 | 143 | 204 | 230 | 267 | 163 | 164 | 136 | 73 | 60 | 16 | 90 | 80 | 70 | 146 | 153 | 50 | 80 | [5 empty] | 2606
| 4 | Pier 1900 mm |  |  | 3270 | 3343.6 | -73.6 | 0 | 108 | 131 | 171.6 | 156 | 162.7 | 132 | 234 | 410 | 282 | 186 | 174 | 198 | 227 | 62 | 84 | 108 | 72 | 90 | 180 | 108 | 68 | [5 empty] | 3344.3
| 5 | Pier 1600 mm |  |  | 5546 | 4672 | 874 | 0 | 0 | 34 | 25 | 59 | 89 | 72 | 172 | 185 | 268 | 145 | 267 | 508 | 382 | 249 | 364 | 227 | 466 | 367 | 176 | 445 | 172 | [5 empty] | 4672
| 6 | Pier Cap |  |  | 8075 | 5660 | 2415 | 0 | 0 | 0 | 0 | 68 | 91 | 127 | 145 | 328 | 258 | 375 | 384 | 481 | 426 | 292 | 239 | 233 | 433 | 498 | 617 | 469 | 196 | [5 empty] | 5660
| 7 | Track Beam with Nose |  |  | 8981 | 7692 | 1289 | 0 | 0 | 0 | 0 | 0 | 36 | 120 | 180 | 468 | 457 | 528 | 599 | 672 | 588 | 372 | 492 | 408 | 612 | 924 | 516 | 492 | 264 | [5 empty] | 7728
| 8 | Track Beam without Nose |  |  | 9585 | 9069 | 516 | 0 | 0 | 0 | 0 | 60 | 228 | 228 | 480 | 612 | 627 | 672 | 528 | 768 | 492 | 294 | 588 | 972 | 768 | 444 | 624 | 516 | 204 | [5 empty] | 9105
| 9 | h - Section Beam |  |  | 4483 | 2875.5 | 1607.5 | 0 | 0 | 0 | 0 | 0 | 36 | 48 | 36 | 144 | 159.5 | 204 | 215 | 144 | 192 | 209 | 240 | 276 | 204 | 72 | 168 | 252 | 288 | [5 empty] | 2887.5
| 10 | U - Section Beam |  |  | 4260 | 2896.5 | 1363.5 | 0 | 0 | 0 | 0 | 24 | 48 | 156 | 216 | 252 | 185.5 | 180 | 239 | 156 | 204 | 60 | 120 | 120 | 192 | 168 | 312 | 228 | 36 | [5 empty] | 2896.5
| 11 | Pre-cast Slab |  |  | 351 | 196.5 | 49.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 17.5 | 32 | 29 | 12.5 | 14 | 9.5 | 13 | 22 | 23.5 | 12.5 | 0.5 | 2.5 | [5 empty] | 196.5
| 12 | Abutment wall- PART-A |  |  | 491 | 673 | -182 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 49 | 53 | 224 | 82 | [5 empty] | 673
| 13 | Abutment wall- PART-D |  |  | 830 | 595 | 235 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 559 | 0 | 0 | [5 empty] | 595
| 14 | Cast In-situ slab- 1- PART-G |  |  | 471 | 0 | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
| 15 | Cast In-situ slab- 2- PART-G |  |  | 1141 | 0 | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0
| 16 | Cast In-situ slab- PART-C |  |  | 650 | 862 | -212 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 844 | 0 | [5 empty] | 862
|  | Planned Total: |  |  | 62550 | 54003.85 | 8441.15 | 21 | 955 | 754 | 952.35 | 1023 | 1439.7 | 2085 | 2807 | 3981 | 3145 | 3197.5 | 3483 | 3252 | 2981.5 | 1620 | 2934.5 | 2693 | 3217 | 3606.5 | 3895.5 | 4067.5 | 1977.5 |  |  |  |  | 0 | 54088.55
[7 empty] | Plan | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
[6 empty] | 0 | A | 60 | 100 | 150 | 180 | 225 | 330 | 410 | 473 | 490 | 449 | 385 | 274 | 212 | 129 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | B | 80 | 115 | 165 | 230 | 345 | 403 | 404 | 423 | 329 | 225 | 207 | 82 | 68 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | C | 15 | 160 | 165 | 200 | 270 | 420 | 470 | 488 | 516 | 442 | 357 | 279 | 220 | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 36 | D | 80 | 115 | 135 | 160 | 385 | 440 | 520 | 620 | 722 | 641 | 458 | 402 | 326 | 244 | 256 | 111 | 53 | 36 | 0 | 0 | 0 | 0
[6 empty] | 0 | E | 0 | 0 | 60 | 90 | 105 | 200 | 305 | 520 | 560 | 573 | 566 | 451 | 371 | 255 | 264 | 101 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | F | 0 | 0 | 0 | 115 | 235 | 375 | 435 | 465 | 526 | 426 | 293 | 292 | 230 | 156 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | G | 0 | 0 | 0 | 190 | 275 | 350 | 398 | 415 | 560 | 632 | 644 | 668 | 535 | 457 | 344 | 224 | 65 | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | H | 90 | 115 | 175 | 220 | 300 | 460 | 524 | 580 | 628 | 582 | 454 | 392 | 339 | 217 | 72 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 60 | I | 0 | 0 | 90 | 185 | 285 | 445 | 560 | 557 | 535 | 566 | 520 | 498 | 459 | 374 | 336 | 265 | 156 | 60 | 0 | 0 | 0 | 0
[6 empty] | 0 | J | 0 | 0 | 0 | 110 | 320 | 470 | 570 | 640 | 692 | 571 | 383 | 366 | 316 | 237 | 181 | 57 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | 74 | K | 0 | 0 | 10 | 95 | 375 | 450 | 925 | 1140 | 1240 | 1450 | 1360 | 1280 | 1140 | 990 | 904 | 554 | 483 | 74 | 0 | 0 | 0 | 0
[6 empty] | 491 | Abutment wall- PART-A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491 | 0 | 0 | 0 | 0
[6 empty] | 830 | Abutment wall- PART-D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 0 | 0 | 0 | 0
[6 empty] | 471 | Cast In-situ slab- 1- PART-G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0
[6 empty] | 1141 | Cast In-situ slab- 2- PART-G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 0 | 0 | 0
[6 empty] | 650 | Cast In-situ slab- PART-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 0 | 0 | 0 | 0
3753
[7 empty] | Actual | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
[7 empty] | A |  | 264 | 24 | 0 | 92 | 29.7 | 114 | 216 | 161 | 14.5 | 140 | 502.5 | 717 | 427.5 | 369.5 | 564.5 | 0 | 4.5 | 195 | 125 | 0 | 2.5
[7 empty] | B | 0 | 0 | 29 | 313.75 | 20 | 59 | 44 | 14 | 288 | 277 | 24 | 91 | 144 | 396 | 167.5 | 143.5 | 97 | 37 | 146 | 425 | 296 | 110
[7 empty] | C | 0 | 0 | 0 | 0 | 0 | 12 | 150 | 465 | 133 | 81 | 43 | 164 | 116 | 255 | 292 | 52 | 362 | 305 | 573 | 422 | 384 | 72
[7 empty] | D | 0 | 0 | 391 | 629.6 | 211 | 364 | 680 | 1038 | 1238 | 704.5 | 322.5 | 162 | 28 | 35 | 0 | 2.5 | 0 | 2.5 | 0 | 0 | 0 | 18
[7 empty] | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345 | 299 | 90 | 58 | 47 | 22 | 16 | 0 | 0 | 36 | 346 | 144 | 462
[7 empty] | F | 0 | 691 | 310 | 0 | 0 | 76 | 56 | 0 | 168 | 72 | 36 | 48 | 40 | 111 | 82 | 228 | 356.5 | 868 | 375.5 | 218.5 | 0 | 0
[7 empty] | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 194 | 228 | 416 | 760 | 223 | 126 | 189 | 508 | 252 | 124 | 771 | 298 | 450 | 390
[7 empty] | H | 0 | 0 | 0 | 0 | 0 | 0 | 628 | 566 | 318 | 230 | 613 | 358 | 573.5 | 952 | 117 | 192 | 84 | 180 | 16 | 82 | 36 | 153
[7 empty] | I | 0 | 0 | 0 | 9 | 586 | 578 | 413 | 178 | 463 | 791 | 1223 | 833.5 | 621.5 | 0 | 12 | 0 | 48 | 288 | 264.5 | 140 | 48.5 | 12
[7 empty] | J | 0 | 0 | 0 | 0 | 114 | 321 | 0 | 0 | 816 | 246 | 60 | 84 | 262 | 168 | 0 | 36 | 238.5 | 447 | 168 | 381 | 520 | 89
[7 empty] | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 330 | 202 | 156 | 21 | 390 | 469 | 464 | 369 | 1192 | 1255 | 660 | 994.5 | 846 | 1121 | 587
[7 empty] | Abutment wall- PART-A | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 265 | 49 | 53 | 224 | 82
[7 empty] | Abutment wall- PART-D | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 559 | 0 | 0
[7 empty] | Cast In-situ slab- 1- PART-G | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Cast In-situ slab- 2- PART-G | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Cast In-situ slab- PART-C | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 844 | 0
[7 empty] | Difference | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
[6 empty] | 266.8 | A | 60 | -164 | 126 | 180 | 133 | 300.3 | 296 | 257 | 329 | 434.5 | 245 | -228.5 | -505 | -298.5 | -333.5 | -564.5 | 0 | -4.5 | -195 | -125 | 0 | -2.5
[6 empty] | 1017.25 | B | 80 | 115 | 136 | -83.75 | 325 | 344 | 360 | 409 | 41 | -52 | 183 | -9 | -76 | -347 | -167.5 | -143.5 | -97 | -37 | -146 | -425 | -296 | -110
[6 empty] | 1932 | C | 15 | 160 | 165 | 200 | 270 | 408 | 320 | 23 | 383 | 361 | 314 | 115 | 104 | -200 | -292 | -52 | -362 | -305 | -573 | -422 | -384 | -72
[6 empty] | -138.1 | D | 80 | 115 | -256 | -469.6 | 174 | 76 | -160 | -418 | -516 | -63.5 | 135.5 | 240 | 298 | 209 | 256 | 108.5 | 53 | 33.5 | 0 | 0 | 0 | -18
[6 empty] | 3544 | E | 0 | 0 | 60 | 90 | 105 | 200 | 305 | 520 | 560 | 228 | 267 | 361 | 313 | 208 | 242 | 85 | 0 | 0 | -36 | -346 | -144 | -462
[6 empty] | 1303.5 | F | 0 | -691 | -310 | 115 | 235 | 299 | 379 | 465 | 358 | 354 | 257 | 244 | 190 | 45 | -52 | -228 | -356.5 | -868 | -375.5 | -218.5 | 0 | 0
[6 empty] | 2861 | G | 0 | 0 | 0 | 190 | 275 | 350 | 398 | 415 | 366 | 404 | 228 | -92 | 312 | 331 | 155 | -284 | -187 | -124 | -771 | -298 | -450 | -390
[6 empty] | 516.5 | H | 90 | 115 | 175 | 220 | 300 | 460 | -104 | 14 | 310 | 352 | -159 | 34 | -234.5 | -735 | -45 | -192 | -84 | -180 | -16 | -82 | -36 | -153
[6 empty] | 75 | I | 0 | 0 | 90 | 176 | -301 | -133 | 147 | 379 | 72 | -225 | -703 | -335.5 | -162.5 | 374 | 324 | 265 | 108 | -228 | -264.5 | -140 | -48.5 | -12
[6 empty] | 2567.5 | J | 0 | 0 | 0 | 110 | 206 | 149 | 570 | 640 | -124 | 325 | 323 | 282 | 54 | 69 | 181 | 21 | -238.5 | -447 | -168 | -381 | -520 | -89
[6 empty] | 7548 | K | 0 | 0 | 10 | 95 | 375 | 450 | 925 | 810 | 1038 | 1294 | 1339 | 890 | 671 | 526 | 535 | -638 | -772 | -586 | -994.5 | -846 | -1121 | -587
[6 empty] | 0 | Abutment wall- PART-A | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 226 | -49 | -53 | -224 | -82
[6 empty] | 0 | Abutment wall- PART-D | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 794 | 0 | -559 | 0 | 0
[6 empty] | 0 | Cast In-situ slab- 1- PART-G | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 0 | 0 | 0
[6 empty] | 0 | Cast In-situ slab- 2- PART-G | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 0 | 0 | 0
[6 empty] | 0 | Cast In-situ slab- PART-C | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | -18 | 0 | -844 | 0
21493.45
[7 empty] | Balance Distribution | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
[6 empty] | 266.8 | A
[6 empty] | 1017.25 | B
[6 empty] | 1932 | C
[6 empty] | -102.1 | D
[6 empty] | 3544 | E
[6 empty] | 1303.5 | F
[6 empty] | 2861 | G
[6 empty] | 516.5 | H
[6 empty] | 135 | I
[6 empty] | 2567.5 | J
[6 empty] | 7622 | K
[6 empty] | 491 | Abutment wall- PART-A
[6 empty] | 830 | Abutment wall- PART-D
[6 empty] | 471 | Cast In-situ slab- 1- PART-G
[6 empty] | 1141 | Cast In-situ slab- 2- PART-G
[6 empty] | 650 | Cast In-situ slab- PART-C
[6 empty] | 25246.45 | Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[7 empty] | Catch-up | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 |  | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 |  |  |  |  | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
[7 empty] | A | 2023-08-01: 0; 2023-09-01: 20; 2023-10-01: 40; 2023-11-01: 50; 2023-12-01: 75 | [9 empty] | 185 | 81.8
[7 empty] | B | 2023-08-01: 0; 2023-09-01: 100; 2023-10-01: 400; 2023-11-01: 500; 2023-12-01: 448 | [9 empty] | 1448 | -430.75
[7 empty] | C | 2023-08-01: 192; 2023-09-01: 400; 2023-10-01: 150; 2023-11-01: 200; 2023-12-01: 200 |  |  |  |  | 250 | 300 | 228 |  |  | 1920 | 12
[7 empty] | D | 2023-08-01: 0 | [9 empty] | 0 | -102.1
[7 empty] | E | 2023-08-01: 0; 2023-10-01: 500; 2023-11-01: 700; 2023-12-01: 1000 |  |  |  |  | 800 | 558 |  |  |  | 3558 | -14
[7 empty] | F | 2023-08-01: 440; 2023-09-01: 900 | [9 empty] | 1340 | -36.5
[7 empty] | G | 2023-08-01: 1374; 2023-09-01: 300; 2023-10-01: 300; 2023-11-01: 300; 2023-12-01: 352 |  |  |  |  | 250 |  |  |  |  | 2876 | -15
[7 empty] | H | 2023-08-01: 60; 2023-09-01: 120; 2023-10-01: 80; 2023-11-01: 72 | [9 empty] | 332 | 184.5
[7 empty] | I | 2023-08-01: 480 | [9 empty] | 480 | -345
[7 empty] | J | 2023-08-01: 268; 2023-09-01: 600; 2023-10-01: 600; 2023-11-01: 500; 2023-12-01: 488 |  |  |  |  | 100 |  |  |  |  | 2556 | 11.5
[7 empty] | K | 2023-08-01: 462; 2023-09-01: 1000; 2023-10-01: 800; 2023-11-01: 1074; 2023-12-01: 1100 |  |  |  |  | 1600 | 1200 | 500 |  |  | 7736 | -114
[7 empty] | Abutment wall- PART-A | 2023-08-01: 280; 2023-09-01: 100; 2023-10-01: 111 | [9 empty] | 491 | 0
[7 empty] | Abutment wall- PART-D | 2023-08-01: 0; 2023-10-01: 830 | [9 empty] | 830 | 0
[7 empty] | Cast In-situ slab- 1- PART-G | 2023-08-01: 0 | [5 empty] | 471 |  |  |  | 471 | 0
[7 empty] | Cast In-situ slab- 2- PART-G | 2023-08-01: 0 | [5 empty] | 1141 |  |  |  | 1141 | 0
[7 empty] | Cast In-situ slab- PART-C | 2023-08-01: 0; 2023-10-01: 650 | [9 empty] | 650 | 0
[7 empty] | Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3556 | 3540 | 4461 | 3396 | 3663 |  |  |  |  | 3000 | 3670 | 728 | 0 |  | 22431 | -767.55
|  |  | 62550 | 37324.55 | 25225.45

## Weekly update (hidden)
Activity | UoM | Scope | Current Plan FTM Aug'23 (Cum) | Current Plan FTM Aug'23 (Nos) | WEEK-1 |  | WEEK-1 ( Nos) |  |  | WEEK-1 (Cum) |  |  | Reason for Shortfall | 2023-10-31 | 2023-11-08 | 2023-11-16 | 2023-11-24 | 2023-11-30
[15 empty] | W1 | W2 | W3 | W4
[5 empty] | Nos | Cum | Plan | Achieved | Shortfall | Plan | Achieved | Shortfall
Civil | cum | 62550 | 4795 | 440 | 105 | 986 | 105 | 73 | 32 | 986 | 1654.5 | -668.5
PCC | cum | 1655 | 79 | 23 | 5 | 25 | 5 | 0 | 5 | 25 | 0 | 25
RCC Foundation | cum | 10211 | 460 | 23 | 5 | 100 | 5 | 3 | 2 | 100 | 75 | 25
Step Footing | cum | 2550 | 115 | 23 | 5 | 25 | 5 | 2 | 3 | 25 | 15 | 10
Pier 1900 mm | cum | 3270 | 222 | 37 | 10 | 60 | 10 | 10 | 0 | 60 | 60 | 0
Pier 1600 mm | cum | 5546 | 500 | 100 | 25 | 125 | 25 | 12 | 13 | 125 | 57 | 68
Pier Cap | cum | 8075 | 560 | 16 | 2 | 100 | 2 | 1 | 1 | 100 | 65 | 35
Track Beam with Nose | cum | 8981 | 996 | 83 | 20 | 240 | 20 | 13 | 7 | 240 | 156 | 84
Track Beam without Nose | cum | 9585 | 408 | 34 | 5 | 60 | 5 | 15 | -10 | 60 | 180 | -120
h - Section Beam | cum | 4483 | 420 | 35 | 10 | 120 | 10 | 4 | 6 | 120 | 48 | 72
U - Section Beam | cum | 4260 | 276 | 23 | 8 | 96 | 8 | 9 | -1 | 96 | 108 | -12
Pre-cast Slab | cum | 351 | 20 | 40 | 10 | 5 | 10 | 1 | 9 | 5 | 0.5 | 4.5
Abutment wall- PART-A | cum | 491 | 90 | 1 | 0 | 30 | 0 | 1 | -1 | 30 | 46 | -16
Abutment wall- PART-D | cum | 830 | 120 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- 1- PART-G | cum | 471 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- 2- PART-G | cum | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- PART-C | cum | 650 | 0 | 1 | 0 | 0 | 0 | 2 | -2 | 0 | 844 | -844
Pre-cast Segment Erection | nos. | 3004 | 200 | 0 | 34 | 0 | 34 | 29 | 5 | 0 | 0 | 0
Track Beam with Nose | nos. | 783 | 42 | 0 | 8 | 0 | 8 | 13 | -5 | 0 | 0 | 0
Track Beam without Nose | nos. | 811 | 58 | 0 | 10 | 0 | 10 | 15 | -5 | 0 | 0 | 0
h-Section Beam | nos. | 369 | 24 | 0 | 4 | 0 | 4 | 0 | 4 | 0 | 0 | 0
U-Section Beam | nos. | 420 | 22 | 0 | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0
Pre-cast Slab | nos. | 621 | 54 | 0 | 10 | 0 | 10 | 1 | 9 | 0 | 0 | 0
Elevated HMT works | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 | 0 | 0 | 0
Track linking | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75
Activity | UoM | Scope | Current Plan FTM Aug'23 (Cum) | Current Plan FTM Aug'23 (Nos) | WEEK-2 |  | WEEK-2 ( Nos) |  |  | WEEK-2 (Cum) |  |  | Reason for Shortfall | Activity | UoM | Scope | Current Plan FTM Aug'23 (Cum) | Current Plan FTM Aug'23 (Nos) | WEEK-3 |  | WEEK-3 ( Nos) |  |  | WEEK-3 (Cum) |  |  | Reason for Shortfall
[5 empty] | Nos | Cum | Plan | Achieved | Shortfall | Plan | Achieved | Shortfall | [6 empty] | Nos | Cum | Plan | Achieved | Shortfall | Plan | Achieved | Shortfall
Civil | cum | 62550 | 4795 | 440 | 119 | 1160 | 119 | 59 | 60 | 1160 | 585 | 575 |  | Civil | cum | 62550 | 4795 | 440 | 118 | 1104 | 118 | 101 | 17 | 1104 | 953 | 151
PCC | cum | 1655 | 79 | 23 | 10 | 30 | 10 | 0 | 10 | 30 | 0 | 30 |  | PCC | cum | 1655 | 79 | 23 | 8 | 24 | 8 | 7 | 1 | 24 | 39 | -15
RCC Foundation | cum | 10211 | 460 | 23 | 10 | 200 | 10 | 1 | 9 | 200 | 45 | 155 |  | RCC Foundation | cum | 10211 | 460 | 23 | 8 | 100 | 8 | 5 | 3 | 100 | 167 | -67
Step Footing | cum | 2550 | 115 | 23 | 10 | 50 | 10 | 1 | 9 | 50 | 5 | 45 |  | Step Footing | cum | 2550 | 115 | 23 | 8 | 40 | 8 | 2 | 6 | 40 | 10 | 30
Pier 1900 mm | cum | 3270 | 222 | 37 | 10 | 60 | 10 | 2 | 8 | 60 | 12 | 48 |  | Pier 1900 mm | cum | 3270 | 222 | 37 | 10 | 60 | 10 | 5 | 5 | 60 | 30 | 30
Pier 1600 mm | cum | 5546 | 500 | 100 | 25 | 125 | 25 | 25 | 0 | 125 | 121 | 4 |  | Pier 1600 mm | cum | 5546 | 500 | 100 | 25 | 125 | 25 | 45 | -20 | 125 | 157 | -32
Pier Cap | cum | 8075 | 560 | 16 | 4 | 140 | 4 | 1 | 3 | 140 | 66 | 74 |  | Pier Cap | cum | 8075 | 560 | 16 | 4 | 140 | 4 | 2 | 2 | 140 | 130 | 10
Track Beam with Nose | cum | 8981 | 996 | 83 | 20 | 240 | 20 | 11 | 9 | 240 | 120 | 120 |  | Track Beam with Nose | cum | 8981 | 996 | 83 | 20 | 240 | 20 | 12 | 8 | 240 | 144 | 96
Track Beam without Nose | cum | 9585 | 408 | 34 | 5 | 60 | 5 | 13 | -8 | 60 | 156 | -96 |  | Track Beam without Nose | cum | 9585 | 408 | 34 | 10 | 120 | 10 | 13 | -3 | 120 | 156 | -36
h - Section Beam | cum | 4483 | 420 | 35 | 10 | 120 | 10 | 3 | 7 | 120 | 36 | 84 |  | h - Section Beam | cum | 4483 | 420 | 35 | 10 | 120 | 10 | 7 | 3 | 120 | 84 | 36
U - Section Beam | cum | 4260 | 276 | 23 | 5 | 60 | 5 | 2 | 3 | 60 | 24 | 36 |  | U - Section Beam | cum | 4260 | 276 | 23 | 5 | 60 | 5 | 3 | 2 | 60 | 36 | 24
Pre-cast Slab | cum | 351 | 20 | 40 | 10 | 5 | 10 | 0 | 10 | 5 | 0 | 5 |  | Pre-cast Slab | cum | 351 | 20 | 40 | 10 | 5 | 10 | 0 | 10 | 5 | 0 | 5
Abutment wall- PART-A | cum | 491 | 90 | 1 | 0 | 30 | 0 | 0 | 0 | 30 | 0 | 30 |  | Abutment wall- PART-A | cum | 491 | 90 | 1 | 0 | 30 | 0 | 0 | 0 | 30 | 0 | 30
Abutment wall- PART-D | cum | 830 | 120 | 1 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 40 |  | Abutment wall- PART-D | cum | 830 | 120 | 1 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 40
Cast In-situ slab- 1- PART-G | cum | 471 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Cast In-situ slab- 1- PART-G | cum | 471 | 529 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- 2- PART-G | cum | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Cast In-situ slab- 2- PART-G | cum | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- PART-C | cum | 650 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Cast In-situ slab- PART-C | cum | 650 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-cast Segment Erection | nos. | 3004 | 200 | 0 | 49 | 0 | 49 | 24 | 25 | 0 | 0 | 0 |  | Pre-cast Segment Erection | nos. | 3004 | 200 | 0 | 49 | 0 | 49 | 25 | 24 | 0 | 0 | 0
Track Beam with Nose | nos. | 783 | 42 | 0 | 10 | 0 | 10 | 11 | -1 | 0 | 0 | 0 |  | Track Beam with Nose | nos. | 783 | 42 | 0 | 10 | 0 | 10 | 12 | -2 | 0 | 0 | 0
Track Beam without Nose | nos. | 811 | 58 | 0 | 14 | 0 | 14 | 13 | 1 | 0 | 0 | 0 |  | Track Beam without Nose | nos. | 811 | 58 | 0 | 14 | 0 | 14 | 13 | 1 | 0 | 0 | 0
h-Section Beam | nos. | 369 | 24 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 0 |  | h-Section Beam | nos. | 369 | 24 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 0
U-Section Beam | nos. | 420 | 22 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 0 |  | U-Section Beam | nos. | 420 | 22 | 0 | 6 | 0 | 6 | 0 | 6 | 0 | 0 | 0
Pre-cast Slab | nos. | 621 | 54 | 0 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 0 |  | Pre-cast Slab | nos. | 621 | 54 | 0 | 13 | 0 | 13 | 0 | 13 | 0 | 0 | 0
Elevated HMT works | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 | 0 | 0 | 0 |  | Elevated HMT works | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 | 0 | 0 | 0 | 0
Track linking | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 |  |  |  |  | Track linking | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75
Activity | UoM | Scope | Current Plan FTM Oct'23 (Cum) | Current Plan FTM Oct'23 (Nos) | WEEK-4 |  | WEEK-4 ( Nos) |  |  | WEEK-4 (Cum) |  |  | Reason for Shortfall
[5 empty] | Nos | Cum | Plan | Achieved | Shortfall | Plan | Achieved | Shortfall
Civil | cum | 62550 | 4795 | 440 | 95 | 1535 | 95 | 53 | 42 | 1535 | 875 | 141 |  | 10 | 30
PCC | cum | 1655 | 79 | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 160
RCC Foundation | cum | 10211 | 460 | 23 | 0 | 60 | 0 | 3 | -3 | 60 | 113 | -53 |  | 10 | 50
Step Footing | cum | 2550 | 115 | 23 | 0 | 0 | 0 | 2 | -2 | 0 | 20 | -20 |  | 12 | 72
Pier 1900 mm | cum | 3270 | 222 | 37 | 7 | 42 | 7 | 1 | 6 | 42 | 6 | 36 |  | 25 | 125
Pier 1600 mm | cum | 5546 | 500 | 100 | 25 | 125 | 25 | 19 | 6 | 125 | 110 | 15 |  | 6 | 170
Pier Cap | cum | 8075 | 560 | 16 | 6 | 180 | 6 | 5 | 1 | 180 | 208 | -28 |  | 22 | 264
Track Beam with Nose | cum | 8981 | 996 | 83 | 23 | 276 | 23 | 6 | 17 | 276 | 72 | 204 |  | 22 | 264
Track Beam without Nose | cum | 9585 | 408 | 34 | 14 | 168 | 14 | 2 | 12 | 168 | 24 | 144 |  | 6 | 72
h - Section Beam | cum | 4483 | 420 | 35 | 5 | 60 | 5 | 7 | -2 | 60 | 84 | -24 |  | 6 | 72
U - Section Beam | cum | 4260 | 276 | 23 | 5 | 60 | 5 | 5 | 0 | 60 | 60 | 0 |  | 20 | 10
Pre-cast Slab | cum | 351 | 20 | 40 | 10 | 5 | 10 | 0 | 10 | 5 | 0 | 5 |  |  | 24
Abutment wall- PART-A | cum | 491 | 90 | 1 | 0 | 0 | 0 | 3 | -3 | 0 | 178 | -178
Abutment wall- PART-D | cum | 830 | 120 | 1 | 0 | 40 | 0 | 0 | 0 | 40 | 0 | 40
Cast In-situ slab- 1- PART-G | cum | 471 | 529 | 0 | 0 | 519 | 0 | 0 | 0 | 519 | 0
Cast In-situ slab- 2- PART-G | cum | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Cast In-situ slab- PART-C | cum | 650 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Pre-cast Segment Erection | nos. | 3004 | 200 | 0 | 68 | 0 | 68 | 8 | 60 | 0 | 0 | 0
Track Beam with Nose | nos. | 783 | 42 | 0 | 14 | 0 | 14 | 6 | 8 | 0 | 0 | 0
Track Beam without Nose | nos. | 811 | 58 | 0 | 20 | 0 | 20 | 2 | 18 | 0 | 0 | 0
h-Section Beam | nos. | 369 | 24 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0
U-Section Beam | nos. | 420 | 22 | 0 | 8 | 0 | 8 | 0 | 8 | 0 | 0 | 0
Pre-cast Slab | nos. | 621 | 54 | 0 | 18 | 0 | 18 | 0 | 18 | 0 | 0 | 0
Elevated HMT works | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 | 0 | 0 | 0
Track linking | RM | 5152 | 300 | 300 | 75 | 0 | 75 | 0 | 75 |  |  | 0

## Overall S-curve (hidden)
Weightage | EPC | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
10% | Engineering | Plan | 0 | 15.3477 | 20.307 | 17.0743 | 12.7802 | 11.944 | 5.06 | 7.4996 | 9.9872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0 | 15.3477 | 35.6547 | 52.729 | 65.5092 | 77.4532 | 82.5132 | 90.0128 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 100.0005 | 10
|  | Actual | 0 | 8.7924 | 10.3901 | 11.9904 | 12.6491 | 9.5923 | 5.4133 | 1.9137 | 0 | 8.9566 | 0 | 0 | 0 | 0 | 0 | 30.3022 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Actual | 0 | 8.7924 | 19.1825 | 31.1729 | 43.822 | 53.4143 | 58.8276 | 60.7413 | 60.7413 | 69.6978 | 69.6978 | 69.6978 | 69.6978 | 69.6978 | 69.6978 | 100 | 100 | 100 | 100 | 100 | 100 | 0
10% | Ordering & Supply | Plan | 0 | 0 | 1 | 3.6 | 7.1 | 8.3 | 16 | 20 | 16.5 | 12.4 | 9.6 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0 | 0 | 1 | 4.6 | 11.7 | 20 | 36 | 56 | 72.5 | 84.9 | 94.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 4.0387 | 0.40387
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 40.1156 | 0 | 0.12351 | 12.6202 | 0 | 0.55779 | 6.1458 | 1.3048 | 0.27173 | 8.1764 | 0.68748 | 0.78506 | 17.5519 | 7.6209 | 0 | 0
|  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 40.1156 | 40.1156 | 40.2391 | 52.8594 | 52.8594 | 53.4172 | 59.563 | 60.8678 | 61.1395 | 69.316 | 70.0035 | 70.7885 | 88.3405 | 95.9613 | 95.9613 | 95.9613
40% | Civil | Plan | 0.51958 | 0.96723 | 1.5188 | 2.8377 | 4.988 | 6.9432 | 8.8265 | 10.1055 | 10.8681 | 10.4828 | 8.996 | 7.968 | 6.7402 | 5.0568 | 3.8737 | 2.0975 | 1.2102 | 3.4229 | 2.5771 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0.51958 | 1.4868 | 3.0056 | 5.8433 | 10.8313 | 17.7746 | 26.6011 | 36.7066 | 47.5747 | 58.0576 | 67.0536 | 75.0216 | 81.7618 | 86.8185 | 90.6922 | 92.7898 | 94 | 97.4229 | 100.0015 | 100.0015 | 100.0015 | 100.0015 | 100.0015 | 100.0015 | 100.0015 | 100.0015 | 16.6905 | 6.6762
|  | Actual | 0.033573 | 1.5268 | 1.2054 | 1.5225 | 1.6355 | 2.3017 | 3.3333 | 4.4876 | 6.3645 | 5.028 | 5.1119 | 5.5683 | 5.199 | 4.7666 | 2.5899 | 4.6914 | 4.3054 | 5.1431 | 5.7658 | 6.2278 | 6.5028 | 3.1615
|  | Cum Actual | 0.033573 | 1.5604 | 2.7658 | 4.2883 | 5.9238 | 8.2255 | 11.5588 | 16.0464 | 22.411 | 27.4389 | 32.5508 | 38.1192 | 43.3182 | 48.0848 | 50.6747 | 55.3662 | 59.6715 | 64.8146 | 70.5804 | 76.8082 | 83.311 | 86.4725
15% | Pre-cast Erection | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63286 | 3.0776 | 5.5508 | 9.694 | 12.1494 | 14.1829 | 14.7609 | 13.6785 | 11.2308 | 7.1937 | 4.8938 | 2.8471 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63286 | 3.7104 | 9.2613 | 18.9553 | 31.1047 | 45.2876 | 60.0485 | 73.727 | 84.9578 | 92.1515 | 97.0453 | 99.8925 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 51.7643 | 7.7646
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26631 | 1.1651 | 2.2636 | 7.1238 | 4.5939 | 3.7949 | 4.9268 | 3.7284 | 4.1944 | 2.2636 | 3.6285 | 5.3595 | 4.9268 | 1.8309
|  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26631 | 1.4314 | 3.6951 | 10.8189 | 15.4128 | 19.2077 | 24.1345 | 27.8628 | 32.0573 | 34.3209 | 37.9494 | 43.3089 | 48.2357 | 50.0666
20% | Track laying | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6107 | 7.8587 | 13.399 | 18.5823 | 18.0935 | 18.1235 | 13.2606 | 8.0745 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6107 | 10.4694 | 23.8685 | 42.4508 | 60.5443 | 78.6678 | 91.9285 | 100.003 | 100 | 100 | 100 | 100 | 100 | 100 | 82.3758 | 16.4752
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.882 | 0 | 8.1522 | 5.5901 | 0 | 0 | 0 | 0
|  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.882 | 3.882 | 12.0342 | 17.6242 | 17.6242 | 17.6242 | 17.6242 | 0
5% | Commissioning | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 25 | 50 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 50 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 5
|  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
100% | Overall | Plan | 0.20783 | 1.9217 | 2.7382 | 3.2025 | 3.9832 | 4.8017 | 5.6366 | 6.8871 | 7.4576 | 6.2658 | 6.0125 | 5.5596 | 5.3457 | 5.8086 | 6.2811 | 6.2401 | 5.1818 | 5.7279 | 5.36 | 2.8649 | 2.5 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0.20783 | 2.1295 | 4.8677 | 8.0702 | 12.0535 | 16.8552 | 22.4918 | 29.3789 | 36.8365 | 43.1022 | 49.1147 | 54.6743 | 60.02 | 65.8286 | 72.1096 | 78.3497 | 83.5316 | 89.2595 | 94.6196 | 97.4845 | 99.9845 | 99.9845 | 99.9845 | 99.9845 | 99.9845 | 99.9845 | 36.3037 | 36.3037
|  | Actual | 0.013429 | 1.49 | 1.5212 | 1.8081 | 1.9191 | 1.8799 | 5.8862 | 1.9864 | 2.5981 | 4.3436 | 2.3843 | 3.3517 | 3.3833 | 2.6064 | 2.5786 | 6.2837 | 4.0505 | 3.5933 | 4.6058 | 4.0571 | 3.3401 | 1.5392
|  | Cum Actual | 0.013429 | 1.5034 | 3.0246 | 4.8326 | 6.7517 | 8.6316 | 14.5179 | 16.5043 | 19.1024 | 23.446 | 25.8303 | 29.182 | 32.5653 | 35.1716 | 37.7502 | 44.0339 | 48.0844 | 51.6777 | 56.2835 | 60.3406 | 63.6807 | 65.22
|  | Cum Revised Plan |  | 2023-05-01: 38.1251; 2023-06-01: 44.4088; 2023-07-01: 48.4592; 2023-08-01: 51.9827; 2023-09-01: 56.5878; 2023-10-01: 62.0878; 2023-11-01: 69.0878; 2023-12-01: 76.5878; 2024-01-01: 84.0878; 2024-02-01: 100
|  | Moving average | 3.1022 | 2023-03-01: 3.2354; 2023-04-01: 6.5; 2023-05-01: 7.5; 2023-06-01: 7; 2023-07-01: 5; 2023-08-01: 5; 2023-09-01: 5; 2023-10-01: 5.5; 2023-11-01: 7; 2023-12-01: 7.5; 2024-01-01: 7.5; 2024-02-01: 15.9122
[17 empty] | 34.3594 | 34.3158 | 35.4472 | 37.5818 | 38.3361 | 37.1439 | 36.3037 | 34.7645
# | Discipline | Weightage
A | Engineering | 10%
A1 | Civil | 5%
A2 | Track Linking | 3%
A3 | OHE and S&T | 2%
B | Ordering | 4%
C | Equipment Delivery | 6%
D | Work Execution | 75%
D1 | Civil | 35%
D2 | Pre-cast Erection | 10%
D3 | Track Linking | 15%
D4 | OHE | 10%
D5 | S&T | 5%
E | Commissioning | 5%
| Total | 100%
Weightage | EPC | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
75% | Construction | Plan | 0.27711 | 0.51585 | 0.81002 | 1.5135 | 2.6603 | 3.7031 | 4.7075 | 5.5162 | 6.4118 | 6.701 | 6.7367 | 6.6795 | 7.1276 | 7.7448 | 8.3747 | 8.3201 | 6.9091 | 7.6372 | 5.4801 | 2.1532 | 0 | 0 | 0 | 0 | 0 | 0
|  | Cum Plan | 0.27711 | 0.79297 | 1.603 | 3.1164 | 5.7767 | 9.4798 | 14.1873 | 19.7034 | 26.1153 | 32.8163 | 39.553 | 46.2324 | 53.36 | 61.1048 | 69.4795 | 77.7997 | 84.7088 | 92.346 | 97.8261 | 99.9793 | 99.9793 | 99.9793 | 99.9793 | 99.9793 | 99.9793 | 99.9793
|  | Actual | 0.017906 | 0.81428 | 0.6429 | 0.81202 | 0.87226 | 1.2276 | 1.7778 | 2.3934 | 3.4477 | 2.9146 | 3.1791 | 4.3946 | 3.6916 | 3.3012 | 3.4018 | 3.2478 | 5.309 | 4.6864 | 3.8008 | 4.3934 | 4.4535
|  | Cum Actual | 0.017906 | 0.83219 | 1.4751 | 2.2871 | 3.1594 | 4.3869 | 6.1647 | 8.5581 | 12.0058 | 14.9204 | 18.0995 | 22.494 | 26.1856 | 29.4868 | 32.8886 | 36.1364 | 41.4454 | 46.1318 | 49.9326 | 54.326 | 58.7795
[18 empty] | 41.6633 | 43.2634

## Engg S-curve (hidden)
|  | Activity | Conc per footing | Completed till date (nos.) | Area | Footings (nos.) | Completed till date (%) |  |  |  | SN | Part | Cast-in-situ | Pre-cast | Total | Remarks |  | Tentative Scope in Nos. | Tentative Scope in Cum | Total received in Nos. |  | Revised Scope Statement | Part | Cast-in-situ | Pre-cast | Total |  | Cumulative Dwg receipt as of Jun-23 | Part | Cast-in-situ | Pre-cast | Total | Dwg received in Dec-22 | Part | Cast-in-situ | Pre-cast | Total
|  | PCC | 3.8017 | 339.7071 | A | 40 | 37.36% |  |  |  | 1 | A | 1999 | 2090 | 4089 |  |  | 266 | 1831 | 266 |  |  | A | 1941 | 1827 | 3768 |  |  | A | 1941 | 1827 | 3768 |  | A | -58 | -263 | -321
|  | RCC Foundation | 21.1569 | 151 | B | 28 | 16.61% |  |  |  | 2 | B | 1430 | 1694 | 3124 |  |  | 190 | 1633 | 190 |  |  | B | 1396 | 1616 | 3012 |  |  | B | 1396 | 1616 | 3012 |  | B | -34 | -78 | -112
|  | Step Footing | 5.5447 | 147 | C | 40 | 16.17% |  |  |  | 3 | C | 1590 | 0 | 1590 | dwg NA for precast & pier cap |  | 184 | 1771 | 184 |  |  | C | 3364 | 1574 | 4938 |  |  | C | 3364 | 1574 | 4938 |  | C | 1774 | 1574 | 3348
|  | Pier 1900 mm | 6.4177 | 136 | D | 54 | 14.96% |  |  |  | 4 | D | 3158 | 2871 | 6029 |  |  | 342 | 2943 | 342 |  |  | D | 2524 | 2740 | 5264 |  |  | D | 2524 | 2740 | 5264 |  | D | -634 | -131 | -765
|  | Pier 1600 mm | 9.4384 | 50.59 | E | 36 | 5.563% |  |  |  | 5 | E | 1477 | 0 | 1477 | Workfront unavailable |  | 190 | 2165 | 190 |  |  | E | 2001 | 2158 | 4159 |  |  | E | 2001 | 2158 | 4159 |  | E | 524 | 2158 | 2682
|  | Pier Cap | 27.2115 | 18 | F | 30 | 1.979% |  |  |  | 6 | F | 1512 | 1716 | 3228 |  |  | 172 | 1598 | 172 |  |  | F | 1848 | 1584 | 3432 |  |  | F | 1848 | 1584 | 3432 |  | F | 336 | -132 | 204
|  | Track Beam with Nose | 11.9429 | 11.0526 | G | 60 | 1.215% |  |  |  | 7 | G | 2631 | 0 | 2631 | dwg NA for precast & pier cap |  | 245 | 2123 | 245 |  |  | G | 4551 | 3214 | 7765 |  |  | G | 4551 | 3214 | 7765 |  | G | 1920 | 3214 | 5134
|  | Track Beam without Nose | 10.4571 | 36.7213 | H | 50 | 4.038% |  |  |  | 8 | H | 1965 | 2497 | 4462 |  |  | 252 | 2639 | 252 |  |  | H | 2551 | 2597 | 5148 |  |  | H | 2551 | 2597 | 5148 |  | H | 586 | 100 | 686
|  | h - Section Beam | 14.64 | 3.2787 | I | 55 | 0.3606% |  |  |  | 9 | I | 2466 | 3179 | 5645 |  |  | 319 | 3086 | 319 |  |  | I | 2630 | 3188 | 5818 |  |  | I | 2630 | 3188 | 5818 |  | I | 164 | 9 | 173
|  | U - Section Beam | 10.44 | 15.9962 | J | 43 | 1.759% |  |  |  | 10 | J | 2193 | 2299 | 4492 |  |  | 234 | 2209 | 234 |  |  | J | 2677 | 2403 | 5080 |  |  | J | 2677 | 2403 | 5080 |  | J | 484 | 104 | 588
|  | P-way |  |  | K | 110 |  |  |  |  | 11 | K | 3780 | 5610 | 9390 |  |  | 610 | 5662 | 610 |  |  | K | 5333 | 5559 | 10892 |  |  | K | 5333 | 5559 | 10892 |  | K | 1553 | -51 | 1502
|  | Electrical | [9 empty] | Total | 24201 | 21956 | 46157 |  |  | 3004 | 27660 | 3004 |  |  | Total | 30816 | 28460 | 59276 |  |  | Total | 30816 | 28460 | 59276 |  | Total | 6615 | 6504 | 13119
|  |  |  | 909.3459 |  | 546 | [11 empty] | 26320.8
|  | Plan |  | 2022-09-24
| # | Area | Total Footings (nos.) | Concreting Scope (cum) | Completed Till Mar-22 (cum) | Balance (cum) | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 |  |  |  | Revised Scope Statement | Part | Cast-in-situ | Pre-cast | Total
7.326% | 1 | A | 40 | 3903 |  | 3903 | 1500 | 2009 | 0 | 0 | 0 | 0 | 0 | 394 | 0 | 0 | 0 | 0 | 0 |  |  | 3903 | 0 |  |  | A | 2070 | 1829 | 3899
5.128% | 2 | B | 28 | 3125 |  | 3125 | 1000 | 1493 | 0 | 0 | 0 | 0 | 0 | 632 | 0 | 0 | 0 | 0 | 0 |  |  | 3125 | 0 |  |  | B | 1491 | 1632 | 3123
7.326% | 3 | C | 40 | 4057 |  | 4057 | 500 | 800 | 1000 | 1000 | 757 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4057 | 0 |  |  | C | 2284 | 1768 | 4052
9.89% | 4 | D | 54 | 5704 |  | 5704 | 500 | 500 | 500 | 800 | 500 | 520 | 0 | 2384 | 0 | 0 | 0 | 0 | 0 |  |  | 5704 | 0 |  |  | D | 2738 | 2942 | 5680
6.593% | 5 | E | 36 | 4421 |  | 4421 | 600 | 800 | 1000 | 959 | 800 | 0 | 0 | 262 | 0 | 0 | 0 | 0 | 0 |  |  | 4421 | 0 |  |  | E | 2254 | 2164 | 4418
5.495% | 6 | F | 30 | 3578 |  | 3578 | 500 | 500 | 654 | 500 | 500 | 0 | 0 | 924 | 0 | 0 | 0 | 0 | 0 |  |  | 3578 | 0 |  |  | F | 1978 | 1597 | 3575
10.99% | 7 | G | 60 | 5757 |  | 5757 | 1000 | 1200 | 2000 |  | 1557 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5757 | 0 |  |  | G | 3567 | 2380 | 5947
9.158% | 8 | H | 50 | 5148 |  | 5148 | 1200 | 1500 | 1500 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 5148 | 0 |  |  | H | 2576 | 2636 | 5212
10.07% | 9 | I | 55 | 5891 |  | 5891 | 800 | 1000 | 1000 | 1500 | 1157 | 361 | 0 | 73 | 0 | 0 | 0 | 0 | 0 |  |  | 5891 | 0 |  |  | I | 2803 | 3083 | 5886
7.875% | 10 | J | 43 | 4913 |  | 4913 | 1200 | 1700 | 1526 | 487 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 4913 | 0 |  |  | J | 2702 | 2207 | 4909
20.15% | 11 | K | 110 | 12470 |  | 12470 | 800 | 1200 | 1500 | 1800 | 2200 | 2284 | 1108 | 1578 | 0 | 0 | 0 | 0 | 0 |  |  | 12470 | 0 |  |  | K | 6807 | 5661 | 12468
| 12 | Abutment wall- PART-A |  | 491 |  | 491 | 2022-10-01: 491 | 491 | 0
| 13 | Abutment wall- PART-D |  | 830 |  | 830 | 2022-10-01: 830 | 830 | 0
| 14 | Cast In-situ slab- 1- PART-G |  | 471 |  | 471 | 2022-10-01: 471 | 471 | 0
| 15 | Cast In-situ slab- 2- PART-G |  | 1141 |  | 1141 | 2022-10-01: 1141 | 1141 | 0
| 16 | Cast In-situ slab- PART-C |  | 650 |  | 650 | 2022-10-01: 650 | 650 | 0 |  |  | Total | 31270 | 27899 | 59169
|  | Planned Total: | 546 | 62550 | 0 | 62550 | 9600 | 12702 | 10680 | 7994 | 7471 | 3165 | 4691 | 6247 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62550
|  | Actual |  | 2022-09-24
| # | Area | Total Footings (nos.) | Concreting Scope (cum) | Completed Till Mar-22 (cum) | Balance (cum) | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
7.326% | 1 | A | 40 | 3903 |  | 3903 | 1000 | 500 | 0 | 1000 | 1000 | 358 | 0 | 0 | -90 | 0 | 0 | 0 | 0 | 0 | 135 | 3903 | 0
5.128% | 2 | B | 28 | 3125 |  | 3125 | 0 | 500 | 1000 | 500 | 363 | 0 | 0 | 0 | 649 | 0 | 0 | 0 | 0 | 0 | 113 | 3125 | 0
7.326% | 3 | C | 40 | 4057 |  | 4057 | 0 | 800 | 1000 | 1500 | 817 | 0 | 0 | 0 | -753 | 0 | 0 | 0 | 0 | 0 | 693 | 4057 | 0
9.89% | 4 | D | 54 | 5704 |  | 5704 | 0 | 0 | 1000 | 500 | 1000 | 500 | 500 | 0 | 1764 | 0 | 0 | 0 | 0 | 0 | 440 | 5704 | 0
6.593% | 5 | E | 36 | 4421 |  | 4421 | 0 | 0 | 1000 | 1500 | 1000 | 206 | 0 | 0 | 453 | 0 | 0 | 0 | 0 | 0 | 262 | 4421 | 0
5.495% | 6 | F | 30 | 3578 |  | 3578 | 833 | 699 | 500 | 278 | 0 | 0 | 0 | 0 | 1122 | 0 | 0 | 0 | 0 | 0 | 146 | 3578 | 0
10.99% | 7 | G | 60 | 5757 |  | 5757 | 0 | 1000 | 1000 | 1000 | 500 | 800 | 300 | 0 | -49 | 0 | 0 | 0 | 0 | 0 | 1206 | 5757 | 0
9.158% | 8 | H | 50 | 5148 |  | 5148 | 0 | 1000 | 1000 | 1000 | 500 | 500 | 200 | 0 | 948 | 0 | 0 | 0 | 0 | 0 | 0 | 5148 | 0
10.07% | 9 | I | 55 | 5891 |  | 5891 | 1833.3333 | 1000 | 500 | 634 | 500 | 500 | 197 | 0 | 653.6667 | 0 | 0 | 0 | 0 | 0 | 73 | 5891 | 0
7.875% | 10 | J | 43 | 4913 |  | 4913 | 1833.3333 | 1000 | 500 | 0 | 320 | 522 | 0 | 0 | 904.6667 | 0 | 0 | 0 | 0 | 0 | -167 | 4913 | 0
20.15% | 11 | K | 110 | 12470 |  | 12470 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12470 | 12470 | 0
| 12 | Abutment wall- PART-A |  | 491 |  | 491 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 491 | 491 | 0
| 13 | Abutment wall- PART-D |  | 830 |  | 830 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 830 | 830 | 0
| 14 | Cast In-situ slab- 1- PART-G |  | 471 |  | 471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 471 | 471 | 0
| 15 | Cast In-situ slab- 2- PART-G |  | 1141 |  | 1141 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1141 | 1141 | 0
| 16 | Cast In-situ slab- PART-C |  | 650 |  | 650 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 650 | 650 | 0
|  | Actual Total: | 546 | 62550 | 0 | 62550 | 5499.6667 | 6499 | 7500 | 7912 | 6000 | 3386 | 1197 | 0 | 5602.3333 | 0 | 0 | 0 | 0 | 0 | 18954 | 62550
[13 empty] | 2197 | 1000
[5 empty] | Quantity | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
[5 empty] | Plan | 0 | 9600 | 12702 | 10680 | 7994 | 7471 | 3165 | 4691 | 6247 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Cum Plan | 0 | 9600 | 22302 | 32982 | 40976 | 48447 | 51612 | 56303 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550
[5 empty] | Actual | 0 | 5499.6667 | 6499 | 7500 | 7912 | 6000 | 3386 | 1197 | 0 | 5602.3333 | 0 | 0 | 0 | 0 | 0 | 18954 | 0 | 0 | 0 | 0 | 0
[5 empty] | Cum Actual | 0 | 5499.6667 | 11998.6667 | 19498.6667 | 27410.6667 | 33410.6667 | 36796.6667 | 37993.6667 | 37993.6667 | 43596 | 43596 | 43596 | 43596 | 43596 | 43596 | 62550 | 62550 | 62550 | 62550 | 62550 | 62550
[5 empty] | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01
[5 empty] | Plan | 0 | 15.3477 | 20.307 | 17.0743 | 12.7802 | 11.944 | 5.06 | 7.4996 | 9.9872 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[5 empty] | Cum Plan | 0 | 15.3477 | 35.6547 | 52.729 | 65.5092 | 77.4532 | 82.5132 | 90.0128 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[5 empty] | Actual | 0 | 8.7924 | 10.3901 | 11.9904 | 12.6491 | 9.5923 | 5.4133 | 1.9137 | 0 | 8.9566 | 0 | 0 | 0 | 0 | 0 | 30.3022 | 0 | 0 | 0 | 0 | 0
[5 empty] | Cum Actual | 0 | 8.7924 | 19.1825 | 31.1729 | 43.822 | 53.4143 | 58.8276 | 60.7413 | 60.7413 | 69.6978 | 69.6978 | 69.6978 | 69.6978 | 69.6978 | 69.6978 | 100 | 100 | 100 | 100 | 100 | 100

## Procurement S-curve (hidden)
| As on: | 2023-02-27
| # | Material | Scope | UoM | Received | Balance | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
| 1 | Curved Sleepers | 6000 | EA | 0 | 6000 |  | 2022-09-01: 0; 2023-02-01: 0; 2023-03-01: 54; 2023-04-01: 854; 2023-05-01: 100; 2023-06-01: 694; 2023-07-01: 666; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 100; 2023-11-01: 0 | 2468
| 2 | Wide PSC Sleepers | 18000 | EA | 0 | 18000 |  | 2022-09-01: 0; 2022-12-01: 3500; 2023-02-01: 1200; 2023-03-01: 1510; 2023-04-01: 1660; 2023-05-01: 500; 2023-06-01: 1895; 2023-07-01: 1114; 2023-08-01: 770; 2023-09-01: 1850; 2023-10-01: 550; 2023-11-01: 0 | 14549
| 3 | PSC Sleepers Monoblock Suitable | 6500 | EA | 692 | 5808 |  | 2022-09-01: 692; 2022-12-01: 368; 2023-02-01: 1030; 2023-04-01: 758; 2023-05-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 2848
| 4 | Points & Crossings | 60 | SET | 0 | 60 |  | 2022-09-01: 0; 2023-02-01: 8; 2023-03-01: 7; 2023-04-01: 5; 2023-06-01: 3; 2023-07-01: 3; 2023-08-01: 8; 2023-09-01: 2; 2023-10-01: 0; 2023-11-01: 0 | 36
| 5 | Points & Crossings Assembly | 50 | SET | 0 | 50 |  | 2022-09-01: 0; 2022-12-01: 20; 2023-02-01: 20; 2023-03-01: 8; 2023-04-01: 5; 2023-06-01: 7; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 60
| 6 | Fish Plate | 6200 | EA | 6200 | 0 |  | 2022-09-01: 6200; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 6200
| 7 | Bolt | 12500 | EA | 10000 | 2500 |  | 2022-09-01: 1000; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 11500; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 12500
| 8 | Sole Rubber Pads | 25000 | EA | 25000 | 0 |  | 2022-09-01: 25000; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 25000
| 9 | MTL Liners T-3740 | 50000 | EA | 27700 | 22300 |  | 2022-09-01: 27700; 2022-12-01: 22300; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 50000
| 10 | J Clips | 10000 | EA | 0 | 10000 |  | 2022-09-01: 0; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 7950; 2023-10-01: 2050; 2023-11-01: 0 | 10000
| 11 | Clips | 50000 | EA | 0 | 50000 |  | 2022-09-01: 0; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 35050; 2023-10-01: 14950; 2023-11-01: 0 | 50000
| 12 | Composite GRV Rubber Sole | 50000 | EA | 50000 | 0 |  | 2022-09-01: 50000; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 50000
| 13 | Elastic Rail Clips (ERC) | 75000 | EA | 0 | 75000 |  | 2022-09-01: 0; 2022-12-01: 20000; 2023-02-01: 0; 2023-04-01: 0; 2023-05-01: 500; 2023-06-01: 18500; 2023-08-01: 0; 2023-09-01: 23500; 2023-10-01: 12500; 2023-11-01: 0 | 75000
| 14 | Ballast | 17000 | MT | 0 | 17000 |  | 2022-09-01: 0; 2023-02-01: 0; 2023-03-01: 3500; 2023-04-01: 2000; 2023-06-01: 0; 2023-07-01: 1000; 2023-08-01: 2400; 2023-09-01: 2700; 2023-10-01: 700; 2023-11-01: 0 | 12300
| 15 | 60kg Rail - AS/RDSO IRS T-12-2009 | 2500 | MT | 0 | 2500 |  | 2022-09-01: 0; 2022-11-01: 500; 2022-12-01: 500; 2023-02-01: 0; 2023-04-01: 0; 2023-06-01: 500; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 1500
| 16 | MTL Liners T-8616 (GF) | 38000 | EA | 29400 | 8600 |  | 2022-09-01: 29400; 2023-02-01: 0; 2023-03-01: 8600; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 38000
| 17 | MTL Liners T-8617 (NGF) | 38000 | EA | 22400 | 15600 |  | 2022-09-01: 22400; 2022-12-01: 4400; 2023-02-01: 0; 2023-03-01: 11200; 2023-04-01: 0; 2023-06-01: 0; 2023-08-01: 0; 2023-09-01: 0; 2023-10-01: 0; 2023-11-01: 0 | 38000
|  |  | 404810 |  | 171392 | 233418 | 0 | 0 | 0 | 0 | 0 | 0 | 162392 | 0 | 500 | 51088 | 0 | 2258 | 24879 | 5282 | 1100 | 33099 | 2783 | 3178 | 71052 | 30850 | 0 | 0 | 0 | 0 | 0 | 0 | 388461
Weightage |  | Plan %
| # | Area | Scope | UoM | Received till Sep-22 | Balance | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
7.326% | 1 | A | 29656.4103 | Units | 12556.1905 | 17100.2198 | 0 | 0 | 809.62 | 2024.05 | 4048.1 | 4048.1 | 8096.2 | 8096.2 | 2428.86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29551.13
5.128% | 2 | B | 20759.4872 | Units | 8789.3333 | 11970.1538 | 0 | 0 | 404.81 | 1214.43 | 3238.48 | 4048.1 | 4048.1 | 4048.1 | 3643.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20645.31
7.326% | 3 | C | 29656.4103 | Units | 12556.1905 | 17100.2198 | 0 | 0 | 404.81 | 2024.05 | 3238.48 | 4048.1 | 4048.1 | 8096.2 | 4048.1 | 3643.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29551.13
9.89% | 4 | D | 40036.1538 | Units | 16950.8571 | 23085.2967 | 0 | 0 | 809.62 | 3238.48 | 4048.1 | 3238.48 | 4048.1 | 8096.2 | 8096.2 | 8501.01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40076.19
6.593% | 5 | E | 26690.7692 | Units | 11300.5714 | 15390.1978 | 0 | 0 | 0 | 809.62 | 2024.05 | 2024.05 | 4048.1 | 8096.2 | 8096.2 | 1619.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26717.46
5.495% | 6 | F | 22242.3077 | Units | 9417.1429 | 12825.1648 | 0 | 0 | 0 | 1214.43 | 2024.05 | 2024.05 | 4048.1 | 4048.1 | 4048.1 | 2024.05 | 2833.67 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22264.55
11.9% | 7 | G | 48191.6667 | Units | 20403.8095 | 27787.8571 | 0 | 0 | 0 | 2024.05 | 4048.1 | 4048.1 | 8096.2 | 8096.2 | 8096.2 | 8096.2 | 4048.1 | 1619.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 48172.39
9.158% | 8 | H | 37070.5128 | Units | 15695.2381 | 21375.2747 | 0 | 0 | 809.62 | 2024.05 | 4048.1 | 8096.2 | 8096.2 | 8096.2 | 4048.1 | 2024.05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37242.52
10.07% | 9 | I | 40777.5641 | Units | 17264.7619 | 23512.8022 | 0 | 0 | 809.62 | 0 | 2024.05 | 2024.05 | 4048.1 | 8096.2 | 8096.2 | 8096.2 | 4048.1 | 3643.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40885.81
7.875% | 10 | J | 31880.641 | Units | 13497.9048 | 18382.7363 | 0 | 0 | 0 | 0 | 0 | 0 | 8096.2 | 8096.2 | 8096.2 | 4048.1 | 3643.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31979.99
19.23% | 11 | K | 77848.0769 | Units | 32960 | 44888.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 8096.2 | 8096.2 | 8096.2 | 12144.3 | 24288.6 | 17002.02 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 77723.52
|  | Planned Total %: | 404810 |  | 171392 | 233418 | 0 | 0 | 4048.1 | 14573.16 | 28741.51 | 33599.23 | 64769.6 | 80962 | 66793.65 | 50196.44 | 38861.76 | 22264.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 404810
Actual %
| # | Area | Scope | UoM | Received till Sep-22 | Balance | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
7.326% | 1 | A | 29656.4103 | Units | 12556.1905 | 17100.2198 | 0 | 0 | 0 | 0 | 0 | 0 | 11896.8498 | 0 | 36.63 | 3742.7106 | 0 | 165.4212 | 1822.6374 | 386.9597 | 80.5861 | 2424.8352 | 203.8828 | 232.8205 | 5205.2747 | 2260.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 28458.6813
5.128% | 2 | B | 20759.4872 | Units | 8789.3333 | 11970.1538 | 0 | 0 | 0 | 0 | 0 | 0 | 8327.7949 | 0 | 25.641 | 2619.8974 | 0 | 115.7949 | 1275.8462 | 270.8718 | 56.4103 | 1697.3846 | 142.7179 | 162.9744 | 3643.6923 | 1582.0513 | 0 | 0 | 0 | 0 | 0 | 0 | 19921.0769
7.326% | 3 | C | 29656.4103 | Units | 12556.1905 | 17100.2198 | 0 | 0 | 0 | 0 | 0 | 0 | 11896.8498 | 0 | 36.63 | 3742.7106 | 0 | 165.4212 | 1822.6374 | 386.9597 | 80.5861 | 2424.8352 | 203.8828 | 232.8205 | 5205.2747 | 2260.0733 | 0 | 0 | 0 | 0 | 0 | 0 | 28458.6813
9.89% | 4 | D | 40036.1538 | Units | 16950.8571 | 23085.2967 | 0 | 0 | 0 | 0 | 0 | 0 | 16060.7473 | 0 | 49.4505 | 5052.6593 | 0 | 223.3187 | 2460.5604 | 522.3956 | 108.7912 | 3273.5275 | 275.2418 | 314.3077 | 7027.1209 | 3051.0989 | 0 | 0 | 0 | 0 | 0 | 0 | 38419.2198
6.593% | 5 | E | 26690.7692 | Units | 11300.5714 | 15390.1978 | 0 | 0 | 0 | 0 | 0 | 0 | 10707.1648 | 0 | 32.967 | 3368.4396 | 0 | 148.8791 | 1640.3736 | 348.2637 | 72.5275 | 2182.3516 | 183.4945 | 209.5385 | 4684.7473 | 2034.0659 | 0 | 0 | 0 | 0 | 0 | 0 | 25612.8132
5.495% | 6 | F | 22242.3077 | Units | 9417.1429 | 12825.1648 | 0 | 0 | 0 | 0 | 0 | 0 | 8922.6374 | 0 | 27.4725 | 2807.033 | 0 | 124.0659 | 1366.978 | 290.2198 | 60.4396 | 1818.6264 | 152.9121 | 174.6154 | 3903.956 | 1695.0549 | 0 | 0 | 0 | 0 | 0 | 0 | 21344.011
11.9% | 7 | G | 48191.6667 | Units | 20403.8095 | 27787.8571 | 0 | 0 | 0 | 0 | 0 | 0 | 19332.381 | 0 | 59.5238 | 6081.9048 | 0 | 268.8095 | 2961.7857 | 628.8095 | 130.9524 | 3940.3571 | 331.3095 | 378.3333 | 8458.5714 | 3672.619 | 0 | 0 | 0 | 0 | 0 | 0 | 46245.3571
9.158% | 8 | H | 37070.5128 | Units | 15695.2381 | 21375.2747 | 0 | 0 | 0 | 0 | 0 | 0 | 14871.0623 | 0 | 45.7875 | 4678.3883 | 0 | 206.7766 | 2278.2967 | 483.6996 | 100.7326 | 3031.044 | 254.8535 | 291.0256 | 6506.5934 | 2825.0916 | 0 | 0 | 0 | 0 | 0 | 0 | 35573.3516
10.07% | 9 | I | 40777.5641 | Units | 17264.7619 | 23512.8022 | 0 | 0 | 0 | 0 | 0 | 0 | 16358.1685 | 0 | 50.3663 | 5146.2271 | 0 | 227.4542 | 2506.1264 | 532.0696 | 110.8059 | 3334.1484 | 280.3388 | 320.1282 | 7157.2527 | 3107.6007 | 0 | 0 | 0 | 0 | 0 | 0 | 39130.6868
7.875% | 10 | J | 31880.641 | Units | 13497.9048 | 18382.7363 | 0 | 0 | 0 | 0 | 0 | 0 | 12789.1136 | 0 | 39.3773 | 4023.4139 | 0 | 177.8278 | 1959.3352 | 415.9817 | 86.63 | 2606.6978 | 219.174 | 250.2821 | 5595.6703 | 2429.5788 | 0 | 0 | 0 | 0 | 0 | 0 | 30593.0824
19.23% | 11 | K | 77848.0769 | Units | 32960 | 44888.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 31229.2308 | 0 | 96.1538 | 9824.6154 | 0 | 434.2308 | 4784.4231 | 1015.7692 | 211.5385 | 6365.1923 | 535.1923 | 611.1538 | 13663.8462 | 5932.6923 | 0 | 0 | 0 | 0 | 0 | 0 | 74704.0385
|  | Planned Total %: | 404810 |  | 171392 | 233418 | 0 | 0 | 0 | 0 | 0 | 0 | 162392 | 0 | 500 | 51088 | 0 | 2258 | 24879 | 5282 | 1100 | 33099 | 2783 | 3178 | 71052 | 30850 | 0 | 0 | 0 | 0 | 0 | 0 | 388461
[6 empty] | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
[6 empty] | Plan | 0 | 0 | 4048.1 | 14573.16 | 28741.51 | 33599.23 | 64769.6 | 80962 | 66793.65 | 50196.44 | 38861.76 | 22264.55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Cum Plan | 0 | 0 | 4048.1 | 18621.26 | 47362.77 | 80962 | 145731.6 | 226693.6 | 293487.25 | 343683.69 | 382545.45 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810 | 404810
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 162392 | 0 | 500 | 51088 | 0 | 2258 | 24879 | 5282 | 1100 | 33099 | 2783 | 3178 | 71052 | 30850 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 162392 | 162392 | 162892 | 213980 | 213980 | 216238 | 241117 | 246399 | 247499 | 280598 | 283381 | 286559 | 357611 | 388461 | 388461 | 388461
[6 empty] | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
[6 empty] | Plan | 0 | 0 | 1 | 3.6 | 7.1 | 8.3 | 16 | 20 | 16.5 | 12.4 | 9.6 | 5.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Cum Plan | 0 | 0 | 1 | 4.6 | 11.7 | 20 | 36 | 56 | 72.5 | 84.9 | 94.5 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
[6 empty] | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 40.1156 | 0 | 0.12351 | 12.6202 | 0 | 0.55779 | 6.1458 | 1.3048 | 0.27173 | 8.1764 | 0.68748 | 0.78506 | 17.5519 | 7.6209 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 40.1156 | 40.1156 | 40.2391 | 52.8594 | 52.8594 | 53.4172 | 59.563 | 60.8678 | 61.1395 | 69.316 | 70.0035 | 70.7885 | 88.3405 | 95.9613 | 95.9613 | 95.9613

## Pre-cast Erection S-Curve (hidden)
|  | Plan | [12 empty] | 5% | 10% | 15% | 15% | 15% | 15% | 10% | 10% | 5%
| # | Area | UoM | Scope | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01
| 1 | A |  | 8.855% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5934 | 26.7912 | 35 | 42 | 54 | 48 | 27.3956 | 21.3956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 76 |  | 2022-11-01: 2.1978; 2022-12-01: 8; 2023-01-01: 10; 2023-02-01: 12; 2023-03-01: 14; 2023-04-01: 12; 2023-05-01: 10; 2023-06-01: 8
| b | Erection-Track Beam without Nose | nos. | 0
| c | Erection-h - Section Beam | nos. | 38 |  | 2022-11-01: 2.1978; 2022-12-01: 4.3956; 2023-01-01: 5; 2023-02-01: 5; 2023-03-01: 7; 2023-04-01: 8; 2023-05-01: 4.3956; 2023-06-01: 2.1978
| d | Erection-U - Section Beam | nos. | 38 |  | 2022-11-01: 2.1978; 2022-12-01: 4.3956; 2023-01-01: 5; 2023-02-01: 5; 2023-03-01: 8; 2023-04-01: 8; 2023-05-01: 3; 2023-06-01: 2.1978
| e | Erection-Pre-cast Slab | nos. | 114 |  | 2022-11-01: 5; 2022-12-01: 10; 2023-01-01: 15; 2023-02-01: 20; 2023-03-01: 25; 2023-04-01: 20; 2023-05-01: 10; 2023-06-01: 9
| 2 | B |  | 6.325% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6154 | 15.2308 | 23 | 28 | 36 | 34 | 26 | 17.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 46 |  | 2022-10-01: 1.5385; 2022-11-01: 3.0769; 2022-12-01: 6; 2023-01-01: 7; 2023-02-01: 9; 2023-03-01: 10; 2023-04-01: 5; 2023-05-01: 4
| b | Erection-Track Beam without Nose | nos. | 48 |  | 2022-10-01: 1.5385; 2022-11-01: 3.0769; 2022-12-01: 7; 2023-01-01: 7; 2023-02-01: 8; 2023-03-01: 8; 2023-04-01: 8; 2023-05-01: 5
| c | Erection-h - Section Beam | nos. | 28 |  | 2022-10-01: 1.5385; 2022-11-01: 3.0769; 2022-12-01: 4; 2023-01-01: 4; 2023-02-01: 5; 2023-03-01: 5; 2023-04-01: 4; 2023-05-01: 1.5385
| d | Erection-U - Section Beam | nos. | 14 |  | 2023-01-01: 2; 2023-02-01: 4; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 1.5385
| e | Erection-Pre-cast Slab | nos. | 54 |  | 2022-10-01: 5; 2022-11-01: 6; 2022-12-01: 6; 2023-01-01: 8; 2023-02-01: 10; 2023-03-01: 8; 2023-04-01: 6; 2023-05-01: 5
| 3 | C |  | 6.125% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3956 | 18 | 24 | 28 | 36 | 32 | 23 | 14.5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 63 |  | 2022-10-01: 3; 2022-11-01: 6; 2022-12-01: 8; 2023-01-01: 10; 2023-02-01: 12; 2023-03-01: 10; 2023-04-01: 8; 2023-05-01: 6
| b | Erection-Track Beam without Nose | nos. | 30 |  | 2022-10-01: 2.1978; 2022-11-01: 3; 2022-12-01: 4; 2023-01-01: 4; 2023-02-01: 6; 2023-03-01: 5; 2023-04-01: 4; 2023-05-01: 2.1978
| c | Erection-h - Section Beam | nos. | 32 |  | 2022-10-01: 2.1978; 2022-11-01: 3; 2022-12-01: 4; 2023-01-01: 5; 2023-02-01: 6; 2023-03-01: 7; 2023-04-01: 3; 2023-05-01: 2
| d | Erection-U - Section Beam | nos. | 32 |  | 2022-11-01: 3; 2022-12-01: 5; 2023-01-01: 5; 2023-02-01: 6; 2023-03-01: 6; 2023-04-01: 5; 2023-05-01: 2.1978
| e | Erection-Pre-cast Slab | nos. | 27 |  | 2022-10-01: 2; 2022-11-01: 3; 2022-12-01: 3; 2023-01-01: 4; 2023-02-01: 6; 2023-03-01: 4; 2023-04-01: 3; 2023-05-01: 2.1978
| 4 | D |  | 11.38% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9341 | 33 | 34 | 40 | 47 | 49 | 41 | 33 | 26.9341 | 19.967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 84 |  | 2022-12-01: 5; 2023-01-01: 8; 2023-02-01: 8; 2023-03-01: 10; 2023-04-01: 12; 2023-05-01: 12; 2023-06-01: 10; 2023-07-01: 8; 2023-08-01: 5.9341; 2023-09-01: 5
| b | Erection-Track Beam without Nose | nos. | 83 |  | 2022-12-01: 2.967; 2023-01-01: 8; 2023-02-01: 8; 2023-03-01: 10; 2023-04-01: 12; 2023-05-01: 12; 2023-06-01: 10; 2023-07-01: 8; 2023-08-01: 7; 2023-09-01: 5
| c | Erection-h - Section Beam | nos. | 34 |  | 2022-12-01: 2; 2023-01-01: 3; 2023-02-01: 4; 2023-03-01: 5; 2023-04-01: 5; 2023-05-01: 4; 2023-06-01: 4; 2023-07-01: 3; 2023-08-01: 2; 2023-09-01: 2
| d | Erection-U - Section Beam | nos. | 45 |  | 2022-12-01: 2.967; 2023-01-01: 4; 2023-02-01: 4; 2023-03-01: 5; 2023-04-01: 6; 2023-05-01: 7; 2023-06-01: 5; 2023-07-01: 4; 2023-08-01: 4; 2023-09-01: 2.967
| e | Erection-Pre-cast Slab | nos. | 96 |  | 2022-12-01: 5; 2023-01-01: 10; 2023-02-01: 10; 2023-03-01: 10; 2023-04-01: 12; 2023-05-01: 14; 2023-06-01: 12; 2023-07-01: 10; 2023-08-01: 8; 2023-09-01: 5
| 5 | E |  | 6.325% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9341 | 12 | 17.8681 | 25.8022 | 25.8022 | 27.8022 | 29.8022 | 25.8681 | 13.9341 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 76 |  | 2022-11-01: 4; 2022-12-01: 6; 2023-01-01: 6; 2023-02-01: 8; 2023-03-01: 8; 2023-04-01: 10; 2023-05-01: 12; 2023-06-01: 14; 2023-07-01: 8
| b | Erection-Track Beam without Nose | nos. | 38 |  | 2022-11-01: 1.978; 2022-12-01: 2; 2023-01-01: 3.956; 2023-02-01: 5.9341; 2023-03-01: 5.9341; 2023-04-01: 5.9341; 2023-05-01: 5.9341; 2023-06-01: 3.956; 2023-07-01: 1.978
| c | Erection-h - Section Beam | nos. | 38 |  | 2022-11-01: 1.978; 2022-12-01: 2; 2023-01-01: 3.956; 2023-02-01: 5.9341; 2023-03-01: 5.9341; 2023-04-01: 5.9341; 2023-05-01: 5.9341; 2023-06-01: 3.956; 2023-07-01: 1.978
| d | Erection-U - Section Beam | nos. | 38 |  | 2022-11-01: 1.978; 2022-12-01: 2; 2023-01-01: 3.956; 2023-02-01: 5.9341; 2023-03-01: 5.9341; 2023-04-01: 5.9341; 2023-05-01: 5.9341; 2023-06-01: 3.956; 2023-07-01: 1.978
| e | Erection-Pre-cast Slab | nos. | 0
| 6 | F |  | 5.726% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2418 | 20.2967 | 24 | 26 | 27.9451 | 27 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 27 |  | 2022-11-01: 1.6484; 2022-12-01: 3.2967; 2023-01-01: 4; 2023-02-01: 4; 2023-03-01: 4.9451; 2023-04-01: 4; 2023-05-01: 3; 2023-06-01: 2
| b | Erection-Track Beam without Nose | nos. | 73 |  | 2022-11-01: 1.6484; 2022-12-01: 8; 2023-01-01: 10; 2023-02-01: 12; 2023-03-01: 10; 2023-04-01: 12; 2023-05-01: 10; 2023-06-01: 9
| c | Erection-h - Section Beam | nos. | 18 |  | 2022-11-01: 1.6484; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 3; 2023-04-01: 3; 2023-05-01: 2; 2023-06-01: 2
| d | Erection-U - Section Beam | nos. | 15 |  | 2022-11-01: 1.6484; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 2; 2023-05-01: 2; 2023-06-01: 1
| e | Erection-Pre-cast Slab | nos. | 39 |  | 2022-11-01: 1.6484; 2022-12-01: 5; 2023-01-01: 6; 2023-02-01: 6; 2023-03-01: 8; 2023-04-01: 6; 2023-05-01: 4; 2023-06-01: 2
| 7 | G |  | 8.156% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7143 | 22 | 31 | 36 | 39 | 41 | 36 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 61 |  | 2023-01-01: 3.5714; 2023-02-01: 5; 2023-03-01: 8; 2023-04-01: 8; 2023-05-01: 10; 2023-06-01: 10; 2023-07-01: 10; 2023-08-01: 6
| b | Erection-Track Beam without Nose | nos. | 55 |  | 2023-01-01: 3.5714; 2023-02-01: 5; 2023-03-01: 6; 2023-04-01: 8; 2023-05-01: 8; 2023-06-01: 10; 2023-07-01: 8; 2023-08-01: 6
| c | Erection-h - Section Beam | nos. | 38 |  | 2023-01-01: 2; 2023-02-01: 3; 2023-03-01: 5; 2023-04-01: 5; 2023-05-01: 6; 2023-06-01: 7; 2023-07-01: 6; 2023-08-01: 4
| d | Erection-U - Section Beam | nos. | 22 |  | 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 3; 2023-05-01: 3; 2023-06-01: 4; 2023-07-01: 4; 2023-08-01: 2
| e | Erection-Pre-cast Slab | nos. | 69 |  | 2023-01-01: 3.5714; 2023-02-01: 7; 2023-03-01: 10; 2023-04-01: 12; 2023-05-01: 12; 2023-06-01: 10; 2023-07-01: 8; 2023-08-01: 6
| 8 | H |  | 8.389% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 28 | 32 | 38 | 46 | 41 | 27.4945 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 50 |  | 2022-11-01: 4; 2022-12-01: 6; 2023-01-01: 6; 2023-02-01: 6; 2023-03-01: 6; 2023-04-01: 8; 2023-05-01: 8; 2023-06-01: 6
| b | Erection-Track Beam without Nose | nos. | 110 |  | 2022-11-01: 6; 2022-12-01: 10; 2023-01-01: 12; 2023-02-01: 16; 2023-03-01: 18; 2023-04-01: 20; 2023-05-01: 18; 2023-06-01: 10
| c | Erection-h - Section Beam | nos. | 40 |  | 2022-11-01: 2; 2022-12-01: 4; 2023-01-01: 6; 2023-02-01: 6; 2023-03-01: 6; 2023-04-01: 6; 2023-05-01: 6; 2023-06-01: 4
| d | Erection-U - Section Beam | nos. | 19 |  | 2022-11-01: 2; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 4; 2023-05-01: 3; 2023-06-01: 2
| e | Erection-Pre-cast Slab | nos. | 33 |  | 2022-11-01: 2; 2022-12-01: 2; 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 6; 2023-04-01: 8; 2023-05-01: 6; 2023-06-01: 5.4945
| 9 | I |  | 10.62% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.0879 | 26.0879 | 38 | 44 | 50 | 48 | 41 | 33 | 23.022 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 80 |  | 2023-01-01: 3.022; 2023-02-01: 6.044; 2023-03-01: 12; 2023-04-01: 12; 2023-05-01: 14; 2023-06-01: 12; 2023-07-01: 10; 2023-08-01: 6; 2023-09-01: 5
| b | Erection-Track Beam without Nose | nos. | 115 |  | 2023-01-01: 4; 2023-02-01: 6; 2023-03-01: 12; 2023-04-01: 14; 2023-05-01: 18; 2023-06-01: 20; 2023-07-01: 18; 2023-08-01: 14; 2023-09-01: 9
| c | Erection-h - Section Beam | nos. | 40 |  | 2023-01-01: 3.022; 2023-02-01: 4; 2023-03-01: 4; 2023-04-01: 6; 2023-05-01: 6; 2023-06-01: 6; 2023-07-01: 4; 2023-08-01: 4; 2023-09-01: 3.022
| d | Erection-U - Section Beam | nos. | 39 |  | 2023-01-01: 3.022; 2023-02-01: 4; 2023-03-01: 4; 2023-04-01: 6; 2023-05-01: 6; 2023-06-01: 4; 2023-07-01: 4; 2023-08-01: 4; 2023-09-01: 4
| e | Erection-Pre-cast Slab | nos. | 45 |  | 2023-01-01: 3.022; 2023-02-01: 6.044; 2023-03-01: 6; 2023-04-01: 6; 2023-05-01: 6; 2023-06-01: 6; 2023-07-01: 5; 2023-08-01: 5; 2023-09-01: 2
| 10 | J |  | 7.79% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4505 | 18.7253 | 29 | 33 | 36 | 38 | 28.7253 | 20 | 17.0879 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 78 |  | 2022-11-01: 4; 2022-12-01: 6; 2023-01-01: 10; 2023-02-01: 12; 2023-03-01: 12; 2023-04-01: 12; 2023-05-01: 10; 2023-06-01: 6; 2023-07-01: 6
| b | Erection-Track Beam without Nose | nos. | 60 |  | 2022-11-01: 2.3626; 2022-12-01: 4; 2023-01-01: 6; 2023-02-01: 8; 2023-03-01: 10; 2023-04-01: 12; 2023-05-01: 8; 2023-06-01: 6; 2023-07-01: 4
| c | Erection-h - Section Beam | nos. | 24 |  | 2022-11-01: 2.3626; 2022-12-01: 2; 2023-01-01: 3; 2023-02-01: 3; 2023-03-01: 3; 2023-04-01: 4; 2023-05-01: 2; 2023-06-01: 2; 2023-07-01: 2.3626
| d | Erection-U - Section Beam | nos. | 42 |  | 2022-11-01: 2.3626; 2022-12-01: 4.7253; 2023-01-01: 6; 2023-02-01: 6; 2023-03-01: 6; 2023-04-01: 6; 2023-05-01: 4.7253; 2023-06-01: 4; 2023-07-01: 2.3626
| e | Erection-Pre-cast Slab | nos. | 30 |  | 2022-11-01: 2.3626; 2022-12-01: 2; 2023-01-01: 4; 2023-02-01: 4; 2023-03-01: 5; 2023-04-01: 4; 2023-05-01: 4; 2023-06-01: 2; 2023-07-01: 2.3626
| 11 | K |  | 20.31% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5385 | 52.0769 | 69.3077 | 80.6154 | 93.3077 | 96.6154 | 75.0769 | 63.0769 | 42.5385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 142 |  | 2023-01-01: 10; 2023-02-01: 12; 2023-03-01: 16; 2023-04-01: 20; 2023-05-01: 24; 2023-06-01: 24; 2023-07-01: 20; 2023-08-01: 10; 2023-09-01: 6
| b | Erection-Track Beam without Nose | nos. | 199 |  | 2023-01-01: 14; 2023-02-01: 15; 2023-03-01: 18; 2023-04-01: 20; 2023-05-01: 28; 2023-06-01: 30; 2023-07-01: 26; 2023-08-01: 26; 2023-09-01: 22
| c | Erection-h - Section Beam | nos. | 39 |  | 2023-01-01: 2; 2023-02-01: 2; 2023-03-01: 2; 2023-04-01: 6; 2023-05-01: 6; 2023-06-01: 8; 2023-07-01: 6; 2023-08-01: 4; 2023-09-01: 3
| d | Erection-U - Section Beam | nos. | 116 |  | 2023-01-01: 5.7692; 2023-02-01: 11.5385; 2023-03-01: 17.3077; 2023-04-01: 17.3077; 2023-05-01: 18; 2023-06-01: 17.3077; 2023-07-01: 11.5385; 2023-08-01: 11.5385; 2023-09-01: 5.7692
| e | Erection-Pre-cast Slab | nos. | 114 |  | 2023-01-01: 5.7692; 2023-02-01: 11.5385; 2023-03-01: 16; 2023-04-01: 17.3077; 2023-05-01: 17.3077; 2023-06-01: 17.3077; 2023-07-01: 11.5385; 2023-08-01: 11.5385; 2023-09-01: 5.7692
|  | Planned Total: |  | 3004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.011 | 92.4505 | 166.7473 | 291.2088 | 364.967 | 426.0549 | 443.4176 | 410.9011 | 337.3736 | 216.0989 | 147.011 | 85.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual
| # | Area | UoM | Scope | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01
266 | 1 | A |  | 8.855% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188 | 90
| a | Erection-Track Beam with Nose | nos. | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 64
| b | Erection-Track Beam without Nose | nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
| d | Erection-U - Section Beam | nos. | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32
| e | Erection-Pre-cast Slab | nos. | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60
190 | 2 | B |  | 6.325% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 62
| a | Erection-Track Beam with Nose | nos. | 46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
| b | Erection-Track Beam without Nose | nos. | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| c | Erection-h - Section Beam | nos. | 28 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10
| d | Erection-U - Section Beam | nos. | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| e | Erection-Pre-cast Slab | nos. | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18
184 | 3 | C |  | 6.125% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55 | 5 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 63 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| b | Erection-Track Beam without Nose | nos. | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 17 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| d | Erection-U - Section Beam | nos. | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| e | Erection-Pre-cast Slab | nos. | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0
342 | 4 | D |  | 11.38% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 68 | 154 | 0 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 355
| a | Erection-Track Beam with Nose | nos. | 84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 24 | 30 | 0 | 18 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82
| b | Erection-Track Beam without Nose | nos. | 83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 47 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 90
| c | Erection-h - Section Beam | nos. | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 8 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31
| d | Erection-U - Section Beam | nos. | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 18 | 10 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44
| e | Erection-Pre-cast Slab | nos. | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 59 | 0 | 12 | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 108
190 | 5 | E |  | 6.325% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 76 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| b | Erection-Track Beam without Nose | nos. | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| d | Erection-U - Section Beam | nos. | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| e | Erection-Pre-cast Slab | nos. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
172 | 6 | F |  | 5.726% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 80 | 68 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 18 | 13 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| b | Erection-Track Beam without Nose | nos. | 73 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 42 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 7 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| d | Erection-U - Section Beam | nos. | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| e | Erection-Pre-cast Slab | nos. | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
245 | 7 | G |  | 8.156% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| b | Erection-Track Beam without Nose | nos. | 55 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 38 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| d | Erection-U - Section Beam | nos. | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| e | Erection-Pre-cast Slab | nos. | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
252 | 8 | H |  | 8.389% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 91 | 6 | 18 | 23 | 0 | 8 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 129
| a | Erection-Track Beam with Nose | nos. | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 11 | 1 | 6 | 8 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 23
| b | Erection-Track Beam without Nose | nos. | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 72 | 4 | 7 | 6 | 0 | 2 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 87
| c | Erection-h - Section Beam | nos. | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 0 | 2 | 3 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11
| d | Erection-U - Section Beam | nos. | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1 | 1 | 3 | 6 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 8
| e | Erection-Pre-cast Slab | nos. | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33 | 0 | 0 | 0 | 0 | 0 | 0 | 0
319 | 9 | I |  | 10.62% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 86 | 51 | 8 | 24 | 0 | 10 | 4 | 0 | 4 | 50 | 0 | 0 | 0 | 0 | 0 | 229
| a | Erection-Track Beam with Nose | nos. | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17 | 22 | 21 | 2 | 7 | 0 | 4 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 69
| b | Erection-Track Beam without Nose | nos. | 115 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 24 | 0 | 4 | 0 | 6 | 0 | 0 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 78
| c | Erection-h - Section Beam | nos. | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 11 | 3 | 2 | 6 | 0 | 0 | 2 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 26
| d | Erection-U - Section Beam | nos. | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 3 | 3 | 1 | 1 | 0 | 0 | 2 | 0 | 2 | 10 | 0 | 0 | 0 | 0 | 0 | 23
| e | Erection-Pre-cast Slab | nos. | 45 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 3 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33
234 | 10 | J |  | 7.79% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| b | Erection-Track Beam without Nose | nos. | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| d | Erection-U - Section Beam | nos. | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| e | Erection-Pre-cast Slab | nos. | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
610 | 11 | K |  | 20.31% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Erection-Track Beam with Nose | nos. | 142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| b | Erection-Track Beam without Nose | nos. | 199 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| c | Erection-h - Section Beam | nos. | 39 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| d | Erection-U - Section Beam | nos. | 116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| e | Erection-Pre-cast Slab | nos. | 114 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0
|  | Actual Total: |  | 3004 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 35 | 68 | 214 | 138 | 114 | 148 | 112 | 126 | 68 | 109 | 161 | 148 | 55 | 0 | 0 | 0 | 0 | 0 | 963
|  |  |  | Quantity | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01
|  |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.011 | 92.4505 | 166.7473 | 291.2088 | 364.967 | 426.0549 | 443.4176 | 410.9011 | 337.3736 | 216.0989 | 147.011 | 85.5275 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19.011 | 111.4615 | 278.2088 | 569.4176 | 934.3846 | 1360.4396 | 1803.8571 | 2214.7582 | 2552.1319 | 2768.2308 | 2915.2418 | 3000.7692 | 3000.7692 | 3000.7692 | 3000.7692 | 3000.7692 | 3000.7692 | 3000.7692 | 3000.7692 | 3000.7692
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 35 | 68 | 214 | 138 | 114 | 148 | 112 | 126 | 68 | 109 | 161 | 148 | 55
|  |  |  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 43 | 111 | 325 | 463 | 577 | 725 | 837 | 963 | 1031 | 1140 | 1301 | 1449 | 1504
[19 empty] | 1489.7582 | 1715.1319 | 1805.2308 | 1884.2418 | 1860.7692 | 1699.7692 | 1551.7692 | 1496.7692 | 3000.7692
|  |  |  | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01
|  |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63286 | 3.0776 | 5.5508 | 9.694 | 12.1494 | 14.1829 | 14.7609 | 13.6785 | 11.2308 | 7.1937 | 4.8938 | 2.8471 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.63286 | 3.7104 | 9.2613 | 18.9553 | 31.1047 | 45.2876 | 60.0485 | 73.727 | 84.9578 | 92.1515 | 97.0453 | 99.8925 | 99.8925 | 99.8925 | 99.8925 | 99.8925 | 99.8925 | 99.8925 | 99.8925 | 99.8925
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26631 | 1.1651 | 2.2636 | 7.1238 | 4.5939 | 3.7949 | 4.9268 | 3.7284 | 4.1944 | 2.2636 | 3.6285 | 5.3595 | 4.9268 | 1.8309
|  |  |  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.26631 | 1.4314 | 3.6951 | 10.8189 | 15.4128 | 19.2077 | 24.1345 | 27.8628 | 32.0573 | 34.3209 | 37.9494 | 43.3089 | 48.2357 | 50.0666
|  |  |  | Area | A | B | C | D | E | F | G | H | I | J | K
|  | Activity | UoM | Scope | 8.855% | 6.325% | 6.125% | 11.38% | 6.325% | 5.726% | 8.156% | 8.389% | 10.62% | 7.79% | 20.31%
|  | Erection of Solid Girder with Nose | No's | 783 | 76 | 46 | 63 | 84 | 76 | 27 | 61 | 50 | 80 | 78 | 142
|  | Erection of Solid Girder without Nose | No's | 811 | 0 | 48 | 30 | 83 | 38 | 73 | 55 | 110 | 115 | 60 | 199
|  | Erection of h-Girder | No's | 369 | 38 | 28 | 32 | 34 | 38 | 18 | 38 | 40 | 40 | 24 | 39
|  | Erection of U-Girder | No's | 420 | 38 | 14 | 32 | 45 | 38 | 15 | 22 | 19 | 39 | 42 | 116
|  | Erection of Pre-cast Slab | No's | 621 | 114 | 54 | 27 | 96 | 0 | 39 | 69 | 33 | 45 | 30 | 114
|  |  |  | 3004 | 266 | 190 | 184 | 342 | 190 | 172 | 245 | 252 | 319 | 234 | 610
|  | Plan | UoM |  | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  | Erection-Track Beam with Nose | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.5385 | 24.9231 | 48.2967 | 77.5934 | 94.044 | 110.9451 | 111 | 113 | 92 | 62 | 27.9341 | 16 | 0 | 0 | 0 | [5 empty] | 782.2747
|  | Erection-Track Beam without Nose | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7363 | 18.0659 | 37.967 | 72.5275 | 89.9341 | 102.9341 | 115.9341 | 115.1319 | 98.956 | 65.978 | 53 | 36 | 0 | 0 | 0 | [5 empty] | 810.1648
|  | Erection-h - Section Beam | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.7363 | 16.2637 | 24.3956 | 38.978 | 45.9341 | 52.9341 | 55.9341 | 45.8681 | 39.1538 | 23.3407 | 14 | 8.022 | 0 | 0 | 0 | [5 empty] | 368.5604
|  | Erection-U - Section Beam | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.1868 | 23.0879 | 40.7473 | 52.4725 | 61.2418 | 66.2418 | 56.3956 | 43.4615 | 27.8791 | 21.5385 | 12.7363 | 0 | 0 | 0 | [5 empty] | 418.989
|  | Erection-Pre-cast Slab | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 20.011 | 33 | 61.3626 | 82.5824 | 98 | 94.3077 | 80.5055 | 63.8022 | 36.9011 | 30.5385 | 12.7692 | 0 | 0 | 0 | [5 empty] | 620.7802
|  | Actual | UoM |  | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  | Erection-Track Beam with Nose | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 24 | 47 | 37 | 44 | 15 | 40 | 37 | 22 | 23 | 36 | 26 | 22 | [5 empty] | 301
|  | Erection-Track Beam without Nose | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 15 | 47 | 54 | 28 | 80 | 8 | 11 | 12 | 41 | 71 | 53 | 11 | [5 empty] | 316
|  | Erection-h - Section Beam | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 11 | 12 | 19 | 11 | 11 | 22 | 18 | 8 | 10 | 19 | 7 | 10 | [5 empty] | 128
|  | Erection-U - Section Beam | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 18 | 25 | 10 | 19 | 2 | 18 | 18 | 11 | 11 | 14 | 8 | 12 | [5 empty] | 137
|  | Erection-Pre-cast Slab | No's |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 83 | 18 | 12 | 40 | 24 | 42 | 15 | 24 | 21 | 54 | 0 | [5 empty] | 258
|  |  |  | Plan | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  |  | 0 | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11.5934 | 26.7912 | 35 | 42 | 54 | 48 | 27.3956 | 21.3956 | 0 | 0 | 0 | 0 | 0 | 0 | 266.1758 | [5 empty] | 266.1758
|  |  | 0 | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6154 | 15.2308 | 23 | 28 | 36 | 34 | 26 | 17.0769 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 188.9231 | [5 empty] | 188.9231
|  |  | 0 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3956 | 18 | 24 | 28 | 36 | 32 | 23 | 14.5934 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 184.989 | [5 empty] | 184.989
|  |  | 46.9011 | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.9341 | 33 | 34 | 40 | 47 | 49 | 41 | 33 | 26.9341 | 19.967 | 0 | 0 | 0 | 341.8352 | [5 empty] | 294.9341
|  |  | 0 | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9341 | 12 | 17.8681 | 25.8022 | 25.8022 | 27.8022 | 29.8022 | 25.8681 | 13.9341 | 0 | 0 | 0 | 0 | 0 | 188.8132 | [5 empty] | 188.8132
|  |  | 0 | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2418 | 20.2967 | 24 | 26 | 27.9451 | 27 | 21 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 170.4835 | [5 empty] | 170.4835
|  |  | 24 | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7143 | 22 | 31 | 36 | 39 | 41 | 36 | 24 | 0 | 0 | 0 | 0 | 243.7143 | [5 empty] | 219.7143
|  |  | 0 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 28 | 32 | 38 | 46 | 41 | 27.4945 | 0 | 0 | 0 | 0 | 0 | 0 | 252.4945 | [5 empty] | 252.4945
|  |  | 56.022 | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.0879 | 26.0879 | 38 | 44 | 50 | 48 | 41 | 33 | 23.022 | 0 | 0 | 0 | 319.1978 | [5 empty] | 263.1758
|  |  | 0 | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4505 | 18.7253 | 29 | 33 | 36 | 38 | 28.7253 | 20 | 17.0879 | 0 | 0 | 0 | 0 | 0 | 233.989 | [5 empty] | 233.989
|  |  | 105.6154 | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5385 | 52.0769 | 69.3077 | 80.6154 | 93.3077 | 96.6154 | 75.0769 | 63.0769 | 42.5385 | 0 | 0 | 0 | 610.1538 | [5 empty] | 504.5385
232.5385
|  |  |  | Actual | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01
|  |  |  | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 98 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 188
|  |  |  | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 62
|  |  |  | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 55 | 5 | [6 empty] | 0
|  |  |  | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 68 | 154 | 0 | 49 | 49 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 355
|  |  |  | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0
|  |  |  | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21 | 80 | 68 | 13 | 0 | [6 empty] | 0
|  |  |  | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 82 | 0 | 0 | [6 empty] | 0
|  |  |  | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 91 | 6 | 18 | 23 | 0 | 8 | 47 | 0 | [6 empty] | 129
|  |  |  | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 86 | 51 | 8 | 24 | 0 | 10 | 4 | 0 | 4 | 50 | [6 empty] | 229
|  |  |  | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 | 25 | 0 | 0 | 0 | [6 empty] | 0
|  |  |  | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | [6 empty] | 0
|  |  |  | Difference | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01
|  |  | 78.1758 | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5934 | 26.7912 | 35 | 42 | 54 | 48 | 27.3956 | -60.6044 | -98 | 0 | 0 | 0 | 0 | 0
|  |  | 126.9231 | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.6154 | 15.2308 | 23 | 28 | 36 | -18 | 26 | 17.0769 | 0 | -10 | 0 | 0 | 0 | 0 | 0
|  |  | 184.989 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.3956 | 18 | 24 | 28 | 36 | 32 | 23 | 14.5934 | 0 | 0 | 0 | 0 | -3 | -55 | -5
|  |  | -60.0659 | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -17.0659 | -35 | -120 | 40 | -2 | 0 | 41 | 33 | 26.9341 | 19.967 | 0 | 0 | 0
|  |  | 188.8132 | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9.9341 | 12 | 17.8681 | 25.8022 | 25.8022 | 27.8022 | 29.8022 | 25.8681 | 13.9341 | 0 | 0 | 0 | 0 | 0
|  |  | 170.4835 | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.2418 | 20.2967 | 24 | 26 | 27.9451 | 27 | 21 | 16 | 0 | -21 | -80 | -68 | -13 | 0
|  |  | 219.7143 | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14.7143 | 22 | 31 | 36 | 39 | 41 | 36 | 24 | 0 | -82 | 0 | 0
|  |  | 123.4945 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 24 | 28 | 32 | 38 | 32 | -50 | 21.4945 | -18 | -23 | 0 | -8 | -47 | 0
|  |  | 34.1758 | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.0879 | -33.9121 | -48 | -7 | 42 | 24 | 41 | 23 | 19.022 | 0 | -4 | -50
|  |  | 233.989 | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.4505 | 18.7253 | 29 | 33 | 36 | 38 | 28.7253 | 20 | 17.0879 | -14 | -25 | 0 | 0 | 0
|  |  | 504.5385 | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.5385 | 52.0769 | 69.3077 | 80.6154 | 93.3077 | 96.6154 | 75.0769 | 63.0769 | 42.5385 | 0 | -29 | 0
1805.2308
|  |  |  | Balance Distribution | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01
|  |  | 78.1758 | A
|  |  | 126.9231 | B
|  |  | 184.989 | C
|  |  | -13.1648 | D
|  |  | 188.8132 | E
|  |  | 170.4835 | F
|  |  | 243.7143 | G
|  |  | 123.4945 | H
|  |  | 90.1978 | I
|  |  | 233.989 | J
|  |  | 610.1538 | K
|  |  | 2037.7692 | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Catch-up | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 |  |  |  |  | 2024-02-01 | 2024-03-01 | 2024-04-01
|  |  |  | A | 2023-08-01: 0; 2023-11-01: 16; 2023-12-01: 62 | [7 empty] | 0.17582
|  |  |  | B | 2023-08-01: 0; 2023-11-01: 47; 2023-12-01: 80 | [7 empty] | -0.076923
|  |  |  | C | 2023-08-01: 72; 2023-12-01: 20; 2024-01-01: 30 |  |  |  |  | 39 | 24 |  | -0.010989
|  |  |  | D | 2023-08-01: 0 | [7 empty] | -13.1648
|  |  |  | E | 2023-08-01: 0; 2023-11-01: 89 |  |  |  |  | 100 |  |  | -0.18681
|  |  |  | F | 2023-08-01: 0; 2023-10-01: 170 | [7 empty] | 0.48352
|  |  |  | G | 2023-08-01: 0; 2023-12-01: 44; 2024-01-01: 80 |  |  |  |  | 120 |  |  | -0.28571
|  |  |  | H | 2023-08-01: 53; 2023-10-01: 70 | [7 empty] | 0.49451
|  |  |  | I | 2023-08-01: 0; 2023-10-01: 90 | [7 empty] | 0.1978
|  |  |  | J | 2023-08-01: 0; 2023-12-01: 80; 2024-01-01: 154 | [7 empty] | -0.010989
|  |  |  | K | 2023-08-01: 0; 2023-11-01: 40; 2023-12-01: 40; 2024-01-01: 50 |  |  |  |  | 180 | 300 |  | 0.15385
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | 330 | 192 | 326 | 314 |  |  |  |  | 439 | 324 | 0 | -12.2308

## Mechanical S-Curve (hidden)
|  | Plan | [17 empty] | 10% | 15% | 30% | 30% | 15%
| # | Area | UoM | Scope | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
| 1 | A |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1209 | 118.6813 | 118.6813 | 44 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 360.4835
| a | Track Laying | RM | 360 |  | 2023-04-01: 79.1209; 2023-05-01: 118.6813; 2023-06-01: 118.6813; 2023-07-01: 44 |  | 0.48352
| 2 | B |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.3846 | 83.0769 | 83.0769 | 78 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 299.5385
| a | Track Laying | RM | 300 |  | 2023-03-01: 55.3846; 2023-04-01: 83.0769; 2023-05-01: 83.0769; 2023-06-01: 78 |  | -0.46154
| 3 | C |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1209 | 124 | 134 | 113 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450.1209
| a | Track Laying | RM | 450 |  | 2023-03-01: 79.1209; 2023-04-01: 124; 2023-05-01: 134; 2023-06-01: 113 |  | 0.12088
| 4 | D |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 180 | 180 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 620
| a | Track Laying | RM | 620 |  | 2023-07-01: 120; 2023-08-01: 180; 2023-09-01: 180; 2023-10-01: 140 |  | 0
| 5 | E |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.4066 | 106.8132 | 106.8132 | 58 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 325.033
| a | Track Laying | RM | 325 |  | 2023-05-01: 53.4066; 2023-06-01: 106.8132; 2023-07-01: 106.8132; 2023-08-01: 58 |  | 0.032967
| 6 | F |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.5055 | 89.011 | 89.011 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 278.5275
| a | Track Laying | RM | 279 |  | 2023-04-01: 44.5055; 2023-05-01: 89.011; 2023-06-01: 89.011; 2023-07-01: 56 |  | -0.47253
| 7 | G |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.4286 | 174 | 140 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 450.4286
| a | Track Laying | RM | 450 |  | 2023-06-01: 96.4286; 2023-07-01: 174; 2023-08-01: 140; 2023-09-01: 40 |  | 0.42857
| 8 | H |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.1758 | 148.3516 | 124 | 109 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.5275
| a | Track Laying | RM | 456 |  | 2023-04-01: 74.1758; 2023-05-01: 148.3516; 2023-06-01: 124; 2023-07-01: 109 |  | -0.47253
| 9 | I |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.5934 | 163.1868 | 163.1868 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 563.967
| a | Track Laying | RM | 564 |  | 2023-07-01: 81.5934; 2023-08-01: 163.1868; 2023-09-01: 163.1868; 2023-10-01: 156 |  | -0.032967
| 10 | J |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7912 | 127.5824 | 85 | 81 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 357.3736
| a | Track Laying | RM | 357 |  | 2023-05-01: 63.7912; 2023-06-01: 127.5824; 2023-07-01: 85; 2023-08-01: 81 |  | 0.37363
| 11 | K |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8462 | 155.7692 | 311.5385 | 300 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 991.1538
| a | Track Laying | RM | 991 |  | 2023-06-01: 103.8462; 2023-07-01: 155.7692; 2023-08-01: 311.5385; 2023-09-01: 300; 2023-10-01: 120 |  | 0.15385
|  | Planned Total: |  | 5152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.5055 | 404.8791 | 690.3187 | 957.3626 | 932.1758 | 933.7253 | 683.1868 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual
| # | Area | UoM | Scope | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-01-01
| 1 | A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 360 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | B |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3 | C |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4 | D |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 620 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 420 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 5 | E |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 6 | F |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 279 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 7 | G |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 8 | H |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 456 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 9 | I |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 564 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 10 | J |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 357 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 11 | K |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| a | Track Laying | RM | 991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Actual Total: |  | 5152 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 420 | 288 | 0 | 0 | 0 | 470 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Quantity | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
|  |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.5055 | 404.8791 | 690.3187 | 957.3626 | 932.1758 | 933.7253 | 683.1868 | 416 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.5055 | 539.3846 | 1229.7033 | 2187.0659 | 3119.2418 | 4052.967 | 4736.1538 | 5152.1538 | 5152.1538 | 5152.1538 | 5152.1538 | 5152.1538 | 5152.1538 | 5152.1538 | 5152.1538 | 5152.1538
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 420 | 288 | 0 | 0 | 0
|  |  |  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 200 | 620 | 908 | 908 | 908 | 908
[19 empty] | 1029.7033 | 1987.0659
|  |  |  | % | Till Mar-22 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01
|  |  |  | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6107 | 7.8587 | 13.399 | 18.5823 | 18.0935 | 18.1235 | 13.2606 | 8.0745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Cum Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.6107 | 10.4694 | 23.8685 | 42.4508 | 60.5443 | 78.6678 | 91.9285 | 100.003 | 100.003 | 100.003 | 100.003 | 100.003 | 100.003 | 100.003 | 100.003 | 100.003
|  |  |  | Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.882 | 0 | 8.1522 | 5.5901 | 0 | 0 | 0
|  |  |  | Cum Actual | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.882 | 3.882 | 12.0342 | 17.6242 | 17.6242 | 17.6242 | 17.6242
|  | 5152 |  | Plan | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
A | 7.326% | 360 | 0 | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1209 | 118.6813 | 118.6813 | 44 | 0 | 0 | 0 | 0 | 0
B | 5.128% | 300 | 0 | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.3846 | 83.0769 | 83.0769 | 78 | 0 | 0 | 0 | 0 | 0 | 0
C | 7.326% | 450 | 0 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1209 | 124 | 134 | 113 | 0 | 0 | 0 | 0 | 0 | 0
D | 9.89% | 620 | 500 | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 | 180 | 180 | 140 | 0 | 0
E | 6.593% | 325 | 58 | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.4066 | 106.8132 | 106.8132 | 58 | 0 | 0 | 0 | 0
F | 5.495% | 279 | 0 | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.5055 | 89.011 | 89.011 | 56 | 0 | 0 | 0 | 0 | 0
G | 11.9% | 450 | 180 | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.4286 | 174 | 140 | 40 | 0 | 0 | 0
H | 9.158% | 456 | 0 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.1758 | 148.3516 | 124 | 109 | 0 | 0 | 0 | 0 | 0
I | 10.07% | 564 | 482.3736 | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.5934 | 163.1868 | 163.1868 | 156 | 0 | 0
J | 7.875% | 357 | 81 | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7912 | 127.5824 | 85 | 81 | 0 | 0 | 0 | 0
K | 19.23% | 991 | 731.5385 | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8462 | 155.7692 | 311.5385 | 300 | 120 | 0 | 0
2032.9121
|  |  |  | Actual | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  |  | 288 | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 288 | 0 | 0 | 0 | 0
|  |  | 0 | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 620 | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | 420 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 470 | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 470
|  |  | 0 | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1378
|  |  |  | Difference | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  |  | 360.4835 | A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1209 | 118.6813 | 118.6813 | 44 | -288 | 0 | 0 | 0 | 0
|  |  | 299.5385 | B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55.3846 | 83.0769 | 83.0769 | 78 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 450.1209 | C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 79.1209 | 124 | 134 | 113 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | -500 | D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -200 | 0 | -300 | 180 | 180 | 140 | 0 | 0
|  |  | 267.033 | E | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53.4066 | 106.8132 | 106.8132 | 58 | 0 | 0 | 0 | 0
|  |  | 278.5275 | F | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44.5055 | 89.011 | 89.011 | 56 | 0 | 0 | 0 | 0 | 0
|  |  | 270.4286 | G | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 96.4286 | 174 | 140 | 40 | 0 | 0 | 0
|  |  | 455.5275 | H | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74.1758 | 148.3516 | 124 | 109 | 0 | 0 | 0 | 0 | 0
|  |  | 81.5934 | I | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 81.5934 | 163.1868 | 163.1868 | 156 | 0 | -470
|  |  | 276.3736 | J | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 63.7912 | 127.5824 | 85 | 81 | 0 | 0 | 0 | 0
|  |  | 259.6154 | K | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 103.8462 | 155.7692 | 311.5385 | 300 | 120 | 0 | 0
2499.2418
|  |  |  | Balance Distribution | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01
|  |  | 360.4835 | A | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 100; 2023-07-01: 150; 2023-08-01: 146
|  |  | 299.5385 | B | 2023-03-01: 55.3846; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 177; 2023-10-01: 100
|  |  | 450.1209 | C | 2023-03-01: 79.1209; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 200; 2023-10-01: 196
|  |  | 0 | D | 2023-03-01: 0; 2023-04-01: 100; 2023-05-01: 150; 2023-06-01: 150; 2023-07-01: 134
|  |  | 325.033 | E | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 100; 2023-08-01: 156; 2023-09-01: 100
|  |  | 278.5275 | F | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 150; 2023-09-01: 147
|  |  | 450.4286 | G | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 200; 2023-09-01: 243; 2023-10-01: 200
|  |  | 455.5275 | H | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 250; 2023-10-01: 245
|  |  | 563.967 | I | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 100; 2023-06-01: 175; 2023-07-01: 175; 2023-08-01: 94
|  |  | 357.3736 | J | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 0; 2023-08-01: 0; 2023-09-01: 215; 2023-10-01: 210
|  |  | 991.1538 | K | 2023-03-01: 0; 2023-04-01: 0; 2023-05-01: 0; 2023-06-01: 0; 2023-07-01: 250; 2023-08-01: 300; 2023-09-01: 300; 2023-10-01: 188
|  |  | 4532.1538 | Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 134.5055 | 100 | 250 | 425 | 809 | 1046 | 1632 | 1139 | 0 | 0
|  |  |  | Catch-up | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | [6 empty] | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01
|  |  |  | A | 2023-08-01: 150; 2023-09-01: 138 | [6 empty] | 72 |  |  |  |  | 0.48352
|  |  |  | B | 2023-08-01: 90; 2023-09-01: 20; 2023-10-01: 37 | [6 empty] | 153 |  |  |  |  | -0.46154
|  |  |  | C | [28 empty] | 110 | 125 | 115 | 100 |  | 0.12088
|  |  |  | D | [33 empty] | 0 | bar: 2023-09-01
|  |  |  | E | 2023-12-01: 70 | [6 empty] | 100 | 100 | 55 |  |  | 0.032967
|  |  |  | F | 2023-09-01: 149; 2023-10-01: 130 | [11 empty] | -0.47253
|  |  |  | G | [29 empty] | 260 | 190 |  |  | 0.42857
|  |  |  | H | 2023-09-01: 140; 2023-10-01: 140; 2023-11-01: 105; 2023-12-01: 71 | [11 empty] | -0.47253
|  |  |  | I | 2023-09-01: 200; 2023-10-01: 264; 2023-11-01: 100 | [11 empty] | -0.032967
|  |  |  | J | 2023-11-01: 100; 2023-12-01: 120 | [6 empty] | 72 | 65 |  |  |  | 0.37363
|  |  |  | K | 2023-12-01: 120 | [6 empty] | 280 | 260 | 191 | 140 |  | 0.15385
|  |  |  | Total: | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 240 | 647 | 571 | 305 | 381 | [6 empty] | 787 | 810 | 551 | 240 | 0 | 0.15385

## Month-wise Plan (hidden)
Plan month wise in Cum
Sr. No. | Activity | Scope in Cum | Scope in Km | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-23 | 2024-01-24 | 2024-02-24 | 2024-03-24 | 2024-04-24
1 | PCC | 1655 |  | 0 | 600 | 50 | 154 | 120 | 120 | 120 | 150 | 180 | 0 | 147 | 138 | 120 | 150 | 81 | 216 | 36 | 60 | 159 | 0 | 108 | 24 | 69 | 66
2 | RCC Foundation | 10211 |  | 0 | 0 |  | 952 | 846 | 846 | 846 | 1269 | 1269 | 1100 | 1296 | 920 | 880 | 1000 | 540 | 1100 | 240 | 400 | 740 | 0 | 600 | 360 | 460 | 480
3 | Step Footing | 2550 |  |  |  |  | 250 | 222 | 222 | 222 | 295 | 333 | 242 | 231 | 230 | 220 | 250 | 135 | 160 | 60 | 100 | 185 | 50 | 150 | 110 | 115 | 120
4 | Pier 1900 mm | 3270 |  | 0 | 0 |  | 170 | 227 | 173 | 230.8 | 255 | 284 | 303 | 228 | 408 | 402 | 336 | 336 | 330 | 132 | 120 | 120 | 72 | 240 | 234 | 222 | 144
5 | Pier 1600 mm | 5546 |  | 0 | 0 |  | 0 | 80 | 66 | 126 | 240 | 360 | 185 | 390 | 360 | 546 | 420 | 310 | 505 | 500 | 750 | 850 | 600 | 500 | 510 | 500 | 500
6 | Pier Cap | 8075 |  | 0 | 0 |  | 0 |  |  | 120 | 269 | 187 | 325 | 180 | 250 | 340 | 620 | 560 | 535 | 355 | 320 | 300 | 604 | 506 | 600 | 560 | 438
7 | Track Beam with Nose | 8981 |  | 0 | 0 |  | 0 |  |  | 239.76 | 230 | 418 | 600 | 540 | 1068 | 1140 | 1092 | 1092 | 1140 | 1140 | 1080 | 720 | 720 | 720 | 720 | 996 | 480
8 | Track Beam without Nose | 9585 |  | 0 | 0 |  | 0 |  |  | 229.6 | 180 | 366 | 402 | 660 | 888 | 1080 | 936 | 936 | 960 | 960 | 1020 | 720 | 720 | 720 | 720 | 408 | 480
9 | h - Section Beam | 4483 |  | 0 | 0 |  | 0 |  |  | 187 | 76 | 366 | 252 | 300 | 336 | 360 | 312 | 312 | 336 | 336 | 336 | 300 | 240 | 240 | 240 | 420 | 324
10 | U - Section Beam | 4260 |  | 0 | 0 |  | 0 |  |  | 181 | 66 | 261 | 219 | 300 | 324 | 360 | 312 | 312 | 336 | 336 | 336 | 300 | 240 | 240 | 240 | 276 | 276
11 | Pre-cast Slab | 351 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 35 | 35 | 38 | 38 | 30 | 30 | 30 | 30 | 30 | 20 | 20
12 | Abutment wall- PART-A | 491 |  | 2023-10-01: 60; 2023-11-01: 90; 2023-12-23: 60
13 | Abutment wall- PART-D | 830 |  | 2023-10-01: 500; 2023-11-01: 120; 2023-12-23: 120
14 | Cast In-situ slab- 1- PART-G | 471 |  | 2023-10-01: 0; 2023-11-01: 0; 2023-12-23: 0
15 | Cast In-situ slab- 2- PART-G | 1141 |  | 2023-10-01: 0; 2023-11-01: 529; 2023-12-23: 529
16 | Cast In-situ slab- PART-C | 650 |  | 2023-10-01: 650; 2023-11-01: 0; 2023-12-23: 0
17 | Erection-Track Beam with Nose | 7192.8 |  | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 4 | 244 | 720 | 984 | 468 | 324 | 27 | 720 | 348 | 228 | 336 | 192 | 84 | 144
18 | Erection-Track Beam without Nose | 6888 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 480 | 324 | 624 | 48 | 1344 | 78 | 0 | 336 | 96 | 492 | 240 | 504 | 168
19 | Erection-h - Section Beam | 5610 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 122 | 288 | 432 | 228 | 48 | 13 | 360 | 204 | 120 | 108 | 60 | 36 | 48
20 | Erection-U - Section Beam | 5430 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 122 | 396 | 360 | 216 | 168 | 16 | 360 | 156 | 96 | 96 | 120 | 60 | 48
21 | Erection-Pre-cast Slab | 4000 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 48 | 0 | 684 | 108 | 27 | 1080 | 46.5 | 324 | 288 | 216 | 36 | 36
22 | Track Laying |  | 4.5 | 0 | 0 |  | 0 | 0 | 0 | 2502.16 | 3030 | 4024 | 3628 | 4272 | 4972 | 5498 | 5463 | 4649 | 5656 | 4133 | 4552 | 4424 | 3276 | 4054 | 4998 | 4785 | 4037 | 0 | 0 | 0 | 0
Total
Plan month wise in Numbers
Sr. No. | Activity | Scope in Nos. | Scope in Km | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-23 | 2024-01-24 | 2024-02-24 | 2024-03-24 | 2024-04-24
1 | PCC | 468 |  | 0 | 0 | 17 | 52 | 50 | 40 | 40 | 50 | 60 | 0 | 42 | 46 | 40 | 50 | 27 | 72 | 12 | 20 | 53 | 0 | 36 | 0 | 0 | 0
2 | RCC Foundation | 468 |  | 0 | 0 |  | 45 | 40 | 40 | 40 | 60 | 60 | 44 | 42 | 46 | 44 | 50 | 27 | 55 | 12 | 20 | 37 | 0 | 30 | 3200 | 0 | 0
3 | Step Footing | 468 |  |  |  |  | 45 | 40 | 40 | 40 | 60 | 60 | 44 | 54 | 46 | 44 | 50 | 27 | 32 | 12 | 20 | 37 | 10 | 30 | 300 | 0 | 0
4 | Pier 1900 mm | 468 |  | 0 | 0 |  | 30 | 40 | 30 | 40 | 45 | 50 | 51 | 38 | 68 | 67 | 56 | 56 | 55 | 22 | 20 | 20 | 12 | 40 | 504 | 432 | 0
5 | Pier 1600 mm | 468 |  | 0 | 0 |  | 0 | 20 | 30 | 60 | 60 | 60 | 37 | 65 | 60 | 91 | 70 | 62 | 101 | 100 | 150 | 170 | 120 | 100 | 1775 | 1850 | 1700
6 | Pier Cap | 468 |  | 0 | 0 |  | 0 | 0 | 0 | 10 | 30 | 25 | 14 | 20 | 25 | 34 | 38 | 25 | 24 | 23 | 20 | 20 | 25 | 20 | 6400 | 4000 | 0
7 | Track Beam with Nose | 600 |  | 0 |  |  | 0 | 0 | 0 | 20 | 20 | 35 | 50 | 45 | 89 | 95 | 91 | 91 | 95 | 95 | 90 | 60 | 60 | 60 | 60 | 83 | 40
8 | Track Beam without Nose | 600 |  | 0 |  |  | 0 | 0 | 0 | 20 | 15 | 35 | 34 | 55 | 74 | 90 | 78 | 78 | 80 | 80 | 85 | 60 | 60 | 60 | 60 | 34 | 40
9 | h - Section Beam | 600 |  | 0 |  |  | 0 | 0 | 0 | 20 | 6 | 25 | 21 | 25 | 28 | 30 | 26 | 26 | 28 | 28 | 28 | 25 | 20 | 20 | 20 | 35 | 27
10 | U - Section Beam | 600 |  | 0 |  |  | 0 | 0 | 0 | 20 | 6 | 25 | 18 | 25 | 27 | 30 | 26 | 26 | 28 | 28 | 28 | 25 | 20 | 20 | 20 | 23 | 23
11 | Pre-cast Slab | 2000 |  | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 100 | 70 | 70 | 76 | 76 | 60 | 60 | 60 | 60 | 60 | 40 | 40
12 | Abutment wall- PART-A | 1
13 | Abutment wall- PART-D | 1
14 | Cast In-situ slab- 1- PART-G | 1
15 | Cast In-situ slab- 2- PART-G | 1
16 | Cast In-situ slab- PART-C | 1
17 | Erection-Track Beam with Nose | 600 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 60 | 82 | 39 | 27 | 27 | 60 | 29 | 31 | 28 | 41 | 42 | 82
12 | Erection-Track Beam without Nose | 600 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 27 | 52 | 4 | 112 | 78 | 0 | 28 | 25 | 41 | 39 | 58 | 46
13 | Erection-h - Section Beam | 600 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 24 | 36 | 19 | 4 | 13 | 30 | 17 | 18 | 9 | 15 | 22 | 38
14 | Erection-U - Section Beam | 600 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 33 | 30 | 18 | 14 | 16 | 30 | 13 | 12 | 8 | 20 | 24 | 46
15 | Erection-Pre-cast Slab | 2000 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 0 | 57 | 9 | 27 | 90 | 93 | 39 | 24 | 51 | 54 | 33
16 | Track Laying |  | 4.5 | 2022-01-01: 0; 2022-02-01: 0; 2022-03-01: 0; 2022-04-01: 0; 2022-05-01: 0; 2022-06-01: 0; 2022-07-01: 0; 2022-08-01: 0; 2022-09-01: 0; 2022-10-01: 0; 2022-11-01: 0

## June-23 Plan (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 |  |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 0 | 0 | 0 | 0 | 0 | 11 | 15 |  |  | Track beam with nose |  | 1080 | 90 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 0 | 0 | 0 | 0 | 55 | 270 | 325 |  | Track beam without nose |  | 1020 | 85
Part A | Nos. | [6 empty] | 7 |  | 10th May 2023 Clearance will be given by JSW for BRU. | h-section beam |  | 336 | 28
| Qty |  | 0 | 0 | 0 | 0 | 0 | 70 | 70 |  | U-section beam |  | 336 | 28
Part B | Nos. | [5 empty] | 2 | 1 |  | 10th May 2023 Clearance will be given by JSW for BRU. | Pre-cast Slab |  | 30 | 60
| Qty |  | 0 | 0 | 0 | 0 | 10 | 20 | 30 |  | Total: |  | 2802 | 291
Part H | Nos. | [6 empty] | 2 | [9 empty] | Month Plan | Interim
| Qty |  | 0 | 0 | 0 | 0 | 0 | 70 | 70 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 60 | 29.0857
Part C | Nos. | [5 empty] | 9 | 5 |  |  |  |  | A | 70 | 254.7273 | 324.7273 | RCC Foundation | 400 | 193.9047
| Qty |  | 0 | 0 | 0 | 0 | 45 | 110 | 155 |  |  |  | B | 30 | 254.7273 | 284.7273 | Step Footing | 100 | 48.4762
Part I | Nos. | [11 empty] | C | 155 | 254.7273 | 409.7273 | Pier 1900 mm | 120 | 58.1714
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | D | 0 | 254.7273 | 254.7273 | Pier 1600 mm | 750 | 363.5713
Part D | Nos. | [11 empty] | E | 45 | 254.7273 | 299.7273 | Pier Cap | 320 | 155.1238
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 150 | 254.7273 | 404.7273 | Track Beam with Nose | 1080 | 523.5427
Priority Section-2 | Nos. | 20 | 20 | 20 | 20 | 20 | 139 | 5 |  |  |  |  | G | 100 | 254.7273 | 354.7273 | Track Beam without Nose | 1020 | 494.457
| Qty | 0 | 60 | 400 | 100 | 120 | 695 | 50 | 1425 |  |  |  | H | 70 | 254.7273 | 324.7273 | H - Section Beam | 336 | 162.8799
Part E | Nos. | [5 empty] | 9 | [5 empty] | I | 0 | 254.7273 | 254.7273 | U - Section Beam | 336 | 162.8799
| Qty |  | 0 | 0 | 0 | 0 | 45 | 0 | 45 |  |  |  | J | 200 | 254.7273 | 454.7273 | Pre-cast Slab | 30 | 14.5429
Part F | Nos. | [5 empty] | 30 | [5 empty] | K | 930 | 254.7273 | 1184.7273
| Qty |  | 0 | 0 | 0 | 0 | 150 | 0 | 150 |  |  |  |  | 1750 | 2802 | 4552
Part G | Nos. | [5 empty] | 10 | 5
| Qty |  | 0 | 0 | 0 | 0 | 50 | 50 | 100
Part J | Nos. | [5 empty] | 40
| Qty |  | 0 | 0 | 0 | 0 | 200 | 0 | 200
Part K | Nos. | 20 | 20 | 20 | 20 | 20 | 50 |  |  | Clearence to be given by 10th Feb 2023 from JSW.
| Qty |  | 60 | 400 | 100 | 120 | 250 | 0 | 930
Total | Nos. | 20 | 20 | 20 | 20 | 20 | 150 | 20
| Qty | 0 | 60 | 400 | 100 | 120 | 750 | 320 | 1750
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 671.2232 | 23.96%
[10 empty] | Week 2 (9 to 16) | 701.2141 | 25.03%
[10 empty] | Week 3 (17 to 24) | 701.2141 | 25.03%
[10 empty] | Week 4 (25 to 31) | 728.3486 | 25.99%
[10 empty] | Total | 2802
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 367.3242 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 472.1809 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 472.1809 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 438.3141 | 25.05% | 25.52%
[10 empty] | Total | 1750
[10 empty] | Monthly Concreting Target | 4552 | cum
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 60 | 0 | 30 | 30 | 90 | 210 | [10 empty] | Month Plan | Interim
| Qty | 720 | 0 | 360 | 360 | 1080 | 2520 | [9 empty] | Track beam with nose | 60 | 18
Part A | Nos. | 60 |  | 30 | 30 | 90 | 210 | [6 empty] | A | 210 |  | Track beam without nose | 0 | 0
| Qty | 720 | 0 | 360 | 360 | 1080 | 2520 | [6 empty] | B | 0 |  | h-section beam | 30 | 9
Part B | Nos. | [5 empty] | 0 | [6 empty] | C | 0 |  | U-section beam | 30 | 9
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 90 | 27
Part H | Nos. | [5 empty] | 0 | [6 empty] | E | 0
| Qty | [5 empty] | 0 | [6 empty] | F | 0
Part C | Nos. | [12 empty] | G | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | H | 0
Part I | Nos. | [5 empty] | 0 | [6 empty] | I | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | J | 0
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 210
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 21 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 42 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 73.5 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 73.5 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 210
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 60 | 0 | 30 | 30 | 90 | 210
| Qty | 720 | 0 | 360 | 360 | 1080 | 2520
FTM
Track Linking
A |  | 0
B |  | 0
C |  | 0
D |  | 100
E |  | 0
F |  | 0
G |  | 0
H |  | 0
I |  | 0
J |  | 0
K |  | 0

## Week-wise (hidden)
[15 empty] | 2022-03-31 |  |  |  |  | 2022-04-08 | 2022-04-16 | 2022-04-24 | 2022-04-30 |  |  |  | 2022-04-30 |  |  |  |  | 2022-05-08 | 2022-05-16 | 2022-05-24 | 2022-05-31 |  |  |  | 2022-05-31 |  |  |  |  | 2022-06-08 | 2022-06-16 | 2022-06-24 | 2022-06-30 |  |  |  | 2022-06-30 |  |  |  |  | 2022-07-08 | 2022-07-16 | 2022-07-24 | 2022-07-31 |  |  |  | 2022-07-31 |  |  |  |  | 2022-08-08 | 2022-08-16 | 2022-08-24 | 2022-08-31 |  |  |  | 2022-08-31 |  |  |  |  | 2022-09-08 | 2022-09-16 | 2022-09-24 | 2022-09-30 |  |  |  | 2022-09-30 |  |  |  |  | 2022-10-08 | 2022-10-16 | 2022-10-24 | 2022-10-31 |  |  |  | 2022-10-31 |  |  |  |  | 2022-11-08 | 2022-11-16 | 2022-11-24 | 2022-11-30 |  |  |  | 2022-11-30 |  |  |  |  | 2022-12-08 | 2022-12-16 | 2022-12-24 | 2022-12-31 |  |  |  | 2022-12-31 |  |  |  |  | 2023-01-08 | 2023-01-16 | 2023-01-24 | 2023-01-31 |  |  |  | 2023-01-31 |  |  |  |  | 2023-02-08 | 2023-02-16 | 2023-02-24 | 2023-02-28 |  |  |  | 2023-02-28 |  |  |  |  | 2023-03-08 | 2023-03-16 | 2023-03-24 | 2023-03-31 |  |  |  | 2023-03-31 |  |  |  |  | 2023-04-08 | 2023-04-16 | 2023-04-24 | 2023-04-30 |  |  |  | 2023-04-30 |  |  |  |  | 2023-05-08 | 2023-05-16 | 2023-05-24 | 2023-05-31 |  |  |  | 2023-05-31 |  |  |  |  | 2023-06-08 | 2023-06-16 | 2023-06-24 | 2023-06-30 |  |  |  | 2023-06-30 |  |  |  |  | 2023-07-08 | 2023-07-16 | 2023-07-24 | 2023-07-31 |  |  |  | 2023-07-31 |  |  |  |  | 2023-08-08 | 2023-08-16 | 2023-08-24 | 2023-08-31 |  |  |  | 2023-08-31 |  |  |  |  | 2023-09-08 | 2023-09-16 | 2023-09-24 | 2023-09-30 |  |  |  | 2023-09-30 |  |  |  |  | 2023-10-08 | 2023-10-16 | 2023-10-24 | 2023-10-31 |  |  |  | 2023-10-31 |  |  |  |  | 2023-11-08 | 2023-11-16 | 2023-11-24 | 2023-11-30 |  |  |  | 2023-11-30 |  |  |  |  | 2023-12-08 | 2023-12-16 | 2023-12-24 | 2023-12-31
Civil
Sr. No. | Area | Scope | UoM | Cumulative Till Date |  |  |  | Till Mar'22 |  |  |  | Apr'22 |  |  |  | Construction | [7 empty] | May'22 |  |  |  | Construction | [7 empty] | Jun'22 |  |  |  | Construction | [7 empty] | Jul'22 |  |  |  | Construction | [7 empty] | Aug'22 |  |  |  | Construction | [7 empty] | Sep'22 |  |  |  | Construction | [7 empty] | Oct'22 |  |  |  | Construction | [7 empty] | Nov'22 |  |  |  | Construction | [7 empty] | Dec'22 |  |  |  | Construction | [7 empty] | Jan'23 |  |  |  | Construction | [7 empty] | Feb'23 |  |  |  | Construction | [7 empty] | Mar'23 |  |  |  | Construction | [7 empty] | Apr'23 |  |  |  | Construction | [7 empty] | May'23 |  |  |  | Construction | [7 empty] | Jun'23 |  |  |  | Construction | [7 empty] | Jul'23 |  |  |  | Construction | [7 empty] | Aug'23 |  |  |  | Construction | [7 empty] | Sep'23 |  |  |  | Construction | [7 empty] | Oct'23 |  |  |  | Construction | [7 empty] | Nov'23 |  |  |  | Construction | [7 empty] | Dec'23 |  |  |  | Construction
|  |  |  | Design |  | Construction |  | Design |  | Construction |  | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4
| Total: | 58967 |  | 58967 | 46197 | 69253.16 | 53536.55 | 3500 | 3500 | 0 | 620 | 9600 | 7500 | 1461 | 955 | 219.15 | 292.2 | 365.25 | 584.4 | 151 | 344 | 260 | 200 | 12922.0895 | 7588 | 1438 | 754 | 215.7 | 287.6 | 359.5 | 575.2 | 155 | 154 | 230 | 215 | 10126 | 7500 | 1370 | 952.35 | 205.5 | 274 | 342.5 | 548 | 250.6 | 226.5 | 319.25 | 156 | 8947 | 7912 | 2445.16 | 1023 | 366.774 | 489.032 | 611.29 | 978.064 | 156 | 362 | 194 | 311 | 6924 | 6000 | 2974 | 1439.7 | 446.1 | 594.8 | 743.5 | 1189.6 | 310 | 349.7 | 371 | 409 | 2875 | 4000 | 3875 | 2085 | 581.25 | 968.75 | 1162.5 | 1162.5 | 382 | 609 | 657 | 437 | 1308 | 2197 | 3386 | 2807 | 507.9 | 846.5 | 1015.8 | 1015.8 | 571 | 911 | 640 | 685 | 0 | 0 | 5647 | 3981 | 959.99 | 1411.75 | 1411.75 | 1863.51 | 998 | 1073 | 1075 | 835 | 0 | 0 | 4972 | 3145 | 1311.4003 | 1449.3332 | 1449.3332 | 761.9333 | 852.5 | 937.5 | 623 | 732 | 0 | 0 | 5498 | 3197.5 | 1237.05 | 1429.48 | 1429.48 | 1401.99 | 747 | 892 | 984 | 574.5 | 0 | 0 | 5463 | 3483 | 1229.175 | 1420.38 | 1420.38 | 1393.065 | 1172 | 1042.5 | 1042.5 | 226 | 0 | 0 | 4649 | 3252 | 1044.7488 | 1208.9085 | 1208.9085 | 1186.4342 | 403.5 | 1249 | 800.5 | 799 | 0 | 0 | 5656 | 2981.5 | 1271.0474 | 1470.765 | 1470.765 | 1443.4226 | 979.5 | 925.5 | 748.5 | 328 | 0 | 0 | 4133 | 1620 | 928.7905 | 1074.7298 | 1074.7298 | 1054.75 | 245 | 317 | 522 | 536 | 0 | 0 | 4552 | 2934.5 | 1001.44 | 1183.52 | 1183.52 | 1183.52 | 356.5 | 878.5 | 818.5 | 881 | 0 | 0 | 4404 | 2693 | 968.88 | 1145.04 | 1145.04 | 1145.04 | 554.5 | 700 | 786 | 652.5 | 0 | 0 | 3276 | 2915 | 720.72 | 851.76 | 851.76 | 851.76 | 845 | 693.5 | 680 | 696.5 | 0 | 0 | 4054 | 3540.5 | 891.88 | 1054.04 | 1054.04 | 1054.04 | 894.5 | 836.5 | 987 | 822.5 | 0 | 0 | 0 | 3336.5 | 0 | 0 | 0 | 0 | 620 | 1024 | 908.5 | 784 | 0 | 0 | 0 | 3843.5 | 0 | 0 | 0 | 0 | 1608.5 | 585 | 953 | 697 | 0 | 0 | 0 | 1977.5 | 0 | 0 | 0 | 0 | 823 | 830 | 324.5 | 0
1 | A | 3903 | cum | 3903 | 3347.2593 | 5650.1514 | 4718.2 | 259.2593 | 259.2593 | 0 | 620 | 1500 | 2000 | 403.8785 | 264 | 60.5818 | 80.7757 | 100.9696 | 161.5514 | 98 | 70 | 96 | 0 | 2358.0895 | 1088 | 45.6508 | 24 | 6.8476 | 9.1302 | 11.4127 | 18.2603 | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 218.1015 | 92 | 32.7152 | 43.6203 | 54.5254 | 87.2406 | 13 | 29 | 22 | 28 | 0 | 0 | 182.5812 | 29.7 | 27.3872 | 36.5162 | 45.6453 | 73.0325 | 15 | 14.7 | 0 | 0 | 0 | 0 | 168.6667 | 114 | 25.3 | 42.1667 | 50.6 | 50.6 | 14 | 14 | 34 | 52 | 0 | 0 | 185.9091 | 216 | 27.8864 | 46.4773 | 55.7727 | 55.7727 | 110 | 86 | 8 | 12 |  |  | 465 | 161 | 79.05 | 116.25 | 116.25 | 153.45 | 46 | 43 | 72 | 0 |  |  | 446.3636 | 14.5 | 117.7316 | 130.1146 | 130.1146 | 68.4029 | 2.5 | 12 | 0 | 0 |  |  | 671.8182 | 140 | 151.1591 | 174.6727 | 174.6727 | 171.3136 | 0 | 0 | 16 | 124 |  |  | 572.2727 | 502.5 | 128.7614 | 148.7909 | 148.7909 | 145.9295 | 132 | 132 | 214.5 | 24 |  |  | 529.2727 | 717 | 118.9411 | 137.6301 | 137.6301 | 135.0715 | 122 | 314 | 225.5 | 55.5 |  |  | 562.4545 | 427.5 | 126.3979 | 146.2586 | 146.2586 | 143.5395 | 140 | 189 | 74.5 | 24 |  |  | 669.4545 | 369.5 | 150.4435 | 174.0824 | 174.0824 | 170.8462 | 70 | 38.5 | 49 | 212 |  |  | 324.7273 | 564.5 | 71.44 | 84.4291 | 84.4291 | 84.4291 | 151.5 | 281 | 108 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 4.5 | 0 | 0 | 0 | 0 | 2 | 2.5 | 0 | 0 |  |  | 204 | 195 | 44.88 | 53.04 | 53.04 | 53.04 | 0 | 20 | 146 | 29 |  |  | 0 | 178 |  |  |  |  | 0 | 32 | 75 | 71 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 84.5 |  |  |  |  | 49 | 33 | 2.5 | 0
2 | B | 3125 | cum | 3125 | 518.5185 | 3886.6054 | 3121.75 | 518.5185 | 518.5185 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1364 | 0 | 55.1614 | 29 | 8.2742 | 11.0323 | 13.7903 | 22.0646 | 0 | 0 | 29 | 0 | 0 | 0 | 450.3373 | 313.75 | 67.5506 | 90.0675 | 112.5843 | 180.1349 | 0 | 114.5 | 163.25 | 36 | 0 | 0 | 48.467 | 20 | 7.27 | 9.6934 | 12.1167 | 19.3868 | 0 | 0 | 0 | 20 | 0 | 0 | 44.2003 | 59 | 6.63 | 8.8401 | 11.0501 | 17.6801 | 13 | 24 | 14 | 8 | 0 | 0 | 212.6667 | 44 | 31.9 | 53.1667 | 63.8 | 63.8 | 0 | 14 | 30 | 0 | 0 | 0 | 133.9091 | 14 | 20.0864 | 33.4773 | 40.1727 | 40.1727 | 14 | 0 | 0 | 0 |  |  | 231 | 288 | 39.27 | 57.75 | 57.75 | 76.23 | 96 | 156 | 36 | 0 |  |  | 242.3636 | 277 | 63.9251 | 70.6488 | 70.6488 | 37.141 | 48 | 73 | 113 | 43 |  |  | 427.8182 | 24 | 96.2591 | 111.2327 | 111.2327 | 109.0936 | 0 | 0 | 0 | 24 |  |  | 372.2727 | 91 | 83.7614 | 96.7909 | 96.7909 | 94.9295 | 24 | 32 | 35 | 0 |  |  | 244.2727 | 144 | 54.8943 | 63.5198 | 63.5198 | 62.3389 | 0 | 84 | 60 | 0 |  |  | 297.4545 | 396 | 66.8456 | 77.349 | 77.349 | 75.911 | 108 | 144 | 108 | 36 |  |  | 469.4545 | 167.5 | 105.4984 | 122.0752 | 122.0752 | 119.8057 | 18 | 73.5 | 54 | 22 |  |  | 284.7273 | 143.5 | 62.64 | 74.0291 | 74.0291 | 74.0291 | 0 | 8 | 38.5 | 97 |  |  | 14.5 | 97 | 3.19 | 3.77 | 3.77 | 3.77 | 39.5 | 29 | 28 | 0.5 |  |  | 0 | 37 | 0 | 0 | 0 | 0 | 1 | 24 | 0 | 12 |  |  | 358 | 146 | 78.76 | 93.08 | 93.08 | 93.08 | 12 | 0 | 52 | 82 |  |  | 0 | 425 |  |  |  |  | 34 | 142 | 178 | 71 |  |  | 0 | 296 |  |  |  |  | 51 | 30 | 77 | 138 |  |  | 0 | 110 |  |  |  |  | 64 | 36 | 10 | 0
3 | C | 4057 | cum | 4057 | 2050 | 5920.4394 | 4725 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 817 | 1050 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 1000 | 496.6667 | 150 | 74.5 | 124.1667 | 149 | 149 | 79 | 53 | 0 | 18 | 0 | 0 | 341.9091 | 465 | 51.2864 | 85.4773 | 102.5727 | 102.5727 | 55 | 308 | 42 | 60 |  |  | 487 | 133 | 82.79 | 121.75 | 121.75 | 160.71 | 36 | 12 | 15 | 70 |  |  | 458.3636 | 81 | 120.8967 | 133.6126 | 133.6126 | 70.2419 | 55 | 0 | 6 | 20 |  |  | 613.8182 | 43 | 138.1091 | 159.5927 | 159.5927 | 156.5236 | 0 | 5 | 38 | 0 |  |  | 784.2727 | 164 | 176.4614 | 203.9109 | 203.9109 | 199.9895 | 25 | 30 | 99 | 10 |  |  | 767.2727 | 116 | 172.4257 | 199.5187 | 199.5187 | 195.8096 | 27 | 83 | 0 | 6 |  |  | 725.4545 | 255 | 163.0281 | 188.6445 | 188.6445 | 185.1375 | 32 | 12 | 72 | 139 |  |  | 436.4545 | 292 | 98.0825 | 113.494 | 113.494 | 111.3841 | 36 | 72 | 94 | 90 |  |  | 409.7273 | 52 | 90.14 | 106.5291 | 106.5291 | 106.5291 | 52 | 0 | 0 | 0 |  |  | 15.5 | 362 | 3.41 | 4.03 | 4.03 | 4.03 | 43 | 53 | 73 | 193 |  |  | 192 | 305 | 42.24 | 49.92 | 49.92 | 49.92 | 177 | 70 | 46 | 12 |  |  | 192 | 573 | 42.24 | 49.92 | 49.92 | 49.92 | 60 | 218.5 | 173 | 121.5 |  |  | 0 | 422 |  |  |  |  | 72 | 24 | 182 | 144 |  |  | 0 | 1228 |  |  |  |  | 976 | 48 | 96 | 108 |  |  | 0 | 72 |  |  |  |  | 60 | 0 | 12 | 0
4 | D | 5704 | cum | 5704 | 2444.4444 | 7732.0874 | 5826.6 | 1944.4444 | 1944.4444 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 747.5317 | 391 | 112.1298 | 149.5063 | 186.8829 | 299.0127 | 0 | 17 | 175 | 199 | 500 | 0 | 906.7652 | 629.6 | 136.0148 | 181.353 | 226.6913 | 362.7061 | 250.6 | 112 | 147 | 120 | 800 | 0 | 482.2466 | 211 | 72.337 | 96.4493 | 120.5617 | 192.8986 | 113 | 24 | 24 | 50 | 800 | 0 | 659.6044 | 364 | 98.9407 | 131.9209 | 164.9011 | 263.8418 | 85 | 97 | 74 | 108 | 514 | 0 | 1095.6667 | 680 | 164.35 | 273.9167 | 328.7 | 328.7 | 84 | 195 | 189 | 212 | 0 | 500 | 760.9091 | 1038 | 114.1364 | 190.2273 | 228.2727 | 228.2727 | 217 | 372 | 223 | 226 |  |  | 555 | 1238 | 94.35 | 138.75 | 138.75 | 183.15 | 264 | 243 | 431 | 300 |  |  | 724.3636 | 704.5 | 191.0561 | 211.1513 | 211.1513 | 111.005 | 294 | 306.5 | 60 | 44 |  |  | 473.8182 | 322.5 | 106.6091 | 123.1927 | 123.1927 | 120.8236 | 65 | 88 | 75 | 94.5 |  |  | 276.2727 | 162 | 62.1614 | 71.8309 | 71.8309 | 70.4495 | 125.5 | 36.5 | 0 | 0 |  |  | 264.2727 | 28 | 59.3888 | 68.7205 | 68.7205 | 67.4429 | 0 | 10 | 18 | 0 |  |  | 275.4545 | 35 | 61.9017 | 71.6282 | 71.6282 | 70.2966 | 0 | 35 | 0 | 0 |  |  | 255.4545 | 0 | 57.4071 | 66.4274 | 66.4274 | 65.1925 | 0 | 0 | 0 | 0 |  |  | 254.7273 | 2.5 | 56.04 | 66.2291 | 66.2291 | 66.2291 | 0 | 2.5 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 2.5 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 18 |  |  |  |  | 0 | 0 | 18 | 0
5 | E | 4421 | cum | 4421 | 0 | 4266.2727 | 1865 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 133.9091 | 0 | 20.0864 | 33.4773 | 40.1727 | 40.1727 | 0 | 0 | 0 | 0 |  |  | 467 | 0 | 79.39 | 116.75 | 116.75 | 154.11 | 0 | 0 | 0 | 0 |  |  | 466.3636 | 345 | 123.0067 | 135.9445 | 135.9445 | 71.4678 | 78 | 126 | 0 | 141 |  |  | 571.8182 | 299 | 128.6591 | 148.6727 | 148.6727 | 145.8136 | 114 | 157 | 28 | 0 |  |  | 418.2727 | 90 | 94.1114 | 108.7509 | 108.7509 | 106.6595 | 80 | 0 | 0 | 10 |  |  | 314.2727 | 58 | 70.6251 | 81.7223 | 81.7223 | 80.203 | 0 | 40 | 0 | 18 |  |  | 848.4545 | 47 | 190.6694 | 220.6289 | 220.6289 | 216.5273 | 0 | 6 | 0 | 41 |  |  | 270.4545 | 22 | 60.778 | 70.328 | 70.328 | 69.0205 | 0 | 0 | 22 | 0 |  |  | 299.7273 | 16 | 65.94 | 77.9291 | 77.9291 | 77.9291 | 0 | 11 | 5 | 0 |  |  | 476 | 0 | 104.72 | 123.76 | 123.76 | 123.76 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 |  |  | 0 | 346 |  |  |  |  | 36 | 191 | 60 | 59 |  |  | 0 | 144 |  |  |  |  | 36 | 72 | 36 | 0 |  |  | 0 | 462 |  |  |  |  | 96 | 220 | 146 | 0
6 | F | 3578 | cum | 3578 | 2611.1111 | 5725.5172 | 3736.5 | 777.7778 | 777.7778 | 0 | 0 | 500 | 1833.3333 | 1057.1215 | 691 | 158.5682 | 211.4243 | 264.2804 | 422.8486 | 53 | 274 | 164 | 200 | 500 | 0 | 589.6561 | 310 | 88.4484 | 117.9312 | 147.414 | 235.8624 | 155 | 137 | 18 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 310 |  | 40.8003 | 76 | 6.12 | 8.1601 | 10.2001 | 16.3201 | 0 | 0 | 31 | 45 | 0 | 0 | 191.6667 | 56 | 28.75 | 47.9167 | 57.5 | 57.5 | 43 | 13 | 0 | 0 | 0 | 0 | 133.9091 | 0 | 20.0864 | 33.4773 | 40.1727 | 40.1727 | 0 | 0 | 0 | 0 |  |  | 343 | 168 | 58.31 | 85.75 | 85.75 | 113.19 | 0 | 0 | 24 | 144 |  |  | 242.3636 | 72 | 63.9251 | 70.6488 | 70.6488 | 37.141 | 72 | 0 | 0 | 0 |  |  | 271.8182 | 36 | 61.1591 | 70.6727 | 70.6727 | 69.3136 | 36 | 0 | 0 | 0 |  |  | 364.2727 | 48 | 81.9614 | 94.7109 | 94.7109 | 92.8895 | 12 | 24 | 0 | 12 |  |  | 244.2727 | 40 | 54.8943 | 63.5198 | 63.5198 | 62.3389 | 0 | 40 | 0 | 0 |  |  | 405.4545 | 111 | 91.116 | 105.4329 | 105.4329 | 103.4728 | 48 | 12 | 39 | 12 |  |  | 405.4545 | 82 | 91.116 | 105.4329 | 105.4329 | 103.4728 | 20 | 0 | 14 | 48 |  |  | 404.7273 | 228 | 89.04 | 105.2291 | 105.2291 | 105.2291 | 0 | 96 | 20 | 112 |  |  | 441 | 356.5 | 97.02 | 114.66 | 114.66 | 114.66 | 118 | 98.5 | 77 | 63 |  |  | 440 | 867 | 96.8 | 114.4 | 114.4 | 114.4 | 130 | 105 | 301.5 | 330.5 |  |  | 150 | 376.5 | 33 | 39 | 39 | 39 | 110.5 | 58 | 93 | 115 |  |  | 0 | 218.5 |  |  |  |  | 74.5 | 60 | 48 | 36 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
7 | G | 5757 | cum | 5757 | 1850 | 9500.9394 | 4929 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1291 | 1050 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500 | 350.6667 | 0 | 52.6 | 87.6667 | 105.2 | 105.2 | 0 | 0 | 0 | 0 | 0 | 300 | 289.9091 | 0 | 43.4864 | 72.4773 | 86.9727 | 86.9727 | 0 | 0 | 0 | 0 |  |  | 590 | 194 | 100.3 | 147.5 | 147.5 | 194.7 | 0 | 0 | 35 | 159 |  |  | 346.3636 | 228 | 91.3559 | 100.9647 | 100.9647 | 53.0784 | 44 | 34 | 40 | 110 |  |  | 725.8182 | 416 | 163.3091 | 188.7127 | 188.7127 | 185.0836 | 24 | 133 | 180 | 79 |  |  | 728.2727 | 760 | 163.8614 | 189.3509 | 189.3509 | 185.7095 | 141 | 408 | 167 | 44 |  |  | 832.2727 | 223 | 187.0329 | 216.4211 | 216.4211 | 212.3977 | 0 | 129 | 36 | 58 |  |  | 365.4545 | 126 | 82.127 | 95.0314 | 95.0314 | 93.2647 | 38 | 83 | 5 | 0 |  |  | 405.4545 | 189 | 91.116 | 105.4329 | 105.4329 | 103.4728 | 12 | 42 | 57 | 78 |  |  | 354.7273 | 508 | 78.04 | 92.2291 | 92.2291 | 92.2291 | 78 | 178 | 132 | 120 |  |  | 1708 | 252 | 375.76 | 444.08 | 444.08 | 444.08 | 144 | 96 | 12 | 0 |  |  | 1374 | 124 | 302.28 | 357.24 | 357.24 | 357.24 | 36 | 14 | 34 | 40 |  |  | 1430 | 771 | 314.6 | 371.8 | 371.8 | 371.8 | 105 | 276 | 276 | 114 |  |  | 0 | 298 |  |  |  |  | 128 | 122 | 20 | 28 |  |  | 0 | 450 |  |  |  |  | 8 | 57 | 246 | 139 |  |  | 0 | 390 |  |  |  |  | 233 | 145 | 12 | 0
8 | H | 5148 | cum | 5148 | 3167 | 4903.9394 | 5098.5 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 947 | 2967 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 426.6667 | 628 | 64 | 106.6667 | 128 | 128 | 57 | 209 | 207 | 155 | 0 | 200 | 508.9091 | 566 | 76.3364 | 127.2273 | 152.6727 | 152.6727 | 175 | 37 | 171 | 183 |  |  | 568 | 318 | 96.56 | 142 | 142 | 187.44 | 144 | 54 | 40 | 80 |  |  | 572.3636 | 230 | 150.965 | 166.8434 | 166.8434 | 87.7118 | 81 | 19 | 70 | 60 |  |  | 399.8182 | 613 | 89.9591 | 103.9527 | 103.9527 | 101.9536 | 36 | 232 | 248 | 97 |  |  | 394.2727 | 358 | 88.7114 | 102.5109 | 102.5109 | 100.5395 | 72 | 106 | 132 | 48 |  |  | 544.2727 | 573.5 | 122.312 | 141.5306 | 141.5306 | 138.8995 | 12 | 115 | 133 | 313.5 |  |  | 570.4545 | 952 | 128.1957 | 148.3389 | 148.3389 | 145.5812 | 447.5 | 263.5 | 207 | 34 |  |  | 370.4545 | 117 | 83.2506 | 96.3316 | 96.3316 | 94.5407 | 47 | 0 | 22 | 48 |  |  | 324.7273 | 192 | 71.44 | 84.4291 | 84.4291 | 84.4291 | 12 | 12 | 49 | 119 |  |  | 36 | 84 | 7.92 | 9.36 | 9.36 | 9.36 | 12 | 12 | 24 | 36 |  |  | 60 | 180 | 13.2 | 15.6 | 15.6 | 15.6 | 84 | 84 | 12 | 0 |  |  | 128 | 16 | 28.16 | 33.28 | 33.28 | 33.28 | 14 | 2 | 0 | 0 |  |  | 0 | 82 |  |  |  |  | 45 | 31 | 6 | 0 |  |  | 0 | 36 |  |  |  |  | 12 | 0 | 24 | 0 |  |  | 0 | 153 |  |  |  |  | 56 | 97 | 0 | 0
9 | I | 5891 | cum | 5891 | 13486.3333 | 8153.7265 | 6509 | 0 | 0 | 0 | 0 | 800 | 1833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1000 | 7500 | 12.8975 | 9 | 1.9346 | 2.5795 | 3.2244 | 5.159 | 0 | 0 | 9 | 0 | 1500 | 3956 | 1420.083 | 586 | 213.0125 | 284.0166 | 355.0208 | 568.0332 | 30 | 309 | 76 | 171 | 1000 | 0 | 975.8066 | 578 | 146.371 | 195.1613 | 243.9516 | 390.3226 | 97 | 115 | 130 | 236 | 361 | 0 | 735.6667 | 413 | 110.35 | 183.9167 | 220.7 | 220.7 | 105 | 111 | 197 | 0 | 0 | 197 | 628.9091 | 178 | 94.3364 | 157.2273 | 188.6727 | 188.6727 | 0 | 91 | 35 | 52 |  |  | 530 | 463 | 90.1 | 132.5 | 132.5 | 174.9 | 91 | 200 | 138 | 34 |  |  | 448.3636 | 791 | 118.2591 | 130.6976 | 130.6976 | 68.7094 | 86 | 147 | 302 | 256 |  |  | 607.8182 | 1223 | 136.7591 | 158.0327 | 158.0327 | 154.9936 | 418 | 277 | 396 | 132 |  |  | 534.2727 | 833.5 | 120.2114 | 138.9109 | 138.9109 | 136.2395 | 422.5 | 223 | 146 | 42 |  |  | 294.2727 | 621.5 | 66.1306 | 76.5216 | 76.5216 | 75.099 | 206.5 | 280 | 51 | 84 |  |  | 255.4545 | 0 | 57.4071 | 66.4274 | 66.4274 | 65.1925 | 0 | 0 | 0 | 0 |  |  | 255.4545 | 12 | 57.4071 | 66.4274 | 66.4274 | 65.1925 | 0 | 0 | 12 | 0 |  |  | 254.7273 | 0 | 56.04 | 66.2291 | 66.2291 | 66.2291 | 0 | 0 | 0 | 0 |  |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 24 |  |  | 480 | 288 | 105.6 | 124.8 | 124.8 | 124.8 | 24 | 60 | 60 | 144 |  |  | 720 | 264.5 | 158.4 | 187.2 | 187.2 | 187.2 | 192 | 48 | 0 | 24.5 |  |  | 0 | 140 |  |  |  |  | 38.5 | 41 | 24.5 | 36 |  |  | 0 | 48.5 |  |  |  |  | 12.5 | 0 | 0 | 36 |  |  | 0 | 12 |  |  |  |  | 12 | 0 | 0 | 0
10 | J | 4913 | cum | 4913 | 15722.3333 | 5665.2085 | 3950.5 | 0 | 0 | 0 | 0 | 1200 | 1833.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1700 | 6500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1526 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989 | 276.2619 | 114 | 41.4393 | 55.2524 | 69.0655 | 110.5048 | 0 | 0 | 72 | 42 | 0 | 3900 | 1071.0072 | 321 | 160.6511 | 214.2014 | 267.7518 | 428.4029 | 100 | 99 | 122 | 0 | 0 | 2500 | 196.6667 | 0 | 29.5 | 49.1667 | 59 | 59 | 0 | 0 | 0 | 0 | 0 | 0 | 133.9091 | 0 | 20.0864 | 33.4773 | 40.1727 | 40.1727 | 0 | 0 | 0 | 0 |  |  | 456 | 816 | 77.52 | 114 | 114 | 150.48 | 281 | 275 | 236 | 24 |  |  | 266.3636 | 246 | 70.2553 | 77.6447 | 77.6447 | 40.8189 | 20 | 196 | 20 | 10 |  |  | 271.8182 | 60 | 61.1591 | 70.6727 | 70.6727 | 69.3136 | 36 | 0 | 0 | 24 |  |  | 244.2727 | 84 | 54.9614 | 63.5109 | 63.5109 | 62.2895 | 48 | 12 | 0 | 24 |  |  | 244.2727 | 262 | 54.8943 | 63.5198 | 63.5198 | 62.3389 | 0 | 57 | 130 | 75 |  |  | 405.4545 | 168 | 91.116 | 105.4329 | 105.4329 | 103.4728 | 62 | 10 | 96 | 0 |  |  | 315.4545 | 0 | 70.8907 | 82.0296 | 82.0296 | 80.5046 | 0 | 0 | 0 | 0 |  |  | 454.7273 | 36 | 100.04 | 118.2291 | 118.2291 | 118.2291 | 0 | 12 | 24 | 0 |  |  | 783 | 238.5 | 172.26 | 203.58 | 203.58 | 203.58 | 25 | 24.5 | 165 | 24 |  |  | 268 | 447 | 58.96 | 69.68 | 69.68 | 69.68 | 146 | 160 | 141 | 0 |  |  | 278 | 168 | 61.16 | 72.28 | 72.28 | 72.28 | 22 | 28 | 79 | 39 |  |  | 0 | 381 |  |  |  |  | 20 | 167 | 147 | 47 |  |  | 0 | 520 |  |  |  |  | 216 | 210 | 24 | 70 |  |  | 0 | 89 |  |  |  |  | 0 | 65 | 24 | 0
11 | K | 12470 | cum | 12470 | 1000 | 7848.2727 | 9056.5 | 0 | 0 | 0 | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1308 | 1000 | 133.9091 | 330 | 20.0864 | 33.4773 | 40.1727 | 40.1727 | 0 | 17 | 161 | 152 |  |  | 955 | 202 | 162.35 | 238.75 | 238.75 | 315.15 | 40 | 90 | 48 | 24 |  |  | 758.3636 | 156 | 200.0238 | 221.0623 | 221.0623 | 116.2153 | 72 | 24 | 12 | 48 |  |  | 461.8182 | 21 | 103.9091 | 120.0727 | 120.0727 | 117.7636 | 18 | 0 | 3 | 0 |  |  | 774.2727 | 390 | 174.2114 | 201.3109 | 201.3109 | 197.4395 | 90 | 39 | 249 | 12 |  |  | 370.2727 | 469 | 83.2097 | 96.2843 | 96.2843 | 94.4943 | 36 | 97 | 147 | 189 |  |  | 944.4545 | 464 | 212.243 | 245.5924 | 245.5924 | 241.0267 | 104 | 171 | 147 | 42 |  |  | 279.4545 | 369 | 62.8006 | 72.6683 | 72.6683 | 71.3174 | 42 | 91 | 198 | 38 |  |  | 1184.7273 | 1192 | 260.64 | 308.0291 | 308.0291 | 308.0291 | 63 | 278 | 442 | 409 |  |  | 930 | 1255 | 204.6 | 241.8 | 241.8 | 241.8 | 173 | 387 | 383 | 312 |  |  | 462 | 660 | 101.64 | 120.12 | 120.12 | 120.12 | 245 | 174 | 83 | 158 |  |  | 594 | 994.5 | 130.68 | 154.44 | 154.44 | 154.44 | 379 | 186 | 168 | 261.5 |  |  | 0 | 846 |  |  |  |  | 172 | 214 | 168 | 292 |  |  | 0 | 1121 |  |  |  |  | 297 | 168 | 450 | 206 |  |  | 0 | 587 |  |  |  |  | 253 | 234 | 100 | 0
12 | Abutment wall- PART-A | 491 | cum | 491 | 0 | 364 | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 280 | 0 | 61.6 | 72.8 | 72.8 | 72.8 | 0 | 0 | 0 | 0 |  |  | 84 | 0 | 18.48 | 21.84 | 21.84 | 21.84 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
13 | Abutment wall- PART-D | 830 | cum | 830 | 0 | 500 | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 500 | 0 | 110 | 130 | 130 | 130 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
14 | Cast In-situ slab- 1- PART-G | 471 | cum | 471 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
15 | Cast In-situ slab- 2- PART-G | 1141 | cum | 1141 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
16 | Cast In-situ slab- PART-C | 650 | cum | 650 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
Pre-cast Segment Erection
Sr. No. | Area | Scope | UoM | Cumulative Till Date |  |  |  | Till Mar'22 |  |  |  | Apr'22 |  |  |  | Construction | [7 empty] | May'22 |  |  |  | Construction | [7 empty] | Jun'22 |  |  |  | Construction | [7 empty] | Jul'22 |  |  |  | Construction | [7 empty] | Aug'22 |  |  |  | Construction | [7 empty] | Sep'22 |  |  |  | Construction | [7 empty] | Oct'22 |  |  |  | Construction | [7 empty] | Nov'22 |  |  |  | Construction | [7 empty] | Dec'22 |  |  |  | Construction | [7 empty] | Jan'23 |  |  |  | Construction | [7 empty] | Feb'23 |  |  |  | Construction | [7 empty] | Mar'23 |  |  |  | Construction | [7 empty] | Apr'23 |  |  |  | Construction | [7 empty] | May'23 |  |  |  | Construction | [7 empty] | Jun'23 |  |  |  | Construction | [7 empty] | Jul'23 |  |  |  | Construction | [7 empty] | Aug'23 |  |  |  | Construction | [7 empty] | Sep'23 |  |  |  | Construction | [7 empty] | Oct'23 |  |  |  | Construction | [7 empty] | Nov'23 |  |  |  | Construction | [7 empty] | Dec'23 |  |  |  | Construction
|  |  |  | Design |  | Construction |  | Design |  | Construction |  | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4
| Total: | 3004 |  | 0 | 0 | 5584.5 | 1515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 85 | 34 | 0 | 13 | 34 | 38 | 0 | 0 | 14 | 20 | 0 | 0 | 148 | 68 | 0 | 22.2 | 59.2 | 66.6 | 0 | 21 | 25 | 22 | 0 | 0 | 200 | 214 | 20 | 40 | 70 | 70 | 53 | 47 | 93 | 21 | 0 | 0 | 137 | 138 | 13.7 | 27.4 | 47.95 | 47.95 | 0 | 42 | 50 | 46 | 0 | 0 | 166 | 114 | 37.3044 | 43.166 | 43.166 | 42.3635 | 37 | 44 | 19 | 14 | 0 | 0 | 161 | 148 | 36.1808 | 41.8658 | 41.8658 | 41.0875 | 39 | 35 | 43 | 31 | 0 | 0 | 210.5 | 112 | 21 | 42 | 73.5 | 74 | 24 | 14 | 44 | 30 | 0 | 0 | 180 | 126 | 18 | 36 | 63 | 63 | 16 | 41 | 46 | 23 | 0 | 0 | 125 | 68 | 27.5 | 32.5 | 32.5 | 32.5 | 2 | 21 | 11 | 34 | 0 | 0 | 110 | 111 | 24.2 | 28.6 | 28.6 | 28.6 | 14 | 17 | 62 | 18 | 0 | 0 | 4054 | 167 | 891.88 | 1054.04 | 1054.04 | 1054.04 | 37 | 45 | 32 | 53 | 0 | 0 | 0 | 148 | 0 | 0 | 0 | 0 | 39 | 33 | 56 | 20 | 0 | 0 | 0 | 59 | 0 | 0 | 0 | 0 | 20 | 34 | 5 | 0
1 | A | 266 | cum | 0 | 0 | 510.5 | 188 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 210.5 | 82 | 21 | 42 | 73.5 | 74 | 0 | 8 | 44 | 30 |  |  | 88 | 98 | 8.8 | 17.6 | 30.8 | 30.8 | 16 | 41 | 41 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 204 | 0 | 44.88 | 53.04 | 53.04 | 53.04 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
2 | B | 190 | cum | 0 | 0 | 559.5 | 62 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 16 | 0 | 0 | 2.4 | 6.4 | 7.2 | 0 | 0 | 0 | 0 |  |  | 44 | 0 | 4.4 | 8.8 | 15.4 | 15.4 | 0 | 0 | 0 | 0 |  |  | 55 | 52 | 5.5 | 11 | 19.25 | 19.25 | 0 | 42 | 10 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 13 | 10 | 1.3 | 2.6 | 4.55 | 4.55 | 0 | 0 | 5 | 5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 431.5 | 0 | 94.93 | 112.19 | 112.19 | 112.19 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
3 | C | 184 | cum | 0 | 0 | 616.5 | 65 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 72 | 0 | 15.84 | 18.72 | 18.72 | 18.72 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 544.5 | 5 | 119.79 | 141.57 | 141.57 | 141.57 | 0 | 0 | 0 | 5 |  |  | 0 | 55 |  |  |  |  | 22 | 33 | 0 | 0 |  |  | 0 | 5 |  |  |  |  | 0 | 0 | 5 | 0
4 | D | 342 | cum | 0 | 0 | 335 | 354 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 85 | 34 | 0 | 13 | 34 | 38 | 0 | 0 | 14 | 20 |  |  | 98 | 68 | 0 | 14.7 | 39.2 | 44.1 | 0 | 21 | 25 | 22 |  |  | 104 | 154 | 10.4 | 20.8 | 36.4 | 36.4 | 53 | 47 | 54 | 0 |  |  | 48 | 0 | 4.8 | 9.6 | 16.8 | 16.8 | 0 | 0 | 0 | 0 |  |  | 0 | 49 | 0 | 0 | 0 | 0 | 37 | 5 | 0 | 7 |  |  | 0 | 49 | 0 | 0 | 0 | 0 | 38 | 11 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
5 | E | 190 | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
6 | F | 172 | cum | 0 | 0 | 265 | 187 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 11 | 10 |  |  | 73 | 84 | 16.06 | 18.98 | 18.98 | 18.98 | 0 | 8 | 62 | 14 |  |  | 192 | 69 | 42.24 | 49.92 | 49.92 | 49.92 | 0 | 0 | 32 | 37 |  |  | 0 | 13 |  |  |  |  | 9 | 0 | 4 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
7 | G | 245 | cum | 0 | 0 | 848 | 83 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 848 | 83 | 186.56 | 220.48 | 220.48 | 220.48 | 37 | 45 | 0 | 1 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
8 | H | 252 | cum | 0 | 0 | 757 | 207 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 96 | 14 | 21.5736 | 24.9635 | 24.9635 | 24.4994 | 0 | 0 | 14 | 0 |  |  | 161 | 91 | 36.1808 | 41.8658 | 41.8658 | 41.0875 | 0 | 17 | 43 | 31 |  |  | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 |  |  | 79 | 18 | 7.9 | 15.8 | 27.65 | 27.65 | 0 | 0 | 0 | 18 |  |  | 53 | 23 | 11.66 | 13.78 | 13.78 | 13.78 | 2 | 21 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 368 | 8 | 80.96 | 95.68 | 95.68 | 95.68 | 0 | 0 | 0 | 8 |  |  | 0 | 47 |  |  |  |  | 8 | 0 | 30 | 9 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
9 | I | 319 | cum | 0 | 0 | 460 | 301 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 34 | 0 | 0 | 5.1 | 13.6 | 15.3 | 0 | 0 | 0 | 0 |  |  | 52 | 60 | 5.2 | 10.4 | 18.2 | 18.2 | 0 | 0 | 39 | 21 |  |  | 34 | 86 | 3.4 | 6.8 | 11.9 | 11.9 | 0 | 0 | 40 | 46 |  |  | 70 | 51 | 15.7308 | 18.2025 | 18.2025 | 17.8641 | 0 | 39 | 5 | 7 |  |  | 0 | 8 | 0 | 0 | 0 | 0 | 1 | 7 | 0 | 0 |  |  | 0 | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 |  |  | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 |  |  | 270 | 0 | 59.4 | 70.2 | 70.2 | 70.2 | 0 | 0 | 0 | 0 |  |  | 0 | 4 |  |  |  |  | 0 | 0 | 0 | 4 |  |  | 0 | 54 |  |  |  |  | 20 | 34 | 0 | 0
10 | J | 234 | cum | 0 | 0 | 639 | 37 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 |  |  | 37 | 23 | 8.14 | 9.62 | 9.62 | 9.62 | 14 | 9 | 0 | 0 |  |  | 602 | 0 | 132.44 | 156.52 | 156.52 | 156.52 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
11 | K | 610 | cum | 0 | 0 | 594 | 31 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 594 | 2 | 130.68 | 154.44 | 154.44 | 154.44 | 0 | 0 | 0 | 2 |  |  | 0 | 29 |  |  |  |  | 0 | 0 | 22 | 7 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
[124 empty] | 0% | 15% | 40% | 45%
Track Laying
Sr. No. | Area | Scope | UoM | Cumulative Till Date |  |  |  | Till Mar'22 |  |  |  | Apr'22 |  |  |  | Construction | [7 empty] | May'22 |  |  |  | Construction | [7 empty] | Jun'22 |  |  |  | Construction | [7 empty] | Jul'22 |  |  |  | Construction | [7 empty] | Aug'22 |  |  |  | Construction | [7 empty] | Sep'22 |  |  |  | Construction | [7 empty] | Oct'22 |  |  |  | Construction | [7 empty] | Nov'22 |  |  |  | Construction | [7 empty] | Dec'22 |  |  |  | Construction | [7 empty] | Jan'23 |  |  |  | Construction | [7 empty] | Feb'23 |  |  |  | Construction | [7 empty] | Mar'23 |  |  |  | Construction | [7 empty] | Apr'23 |  |  |  | Construction | [7 empty] | May'23 |  |  |  | Construction | [7 empty] | Jun'23 |  |  |  | Construction | [7 empty] | Jul'23 |  |  |  | Construction | [7 empty] | Aug'23 |  |  |  | Construction | [7 empty] | Sep'23 |  |  |  | Construction | [7 empty] | Oct'23 |  |  |  | Construction | [7 empty] | Nov'23 |  |  |  | Construction | [7 empty] | Dec'23 |  |  |  | Construction
|  |  |  | Design |  | Construction |  | Design |  | Construction |  | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual | Design |  | Construction |  | Plan | Plan | Plan | Plan | Actual | Actual | Actual | Actual
|  |  |  | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4 | Plan | Actual | Plan | Actual | Week1 | Week2 | Week3 | Week4 | Week1 | Week2 | Week3 | Week4
| Total: | 0 |  | 0 | 0 | 1266 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 50 | 100 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 50 | 100 | 100 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | 0 | 50 | 30 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 150 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 166 | 0 | 16.6 | 33.2 | 58.1 | 58.1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | A |  | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
2 | B |  | cum | 0 | 0 | 100 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 100 | 0 |  |  | 50 | 50 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
3 | C |  | cum | 0 | 0 | 72 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 72 | 0 | 7.2 | 14.4 | 25.2 | 25.2 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
4 | D |  | cum | 0 | 0 | 800 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 300 | 0 | 50 | 100 | 100 | 50 | 0 | 0 | 0 | 0 |  |  | 300 | 0 | 50 | 100 | 100 | 50 | 0 | 0 | 0 | 0 |  |  | 100 | 0 | 25 | 25 | 25 | 25 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 100 | 0 |  | 50 | 30 | 20 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
5 | E |  | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
6 | F |  | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
7 | G |  | cum | 0 | 0 | 69 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 69 | 0 | 6.9 | 13.8 | 24.15 | 24.15 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
8 | H |  | cum | 0 | 0 | 225 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 200 | 0 |  |  | 100 | 100 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 25 | 0 | 2.5 | 5 | 8.75 | 8.75 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
9 | I |  | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
10 | J |  | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0
11 | K |  | cum | 0 | 0 | 0 | 0 | [78 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  |  | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0

## Activity-wise (hidden)
Sr. No. | Activity | Scope | UoM | CTD Achieved | time axis 2022-01-01 to 2023-12-01
| Total Concreting: | 55016.8 |  | 17162.35 | 0 | 0 | 21 | 955 | 754 | 952.35 | 1023 | 1439 | 2085 | 50 | 65 | 0 | 69 | 21 | 12 | 86 | 79 | 86 | 43 | 0 | 86 | 122 | 67 | 84 | 121 | 0 | 0 | 120 | 98 | 150 | 105 | 128 | 56 | 0 | 76 | 48 | 166 | 83 | 64 | 2807 | 110 | 0 | 69 | 111 | 0 | 130 | 151 | 0 | 144 | 89 | 131 | 118 | 138 | 82 | 0 | 209 | 76 | 115 | 143 | 98 | 102 | 0 | 0 | 106 | 46 | 128 | 104 | 125 | 72 | 0 | 210 | 3981 | 73 | 108 | 141 | 108 | 0 | 214 | 192 | 162 | 143 | 134 | 182 | 0 | 158 | 141 | 229 | 86 | 221 | 117 | 0 | 66 | 96 | 162 | 187 | 226 | 94 | 0 | 252 | 127 | 183 | 179 | 3145 | 85 | 135 | 0 | 153.5 | 107 | 76 | 68 | 228 | 130 | 0 | 48 | 63 | 221 | 161 | 157 | 157.5 | 0 | 125.5 | 147 | 123 | 61.5 | 166 | 0 | 0 | 49 | 92 | 190 | 99 | 39 | 12 | 251 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | PCC | 2079 | cum | 1090 | 0 | 0 | 21 | 102 | 93 | 51 | 103 | 64 | 211 | 0 | 14 | 0 | 0 | 9 | 0 | 8 | 8 | 0 | 0 | 0 | 32 | 21 | 4 | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 9 | 0 | 12 | 12 | 0 | 18 | 0 | 108 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 6 | 12 | 18 | 0 | 0 | 0 | 12 | 15 | 18 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 217 | 0 | 0 | 0 | 0 | 0 | 36 | 31 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 51 | 0 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 10 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 18 | 14 | 0 | 0 | 0 | 6 | 0 | 16 | 0 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0
2 | RCC Foundation | 11387 | cum | 6067.75 | 0 | 0 | 0 | 616 | 398 | 553.75 | 450 | 542 | 787 | 40 | 20 | 0 | 40 | 0 | 0 | 20 | 30 | 36 | 0 | 0 | 20 | 40 | 0 | 40 | 77 | 0 | 0 | 40 | 40 | 110 | 27 | 20 | 20 | 0 | 20 | 20 | 107 | 20 | 0 | 1006 | 40 | 0 | 20 | 89 | 0 | 40 | 60 | 0 | 58 | 0 | 40 | 40 | 60 | 20 | 0 | 80 | 40 | 49 | 29 | 49 | 29 | 0 | 0 | 0 | 0 | 69 | 20 | 60 | 0 | 0 | 114 | 1098 | 20 | 40 | 20 | 46 | 0 | 50 | 69 | 0 | 40 | 60 | 60 | 0 | 60 | 28 | 60 | 20 | 40 | 40 | 0 | 20 | 0 | 60 | 100 | 60 | 20 | 0 | 40 | 45 | 60 | 40 | 617 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 0 | 77 | 40 | 40 | 40 | 0 | 0 | 40 | 0 | 0 | 60 | 0 | 0 | 0 | 0 | 60 | 60 | 0 | 0 | 60
3 | Step Footing | 2898 | cum | 1488 | 0 | 0 | 0 | 129 | 98 | 151 | 103 | 143 | 204 | 10 | 0 | 0 | 15 | 0 | 0 | 10 | 5 | 0 | 5 | 0 | 5 | 0 | 19 | 0 | 0 | 0 | 0 | 32 | 10 | 10 | 27 | 10 | 0 | 0 | 10 | 10 | 5 | 21 | 0 | 230 | 0 | 0 | 25 | 10 | 0 | 10 | 15 | 0 | 15 | 5 | 13 | 0 | 0 | 0 | 0 | 25 | 0 | 25 | 0 | 15 | 13 | 0 | 0 | 20 | 0 | 0 | 19 | 5 | 0 | 0 | 15 | 267 | 31 | 10 | 10 | 0 | 0 | 5 | 15 | 39 | 10 | 0 | 5 | 0 | 0 | 5 | 27 | 0 | 25 | 5 | 0 | 10 | 0 | 0 | 0 | 20 | 15 | 0 | 25 | 0 | 0 | 10 | 163 | 5 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 15 | 5 | 0 | 33 | 5 | 0 | 20 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 15 | 0 | 15
4 | Pier 1900 mm | 3274 | cum | 1786.6 | 0 | 0 | 0 | 108 | 131 | 171.6 | 156 | 162 | 132 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | 0 | 12 | 0 | 0 | 0 | 12 | 6 | 12 | 6 | 0 | 0 | 0 | 12 | 6 | 12 | 0 | 12 | 0 | 6 | 6 | 6 | 12 | 0 | 234 | 12 | 0 | 12 | 12 | 0 | 6 | 12 | 0 | 12 | 12 | 12 | 0 | 0 | 3 | 0 | 12 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 12 | 12 | 18 | 12 | 12 | 0 | 0 | 27 | 410 | 0 | 12 | 12 | 0 | 0 | 27 | 12 | 16 | 18 | 0 | 24 | 0 | 24 | 18 | 18 | 18 | 12 | 24 | 0 | 24 | 0 | 24 | 24 | 25 | 6 | 0 | 24 | 24 | 12 | 12 | 282 | 0 | 6 | 0 | 12 | 24 | 18 | 0 | 24 | 0 | 0 | 12 | 12 | 12 | 12 | 0 | 24 | 0 | 0 | 24 | 6 | 0 | 18 | 0 | 0 | 24 | 0 | 12 | 12 | 12 | 0 | 18
5 | Pier 1600 mm | 2954 | cum | 904 | 0 | 0 | 0 | 0 | 34 | 25 | 59 | 89 | 72 | 0 | 25 | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 12 | 0 | 5 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 172 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 18 | 0 | 18 | 12 | 18 | 5 | 0 | 20 | 0 | 29 | 15 | 4 | 0 | 0 | 0 | 10 | 10 | 5 | 5 | 0 | 0 | 0 | 0 | 185 | 10 | 10 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 7 | 0 | 0 | 18 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 15 | 25 | 5 | 0 | 25 | 0 | 25 | 25 | 268 | 0 | 25 | 0 | 26 | 16 | 40 | 6 | 30 | 0 | 0 | 0 | 0 | 15 | 18 | 0 | 8 | 0 | 0 | 10 | 0 | 0 | 18 | 0 | 0 | 10 | 0 | 10 | 14 | 12 | 0 | 10
6 | Pier Cap | 6104 | cum | 1017 | 0 | 0 | 0 | 0 | 0 | 0 | 68 | 91 | 127 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | 14 | 0 | 0 | 13 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 28 | 145 | 0 | 0 | 12 | 0 | 0 | 14 | 13 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 0 | 12 | 0 | 42 | 328 | 0 | 0 | 15 | 14 | 0 | 24 | 0 | 30 | 0 | 14 | 26 | 0 | 14 | 12 | 13 | 0 | 24 | 0 | 0 | 12 | 0 | 42 | 0 | 0 | 0 | 0 | 30 | 0 | 14 | 44 | 258 | 0 | 0 | 0 | 29 | 31 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 30 | 0 | 0 | 0 | 14 | 0 | 35 | 0 | 0 | 0 | 0 | 15 | 2 | 14 | 0 | 0 | 0 | 28
7 | Track Beam with Nose | 7192.8 | cum | 1261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 120 | 0 | 0 | 0 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 12 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 180 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 12 | 0 | 0 | 24 | 0 | 12 | 0 | 0 | 12 | 0 | 12 | 24 | 12 | 24 | 0 | 0 | 468 | 12 | 12 | 36 | 12 | 0 | 36 | 24 | 24 | 0 | 24 | 12 | 0 | 12 | 24 | 12 | 24 | 24 | 12 | 0 | 0 | 24 | 12 | 12 | 36 | 12 | 0 | 24 | 12 | 36 | 0 | 457 | 24 | 24 | 0 | 36 | 12 | 0 | 24 | 24 | 12 | 0 | 0 | 0 | 36 | 24 | 10 | 27 | 0 | 30 | 24 | 12 | 24 | 11 | 0 | 0 | 0 | 31 | 12 | 0 | 0 | 12 | 48
8 | Track Beam without Nose | 6888 | cum | 2235 | 0 | 0 | 0 | 0 | 0 | 0 | 60 | 228 | 228 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 24 | 12 | 0 | 0 | 24 | 12 | 0 | 12 | 0 | 0 | 12 | 24 | 12 | 12 | 24 | 0 | 0 | 24 | 0 | 0 | 12 | 12 | 480 | 12 | 0 | 0 | 0 | 0 | 24 | 12 | 0 | 24 | 36 | 36 | 12 | 36 | 24 | 0 | 36 | 24 | 0 | 36 | 0 | 36 | 0 | 0 | 24 | 12 | 24 | 12 | 24 | 24 | 0 | 12 | 612 | 0 | 12 | 36 | 24 | 0 | 12 | 12 | 36 | 36 | 36 | 36 | 0 | 36 | 24 | 36 | 12 | 24 | 24 | 0 | 0 | 24 | 24 | 24 | 24 | 24 | 0 | 24 | 24 | 24 | 24 | 627 | 24 | 24 | 0 | 24 | 24 | 0 | 24 | 24 | 36 | 0 | 0 | 24 | 36 | 36 | 22 | 38 | 0 | 36 | 36 | 36 | 36 | 32 | 0 | 0 | 0 | 30 | 36 | 13 | 0 | 0 | 36
9 | h - Section Beam | 5610 | cum | 423.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 36 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 144 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 0 | 24 | 0 | 12 | 12 | 12 | 0 | 12 | 12 | 12 | 0 | 159.5 | 12 | 12 | 0 | 24 | 0 | 0 | 0 | 12 | 12 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 0 | 12 | 12 | 12 | 0 | 10.5 | 0 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | 12
10 | U - Section Beam | 5430 | cum | 881.5 | 0 | 0 | 0 | 0 | 0 | 0 | 24 | 48 | 156 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 0 | 0 | 0 | 24 | 0 | 12 | 0 | 24 | 0 | 0 | 0 | 0 | 24 | 0 | 12 | 216 | 24 | 0 | 0 | 0 | 0 | 24 | 24 | 0 | 12 | 24 | 12 | 24 | 0 | 0 | 0 | 24 | 0 | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 0 | 252 | 0 | 12 | 0 | 12 | 0 | 24 | 24 | 0 | 24 | 0 | 12 | 0 | 12 | 0 | 12 | 0 | 12 | 12 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 24 | 0 | 0 | 24 | 185.5 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 12 | 24 | 0 | 7 | 15 | 0 | 12 | 0 | 12 | 0 | 10.5 | 0 | 0 | 0 | 9 | 12 | 0 | 0 | 0 | 24
11 | Pre-cast Slab | 1200 | cum | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0.5 | 0 | 1.5 | 1 | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Erection-Track Beam with Nose | 7192.8 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Erection-Track Beam without Nose | 6888 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
14 | Erection-h - Section Beam | 5610 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
15 | Erection-U - Section Beam | 5430 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
16 | Erection-Pre-cast Slab | 4000 | cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | Track Laying | 10.2 | km | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Pictorial (hidden)
1 | 2022-08-01 | Footing 1 Nos | RCC | 20
|  | Step Footing 1 Nos | RCC | 5
|  | Pier 1900 mm | RCC | 12 |  | 1 | 2022-08-01 | Footing 1 Nos | RCC | 20
|  | Track Beam Without Nose | RCC |  | 40 |  |  | Step Footing 1 Nos | RCC | 5
[8 empty] | Pier 1900 mm | RCC | 12
[8 empty] | Track Beam Without Nose | RCC |  | 40
Excavation
PCC
Footing
Pier 1900 mm
Pier 1600 mm
Pier Cap

## Jan-23 Plan (hidden)
|  |  | 3 | 20 | 5 | 6 | 6 | 10 |  |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 24 | 24 | 24 | 24 | 25 | 67 | 34 |  |  | Track beam with nose |  | 1140 | 95 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 72 | 480 | 120 | 150 | 402 | 340 | 1564 |  | Track beam without nose |  | 1080 | 90
Part A | Nos. | 8 | 8 | 8 | 8 | 8 | 8 | 8 |  |  | h-section beam |  | 360 | 30
| Qty |  | 24 | 160 | 40 | 48 | 48 | 80 | 400 |  | U-section beam |  | 360 | 30
Part B | Nos. | 4 | 4 | 4 | 4 | 4 |  | 2 |  | Site Clearence for 4 footing under BRU to be given by 15th January 2023 | Pre-cast Slab |  | 50 | 100
| Qty |  | 12 | 80 | 20 | 24 | 0 | 20 | 156 |  | Total: |  | 2990 | 345
Part H | Nos. | 2 | 2 | 2 | 2 | 2 | 10
| Qty |  | 6 | 40 | 10 | 12 | 60 | 0 | 128 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total
Part C | Nos. | 6 | 6 | 6 | 6 | 6 | 23 |  |  | Clearence to be given by MECON for 4 footings by 7th January 2023 |  |  | A | 400 | 271.8182 | 671.8182
| Qty |  | 18 | 120 | 30 | 36 | 138 | 0 | 342 |  |  |  | B | 156 | 271.8182 | 427.8182
Part I | Nos. | 4 | 4 | 4 | 4 | 5 | 14 | 11 |  |  |  |  | C | 342 | 271.8182 | 613.8182
| Qty |  | 12 | 80 | 20 | 30 | 84 | 110 | 336 |  |  |  | D | 202 | 271.8182 | 473.8182
Part D | Nos. | 0 | 0 | 0 | 0 | 0 | 12 | 13 |  |  |  |  | E | 300 | 271.8182 | 571.8182
| Qty |  | 0 | 0 | 0 | 0 | 72 | 130 | 202 |  |  |  | F | 0 | 271.8182 | 271.8182
Priority Section-2 | Nos. | 16 | 16 | 20 | 20 | 42 | 24 | 0 |  |  |  |  | G | 454 | 271.8182 | 725.8182
| Qty | 0 | 48 | 400 | 100 | 252 | 144 | 0 | 944 |  |  |  | H | 128 | 271.8182 | 399.8182
Part E | Nos. | 2 | 2 | 6 | 6 | 10 | 14 | [5 empty] | I | 336 | 271.8182 | 607.8182
| Qty |  | 6 | 120 | 30 | 60 | 84 | 0 | 300 |  |  |  | J | 0 | 271.8182 | 271.8182
Part F | Nos. | [11 empty] | K | 190 | 271.8182 | 461.8182
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 2508 | 2990 | 5498
Part G | Nos. | 10 | 10 | 10 | 10 | 19 | 10 |  |  | Road Diversion for 5 footings need to be done by JSW by 10th January
| Qty |  | 30 | 200 | 50 | 114 | 60 | 0 | 454
Part J | Nos. |  | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part K | Nos. | 4 | 4 | 4 | 4 | 13 |  |  |  | Clearance for 4 footing to be given by 20th Jan 2023
| Qty |  | 12 | 80 | 20 | 78 | 0 | 0 | 190
Total | Nos. | 40 | 40 | 44 | 44 | 67 | 91 | 34
| Qty | 0 | 120 | 880 | 220 | 402 | 546 | 340 | 2508
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 627.9 | 21%
[10 empty] | Week 2 (9 to 16) | 807.3 | 27%
[10 empty] | Week 3 (17 to 24) | 807.3 | 27%
[10 empty] | Week 4 (25 to 31) | 747.5 | 25%
[10 empty] | Total | 2990
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 601.92 | 24% | 22.5%
[10 empty] | Week 2 (9 to 16) | 627 | 25% | 26%
[10 empty] | Week 3 (17 to 24) | 627 | 25% | 26%
[10 empty] | Week 4 (25 to 31) | 652.08 | 26% | 25.5%
[10 empty] | Total | 2508
[10 empty] | Monthly Concreting Target | 5498 | cum
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 60 | 27 | 33 | 24 | 4 | 148
| Qty | 720 | 324 | 396 | 288 | 48 | 1776
Part A | Nos. | [5 empty] | 0 | [6 empty] | A | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | B | 16
Part B | Nos. | 8 |  |  | 4 | 4 | 16 | [6 empty] | C | 0
| Qty | 96 | 0 | 0 | 48 | 48 | 192 | [6 empty] | D | 98
Part H | Nos. | [5 empty] | 0 | [6 empty] | E | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | F | 0
Part C | Nos. | [5 empty] | 0 | [6 empty] | G | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | H | 0
Part I | Nos. | 16 |  | 12 | 6 |  | 34 | [6 empty] | I | 34
| Qty | 192 | 0 | 144 | 72 | 0 | 408 | [6 empty] | J | 0
Part D | Nos. | 36 | 27 | 21 | 14 |  | 98 | [6 empty] | K | 0
| Qty | 432 | 324 | 252 | 168 | 0 | 1176 | [7 empty] | 148
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 7.4 | 5%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 22.2 | 15%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 51.8 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 66.6 | 45%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 148
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 60 | 27 | 33 | 24 | 4 | 148
| Qty | 720 | 324 | 396 | 288 | 48 | 1776

## Feb-23 Plan (hidden)
|  |  | 3 | 20 | 5 | 6 | 6 | 10 |  |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 17 | 17 | 17 | 17 | 24 | 38 | 38 |  |  | Track beam with nose |  | 1092 | 91 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 51 | 340 | 85 | 144 | 228 | 620 | 1468 |  | Track beam without nose |  | 936 | 78
Part A | Nos. | 5 | 5 | 5 | 5 | 9 | 9 | 8 |  |  | h-section beam |  | 312 | 26
| Qty |  | 15 | 100 | 25 | 54 | 54 | 80 | 328 |  | U-section beam |  | 312 | 26
Part B | Nos. | 2 | 2 | 2 | 2 | 2 |  | 6 |  | As front is not available 6 Pier Cap can be Achieved | Pre-cast Slab |  | 35 | 70
| Qty |  | 6 | 40 | 10 | 12 | 0 | 60 | 128 |  | Total: |  | 2687 | 291
Part H | Nos. | [6 empty] | 5 | [9 empty] | Month Plan | Interim
| Qty |  | 0 | 0 | 0 | 0 | 0 | 150 | 150 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 150 | 72.75
Part C | Nos. | 10 | 10 | 10 | 10 | 12 | 23 | 5 |  | Clearence to be given by MECON for 10 footings by 7th Feb 2023 |  |  | A | 328 | 244.2727 | 572.2727 | RCC Foundation | 1000 | 485
| Qty |  | 30 | 200 | 50 | 72 | 138 | 50 | 540 |  |  |  | B | 128 | 244.2727 | 372.2727 | Step Footing | 250 | 121.25
Part I | Nos. |  |  |  |  | 1 | 4 | 13 |  |  |  |  | C | 540 | 244.2727 | 784.2727 | Pier 1900 mm | 336 | 162.96
| Qty |  | 0 | 0 | 0 | 6 | 24 | 260 | 290 |  |  |  | D | 32 | 244.2727 | 276.2727 | Pier 1600 mm | 420 | 203.7
Part D | Nos. | [5 empty] | 2 | 1 |  |  |  |  | E | 174 | 244.2727 | 418.2727 | Pier Cap | 620 | 300.7
| Qty |  | 0 | 0 | 0 | 0 | 12 | 20 | 32 |  |  |  | F | 120 | 244.2727 | 364.2727 | Track Beam with Nose | 1092 | 529.62
Priority Section-2 | Nos. | 16 | 33 | 33 | 33 | 32 | 32 | 0 |  |  |  |  | G | 484 | 244.2727 | 728.2727 | Track Beam without Nose | 936 | 453.96
| Qty | 0 | 99 | 660 | 165 | 192 | 192 | 0 | 1308 |  |  |  | H | 150 | 244.2727 | 394.2727 | H - Section Beam | 312 | 151.32
Part E | Nos. | 3 | 3 | 3 | 3 | 3 | 12 | [5 empty] | I | 290 | 244.2727 | 534.2727 | U - Section Beam | 312 | 151.32
| Qty |  | 9 | 60 | 15 | 18 | 72 | 0 | 174 |  |  |  | J | 0 | 244.2727 | 244.2727 | Pre-cast Slab | 35 | 16.975
Part F | Nos. | [5 empty] | 20 | [5 empty] | K | 530 | 244.2727 | 774.2727
| Qty |  | 0 | 0 | 0 | 0 | 120 | 0 | 120 |  |  |  |  | 2776 | 2687 | 5463
Part G | Nos. | 13 | 13 | 13 | 13 | 20
| Qty |  | 39 | 260 | 65 | 120 | 0 | 0 | 484
Part J | Nos.
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part K | Nos. |  | 17 | 17 | 17 | 9 |  |  |  | Clearence to be given by 10th Feb 2023 from JSW.
| Qty |  | 51 | 340 | 85 | 54 | 0 | 0 | 530
Total | Nos. | 33 | 50 | 50 | 50 | 56 | 70 | 38
| Qty | 0 | 150 | 1000 | 250 | 336 | 420 | 620 | 2776
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 644.88 | 24%
[10 empty] | Week 2 (9 to 16) | 671.75 | 25%
[10 empty] | Week 3 (17 to 24) | 671.75 | 25%
[10 empty] | Week 4 (25 to 31) | 698.62 | 26%
[10 empty] | Total | 2687
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 582.96 | 21% | 22.5% | 48.5%
[10 empty] | Week 2 (9 to 16) | 749.52 | 27% | 26%
[10 empty] | Week 3 (17 to 24) | 749.52 | 27% | 26%
[10 empty] | Week 4 (25 to 31) | 694 | 25% | 25.5%
[10 empty] | Total | 2776
[10 empty] | Monthly Concreting Target | 5463 | cum
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 82 | 52 | 30 | 36 | 0 | 200 | [10 empty] | Month Plan | Interim
| Qty | 984 | 624 | 360 | 432 | 0 | 2400 | [9 empty] | Track beam with nose | 82 | 24.6
Part A | Nos. | [5 empty] | 0 | [6 empty] | A | 0 |  | Track beam without nose | 52 | 15.6
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | B | 44 |  | h-section beam | 30 | 9
Part B | Nos. | 24 | 8 | 8 | 4 |  | 44 | [6 empty] | C | 0 |  | U-section beam | 36 | 10.8
| Qty | 288 | 96 | 96 | 48 | 0 | 528 | [6 empty] | D | 104 |  | Pre-cast Slab | 0 | 0
Part H | Nos. | [5 empty] | 0 | [6 empty] | E | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | F | 0
Part C | Nos. | [5 empty] | 0 | [6 empty] | G | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | H | 0
Part I | Nos. | 24 | 4 | 8 | 16 |  | 52 | [6 empty] | I | 52
| Qty | 288 | 48 | 96 | 192 | 0 | 624 | [6 empty] | J | 0
Part D | Nos. | 34 | 40 | 14 | 16 |  | 104 | [6 empty] | K | 0
| Qty | 408 | 480 | 168 | 192 | 0 | 1248 | [7 empty] | 200
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 20 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 40 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 70 | 35%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 70 | 35%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 200
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 82 | 52 | 30 | 36 | 0 | 200
| Qty | 984 | 624 | 360 | 432 | 0 | 2400

## Dec-23 Plan (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 | 35 |  |  |  | 12 | 0.5
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 10 | 10 | 10 | 10 | 10 | 12 | 7 |  |  | Track beam with nose |  | 480 | 40 | Concrete with OPC cement to be available at JSW batching Plant
| Qty | 0 | 30 | 200 | 50 | 60 | 60 | 158 | 558 |  | Track beam without nose |  | 480 | 40
Part A | Nos. | [9 empty] | h-section beam |  | 324 | 27
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | U-section beam |  | 276 | 23
Part B | Nos. | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  |  | Pre-cast Slab |  | 20 | 40
| Qty |  | 6 | 40 | 10 | 12 | 10 | 80 | 158 |  | Total: |  | 1580 | 170 | [5 empty] | Pre-cast |  |  | Cast Insitu | Total | UOM | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Part H | Nos. | 2 | 2 | 2 | 2 | 2 | 4 | [10 empty] | Month Plan | Interim |  | Qty | Cum | Cum | Cum | Nos. | 60 | 60 | 20 | 20 | 60 | 220
| Qty |  | 6 | 40 | 10 | 12 | 20 |  | 88 |  | All qty are in Cum |  |  | Cast-in-situ | Pre-cast | Total | PCC | 66 | 31.9943 | A | 0 | 0 | 204 | 204 | Qty | 720 | 720 | 240 | 240 | 30 | 1950
Part C | Nos. | 6 | 6 | 6 | 6 | 6 | 6 | 3 |  |  |  |  | A | 0 | 0 | 0 | RCC Foundation | 480 | 232.6856 | B | 0 | 0 | 358 | 358
| Qty |  | 18 | 120 | 30 | 36 | 30 | 78 | 312 |  |  |  | B | 158 | 12 | 170 | Step Footing | 120 | 58.1714 | C | 16 | 192 | 0 | 192
Part I | Nos. | [11 empty] | C | 312 | 96 | 408 | Pier 1900 mm | 144 | 69.8057 | D | 0 | 0 | 0 | 0
| Qty |  | 0 | 0 | 0 |  | 0 |  | 0 |  |  |  | D | 0 | 0 | 0 | Pier 1600 mm | 500 | 242.3809 | E | 0 | 0 | 0 | 0
Part D | Nos. | [11 empty] | E | 346 | 48 | 394 | Pier Cap | 438 | 212.3256 | F | 0 | 0 | 150 | 150
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | F | 0 | 0 | 0 | Track Beam with Nose | 480 | 232.6856 | G | 159 | 1218 | 452 | 1670
Priority Section-2 | Nos. | 6 | 12 | 14 | 14 | 14 | 88 | 8 |  |  |  |  | G | 304 | 286 | 590 | Track Beam without Nose | 480 | 232.6856 | H | 5 | 60 | 68 | 128
| Qty | 0 | 36 | 280 | 70 | 84 | 440 | 280 | 1190 |  |  |  | H | 88 | 96 | 184 | H - Section Beam | 324 | 157.0628 | I | 40 | 480 | 0 | 480
Part E | Nos. | 6 | 6 | 8 | 8 | 8 |  | 4 |  |  |  |  | I | 0 | 12 | 12 | U - Section Beam | 276 | 133.7942 | J | 0 | 0 | 278 | 278
| Qty |  | 18 | 160 | 40 | 48 | 0 | 80 | 346 |  |  |  | J | 200 | 696 | 896 | Pre-cast Slab | 20 | 9.6952 | K | 0 | 0 | 594 | 594
Part F | Nos. | [11 empty] | K | 340 | 334 | 674 | Abutment wall- PART-A | 60 | 29.0857 | Abutment wall- PART-A |  |  | 84 | 84
| Qty |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  |  |  | Abutment wall- PART-A | 60 |  | 60 | Abutment wall- PART-D | 120 | 58.1714 | Abutment wall- PART-D |  |  | 500 | 500
Part G | Nos. |  | 6 | 6 | 6 | 6 | 20 | [5 empty] | Abutment wall- PART-D | 120 |  | 120 | Cast In-situ slab- 1- PART-G | 0 | 0 | Cast In-situ slab- 1- PART-G |  |  |  | 0
| Qty |  | 18 | 120 | 30 | 36 | 100 |  | 304 |  |  |  | Cast In-situ slab- 1- PART-G | 0 |  | 0 | Cast In-situ slab- 2- PART-G | 529 | 256.439 | Cast In-situ slab- 2- PART-G |  |  |  | 0
Part J | Nos. | [6 empty] | 4 |  |  |  |  | Cast In-situ slab- 2- PART-G | 529 |  | 529 | Cast In-situ slab- PART-C | 0 | 0 | Cast In-situ slab- PART-C |  |  |  | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 200 | 200 |  |  |  | Cast In-situ slab- PART-C | 0 |  | 0 |  | 4037 | 1956.9831 |  | 220 | 1950 | 2688 | 4638
Part K | Nos. | [5 empty] | 68 | [6 empty] | 2457 | 1580 | 4037
| Qty |  | 0 | 0 | 0 | 0 | 340 | 0 | 340
Total | Nos. |  | 0 | 0 | 0 | 0 | 1700 | 0 | 1700
| Qty | 0 | 66 | 480 | 120 | 144 | 500 | 438 | 1748
Abutment wall- PART-A |  |  | 10 | 80 |  |  |  |  | 60
Abutment wall- PART-D |  |  |  | 120 |  |  |  |  | 120
Cast In-situ slab- 1- PART-G | [8 empty] | 0
Cast In-situ slab- 2- PART-G |  |  |  | 529 |  |  |  |  | 529
Cast In-situ slab- PART-C
Cast Insitu | [8 empty] | 0
2457
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 378.4913 | 23.96%
[10 empty] | Week 2 (9 to 16) | 395.4027 | 25.03%
[10 empty] | Week 3 (17 to 24) | 395.4027 | 25.03%
[10 empty] | Week 4 (25 to 31) | 410.7034 | 25.99%
[10 empty] | Total | 1580
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 515.7231 | 20.99% | 22.47% | 48.48%
[10 empty] | Week 2 (9 to 16) | 662.9419 | 26.98% | 26%
[10 empty] | Week 3 (17 to 24) | 662.9419 | 26.98% | 26%
[10 empty] | Week 4 (25 to 31) | 615.393 | 25.05% | 25.52%
[10 empty] | Total | 2457
[10 empty] | Monthly Concreting Target | 4037 | cum
|  | 12 | 12 | 12 | 12 | 0.5
Erection
|  | Track beam with nose | Track beam without nose | U-section beam | h-section beam | Pre-cast Slab | Total | [10 empty] | Erection
Priority Section-1 | Nos. | 70 | 32 | 42 | 34 | 30 | 208 | [7 empty] | Erection |  |  | Month Plan | Interim
| Qty | [5 empty] | 0 | [9 empty] | Track beam with nose | 82 | 24.6
Part A | Nos. | 12 |  | 6 | 6 | 18 | 42 | [6 empty] | A | 42 |  | Track beam without nose | 46 | 13.8
| Qty | [5 empty] | 0 | [6 empty] | B | 40 |  | h-section beam | 46 | 13.8
Part B | Nos. | 10 | 8 | 6 | 4 | 12 | 40 | [6 empty] | C | 80 |  | U-section beam | 38 | 11.4
| Qty | [5 empty] | 0 | [6 empty] | D | 0 |  | Pre-cast Slab | 33 | 9.9
Part H | Nos. |  |  | 6 |  |  | 6 | [6 empty] | E | 0
| Qty | [5 empty] | 0 | [6 empty] | F | 0
Part C | Nos. | 32 | 16 | 16 | 16 |  | 80 | [6 empty] | G | 0
| Qty | 384 | 192 | 192 | 192 | 0 | 960 | [6 empty] | H | 6
Part I | Nos. | 16 | 8 | 8 | 8 |  | 40 | [6 empty] | I | 40
| Qty | 192 | 96 | 96 | 96 | 0 | 480 | [6 empty] | J | 37
Part D | Nos. | [5 empty] | 0 | [6 empty] | K | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 245
Priority Section-2 | Nos. | 12 | 14 | 4 | 4 | 3 | 37
| Qty | 144 | 168 | 48 | 48 | 36 | 444
Part E | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [7 empty] | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 24.5 | 10% | 30%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 49 | 20%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 85.75 | 35%
Part J | Nos. | 12 | 14 | 4 | 4 | 3 | 37 |  |  | Week 4 (25 to 31) | 85.75 | 35%
| Qty | 144 | 168 | 48 | 48 | 36 | 444 |  |  | Total | 245
Part K | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 82 | 46 | 46 | 38 | 33 | 245
| Qty | 144 | 168 | 48 | 48 | 36 | 444
FTM
Track Linking
A |  | 0
B |  | 100
C |  | 60
D |  | 0
E |  | 0
F |  | 200
G |  | 0
H |  | 200
I |  | 0
J |  | 0
K |  | 0
560

## Precast- Segment Casting plan (hidden)
Straight Girders | [11 empty] | Type of Girder | Cum/ Girder
Precast Girder Type | UOM | PART-B | PART-H | PART-C | PART-I | PART-G | PART-F | PART-J | PART-K | PART-E | Total | H-girder | 12 |  | A
H-girder | NOS | 1 |  |  |  | 10 |  |  |  |  | 11 | U-girder | 12 |  | B | 12
| Cum | 12 | 0 | 0 | 0 | 120 | 0 | 0 | 0 | 0 | 132 | Solid Without Nose | 12 |  | C | 96
U-girder | NOS |  |  |  |  | 2 |  |  |  |  | 2 | Solid With Face Nose | 12 |  | D
| Cum | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 24 | Solid With Side Nose | 12 |  | E | 48
Solid Without Nose | NOS |  |  |  |  | 9 |  |  | 19 |  | 28 | Slab | 0.5 |  | F | 0
| Cum | 0 | 0 | 0 | 0 | 108 | 0 | 0 | 228 | 0 | 336 |  |  |  | G | 286
Solid With Face Nose | NOS | [9 empty] | 0 |  |  |  | H | 96
| Cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | I | 12
Solid With Side Nose | NOS |  |  |  |  | 2 |  |  | 8 |  | 10 |  |  |  | J | 696
| Cum | 0 | 0 | 0 | 0 | 24 | 0 | 0 | 96 | 0 | 120 |  |  |  | K | 334 |  | Nos | Cum
Slab | NOS |  |  |  |  | 20 |  |  | 20 |  | 40 | [5 empty] | A | 0
| Cum | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 10 | 0 | 20 | [5 empty] | B | 12
|  | 12 | 0 | 0 | 0 | 286 | 0 | 0 | 334 | 0 | 632 | [5 empty] | C | 96
Total ( Nos ) | [10 empty] | 91 | [5 empty] | D | 0
Total (Cum) | [10 empty] | 632 | [5 empty] | E | 48
[17 empty] | F | 0
Trapezoidal Girders | [16 empty] | G | 286
Precast Girder Type | UOM | PART-I | PART-H | PART-C | PART-G | PART-J | PART-K | PART-E | Total | [7 empty] | H | 96
H-girder | NOS |  | 8 | 8 |  |  |  |  | 16 | [7 empty] | I | 12
| Cum | 0 | 96 | 96 | 0 | 0 | 0 | 0 | 192 | [7 empty] | J | 696
U-girder | NOS | 1 |  |  |  | 20 |  |  | 21 | [7 empty] | K | 334
| Cum | 12 | 0 | 0 | 0 | 240 | 0 | 0 | 252 |  |  | Type of Girder | Nos | Cum |  |  |  | 1580
Solid Without Nose | NOS |  |  |  |  | 8 |  | 4 | 12 |  |  | H-girder | 27 | 324
| Cum | 0 | 0 | 0 | 0 | 96 | 0 | 48 | 144 |  |  | U-girder | 23 | 276
Solid With Face Nose | NOS |  |  |  |  | 20 |  |  | 20 |  |  | Solid Without Nose | 40 | 480
| Cum | 0 | 0 | 0 | 0 | 240 | 0 | 0 | 240 |  |  | Solid With Face Nose | 20 | 240
Solid With Side Nose | NOS |  |  |  |  | 10 |  |  | 10 |  |  | Solid With Side Nose | 20 | 240
| Cum | 0 | 0 | 0 | 0 | 120 | 0 | 0 | 120 |  |  | Slab | 40 | 20
Slab | NOS | [7 empty] | 0 |  |  | Total | 170 | 1580
| Cum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 12 | 96 | 96 | 0 | 696 | 0 | 48 | 948
Total ( Nos ) | [8 empty] | 79
Total (Cum) | [8 empty] | 948

## Plan- Rohan (hidden)
|  |  | 3 | 20 | 5 | 6 | 5 | 10 | [5 empty] | 12 | 0.5 | 400
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [10 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Foundation | Step Footing | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  |  | Quantity | Nos. | Remarks
| Nos. | 22 | 36 | 30 | 30 | 40 | 100 | 20 |  |  |  | Track beam with nose |  | 720 | 60
| Qty | 0 | 108 | 1184 | 150 | 240 | 500 | 506 | 2688 |  |  | Track beam without nose |  | 720 | 60
Part A | Nos. | 6 | 6 | 6 | 6 | 6 | [5 empty] | h-section beam |  | 240 | 20
| Qty |  | 18 | 120 | 30 | 36 | 0 | 0 | 204 |  |  | U-section beam |  | 240 | 20
Part B | Nos. | 16 | 16 | 10 | 10 | 10 | [5 empty] | Pre-cast Slab |  | 30 | 60
| Qty |  | 48 | 200 | 50 | 60 | 0 | 0 | 358 |  |  | Total: |  | 1950 | 220
Part H | Nos. |  | 2 | 2 | 2 | 2
| Qty |  | 6 | 40 | 10 | 12 | 0 |  | 68 |  |  | All qty are in Cum
Part C | Nos.
| Qty |  | 0 | 0 | 0 | 0 | 0 |  | 0
Part I | Nos.
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part D | Nos.
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos.
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [6 empty] | 5
| Qty |  | 0 | 0 | 0 | 0 | 0 | 150 | 150
Part G | Nos. |  | 6 | 6 | 6 | 6 |  | 12
| Qty |  | 18 | 120 | 30 | 36 | 0 | 248 | 452
Part J | Nos. | [5 empty] | 34 | 3
| Qty |  | 0 | 0 | 0 | 0 | 170 | 108 | 278
Part K | Nos. |  | 6 | 6 | 6 | 16 | 66
| Qty |  | 18 | 120 | 30 | 96 | 330 | 0 | 594
Abutment wall- PART-A | Qty |  |  | 84 |  |  |  |  | 84
Abutment wall- PART-D |  |  |  | 500 |  |  |  |  | 500
Cast In-situ slab- 1- PART-G
Cast In-situ slab- 2- PART-G
Cast In-situ slab- PART-C
[9 empty] | Cast In-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) |  | 430 | 16%
[10 empty] | Week 2 (9 to 15) |  | 672 | 25%
[10 empty] | Week 3 (16 to 22) |  | 672 | 25%
[10 empty] | Week 4 (23 to 31) |  | 914 | 34%
[10 empty] | Total |  | 2688
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) |  | 390 | 20%
[10 empty] | Week 2 (9 to 15) |  | 488 | 25%
[10 empty] | Week 3 (16 to 22) |  | 488 | 25%
[10 empty] | Week 4 (23 to 31) |  | 585 | 30%
[10 empty] | Total |  | 1951
[10 empty] | Monthly Concreting Target |  | 4639 | cum
Erection | [10 empty] | Track Linking | [8 empty] | 12 | 12 | 12 | 12 | 0.5
|  | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total | Remarks | [8 empty] | Pre-cast |  |  | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total | Remarks
Priority Section-1 | Nos. | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | Priority Section-1 | Length (M) | Remarks |  |  |  |  | Priority Section-1 | Nos. | 18 | 20 | 9 | 14 | 0 | 61
| Qty | [5 empty] | 0 | [11 empty] | Qty | 216 | 240 | 108 | 168 | 0 | 732
Part A | Nos. | [5 empty] | 0 |  |  |  | Part A | [6 empty] | Part A | Nos. | [5 empty] | 0
| Qty | [5 empty] | 0 | [11 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Part B | Nos. | [5 empty] | 0 |  |  |  | Part B | [6 empty] | Part B | Nos. | [5 empty] | 0
| Qty | [5 empty] | 0 |  |  |  |  | 100 | [6 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Part H | Nos. | [5 empty] | 0 |  |  |  | Part H | [6 empty] | Part H | Nos. |  |  |  | 5 |  | 5
| Qty | [5 empty] | 0 |  |  |  |  | 200 | [6 empty] | Qty | 0 | 0 | 0 | 60 | 0 | 60
Part C | Nos. | [9 empty] | Part C | [6 empty] | Part C | Nos. | 8 |  | 4 | 4 |  | 16
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Qty | 96 | 0 | 48 | 48 | 0 | 192
Part I | Nos. | [5 empty] | 0 |  |  |  | Part I | [6 empty] | Part I | Nos. | 10 | 20 | 5 | 5 |  | 40
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Qty | 120 | 240 | 60 | 60 | 0 | 480
Part D | Nos. | [5 empty] | 0 |  |  |  | Part D | [6 empty] | Part D | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Priority Section-2 | Nos. | 28 | 41 | 8 | 9 | 24 | 110 |  |  |  | Priority Section-2 | [6 empty] | Priority Section-2 | Nos. | 42 | 40 | 11 | 6 | 60 | 159
| Qty | 336 | 492 | 96 | 108 | 288 | 1320 | [11 empty] | Qty | 504 | 480 | 132 | 72 | 30 | 1218
Part E | Nos. | [9 empty] | Part E | [6 empty] | Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | 20 | 24 | 5 | 6 | 18 |  |  |  |  | Part F | [6 empty] | Part F | Nos. | [5 empty] | 0
| Qty | 240 | 288 | 60 | 72 | 216 | 876 | [11 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Part G | Nos. | [9 empty] | Part G | [6 empty] | Part G | Nos. | 42 | 40 | 11 | 6 | 60 | 159
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Qty | 504 | 480 | 132 | 72 | 30 | 1218
Part J | Nos. | 8 | 17 | 3 | 3 | 6 |  |  |  |  | Part J | [6 empty] | Part J | Nos. | [5 empty] | 0
| Qty | 96 | 204 | 36 | 36 | 72 | 444 | [11 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Part K | Nos. | [9 empty] | Part K | [6 empty] | Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0 | [11 empty] | Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 28 | 41 | 8 | 9 | 24 | 110 |  |  |  | Total | [6 empty] | Total | Nos. | 60 | 60 | 20 | 20 | 60 | 220
| Qty | 336 | 492 | 96 | 108 | 288 | 1320 |  |  |  |  | 300 | [6 empty] | Qty | 720 | 720 | 240 | 240 | 30 | 1950

## Dec-22 Plan (hidden)
|  |  | 3 | 5 | 20 | 6 | 6 | 10 |  |  |  |  | 12 | 1
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Step Footing | Foundation | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 24 | 24 | 24 | 24 | 26 | 60 | 25 |  |  | Track beam with nose |  | 1068 | 89
| Qty | 0 | 72 | 120 | 480 | 156 | 360 | 250 | 1438 |  | Track beam without nose |  | 888 | 74
Part A | Nos. | 6 | 6 | 6 | 6 | 6 | 0 | 0 |  |  | h-section beam |  | 336 | 28
| Qty |  | 18 | 30 | 120 | 36 | 0 | 0 | 204 |  | U-section beam |  | 324 | 27
Part B | Nos. | [9 empty] | Pre-cast Slab |  | 50 | 50
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total: |  | 2666 | 268
Part H | Nos. | 6 | 6 | 6 | 6 | 6 | 21
| Qty |  | 18 | 30 | 120 | 36 | 126 | 0 | 330 |  | All qty are in Cum
Part C | Nos. | 6 | 6 | 6 | 6 | 8 | 0 | [5 empty] | A | 204 | 242.3636 | 446.3636
| Qty |  | 18 | 30 | 120 | 48 | 0 | 0 | 216 |  |  |  | B | 0 | 242.3636 | 242.3636
Part I | Nos. |  | 0 | 0 | 0 | 0 | 21 | 8 |  |  |  |  | C | 216 | 242.3636 | 458.3636
| Qty |  | 0 | 0 | 0 | 0 | 126 | 80 | 206 |  |  |  | D | 482 | 242.3636 | 724.3636
Part D | Nos. | 6 | 6 | 6 | 6 | 6 | 18 | 17 |  |  |  |  | E | 224 | 242.3636 | 466.3636
| Qty |  | 18 | 30 | 120 | 36 | 108 | 170 | 482 |  |  |  | F | 0 | 242.3636 | 242.3636
Priority Section-2 | Nos. | 20 | 22 | 22 | 22 | 42 | 0 | 0 |  |  |  |  | G | 104 | 242.3636 | 346.3636
| Qty | 0 | 66 | 110 | 440 | 252 | 0 | 0 | 868 |  |  |  | H | 330 | 242.3636 | 572.3636
Part E | Nos. | 8 | 8 | 8 | 8 | [7 empty] | I | 206 | 242.3636 | 448.3636
| Qty |  | 24 | 40 | 160 | 0 | 0 | 0 | 224 |  |  |  | J | 24 | 242.3636 | 266.3636
Part F | Nos. | [11 empty] | K | 516 | 242.3636 | 758.3636
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part G | Nos. |  | 2 | 2 | 2 | 8
| Qty |  | 6 | 10 | 40 | 48 | 0 | 0 | 104
Part J | Nos. |  | 0 | 0 | 0 | 4
| Qty |  | 0 | 0 | 0 | 24 | 0 | 0 | 24
Part K | Nos. | 12 | 12 | 12 | 12 | 30
| Qty |  | 36 | 60 | 240 | 180 | 0 | 0 | 516
Total | Nos. | 44 | 46 | 46 | 46 | 68 | 60 | 25
| Qty | 0 | 138 | 230 | 920 | 408 | 360 | 250 | 2306
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 788.5846 | 29.58%
[10 empty] | Week 2 (9 to 16) | 774.5653 | 29.05%
[10 empty] | Week 3 (17 to 24) | 774.5653 | 29.05%
[10 empty] | Week 4 (25 to 31) | 328.2848 | 12.31%
[10 empty] | Total | 2666
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 534.3487 | 23.17% | 26.38% | 26.38%
[10 empty] | Week 2 (9 to 16) | 674.4207 | 29.25% | 29.15% | 29.15%
[10 empty] | Week 3 (17 to 24) | 674.4207 | 29.25% | 29.15% | 29.15%
[10 empty] | Week 4 (25 to 31) | 422.8099 | 18.34% | 15.32% | 15.32%
[10 empty] | Total | 2306
[10 empty] | Monthly Concreting Target | 4972 | cum
Erection
|  | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 20 | 40 | 10 | 10 | 5 | 85
| Qty | 244 | 480 | 122 | 122 | 60 | 1028
Part A | Nos. | [5 empty] | 0
| Qty | 4 | 0 | 2 | 2 | 0 | 8
Part B | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part H | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part C | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part I | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part D | Nos. | 20 | 40 | 10 | 10 | 5 | 85
| Qty | 240 | 480 | 120 | 120 | 60 | 1020
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos. | [5 empty] | 0 |  | Pre-cast Segment Erection | Week-wise Planned
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 1 (1 to 8) | 0 | 0%
Part G | Nos. | [5 empty] | 0 |  |  | Week 2 (9 to 16) | 12.75 | 15%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Week 3 (17 to 24) | 34 | 40%
Part J | Nos. | [5 empty] | 0 |  |  | Week 4 (25 to 31) | 38.25 | 45%
| Qty | 0 | 0 | 0 | 0 | 0 | 0 |  |  | Total | 85
Part K | Nos. | [5 empty] | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 20 | 40 | 10 | 10 | 5 | 85
| Qty | 244 | 480 | 122 | 122 | 60 | 1028

## Nov-22 Plan (hidden)
|  |  | 3.5 | 5.5 | 24 | 6 | 6 | 9 |  |  |  |  | 12
Concreting
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [9 empty] | Pre-cast |  | SMS#4 Hot Metal Elevated Track (Pre-cast)
|  | Excavation | PCC | Step Footing | Foundation | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 0 | 31 | 31 | 30 | 38 | 65 | 20 |  |  | Track beam with nose |  | 540 | 45
| Qty | 0 | 108.5 | 170.5 | 720 | 228 | 390 | 180 | 1797 |  | Track beam without nose |  | 660 | 55
Part A | Nos. | [5 empty] | 2 | 5 |  |  | h-section beam |  | 300 | 25
| Qty |  | 0 | 0 | 0 | 0 | 12 | 45 | 57 |  | U-section beam |  | 300 | 25
Part B | Nos. | [9 empty] | Pre-cast Slab |  | 0 | 0
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Total: |  | 1800 | 150
Part H | Nos. |  | 8 | 8 | 8 |  | 15
| Qty |  | 28 | 44 | 192 | 0 | 90 | 0 | 354 |  | All qty are in Cum
Part C | Nos. |  | 3 | 3 | 2 | 9 | 10 | [5 empty] | A | 57 | 163.6364 | 220.6364
| Qty |  | 10.5 | 16.5 | 48 | 54 | 60 | 0 | 189 |  |  |  | B | 0 | 163.6364 | 163.6364
Part I | Nos. |  | 2 | 2 | 2 | 11 | 15 | 10 |  |  |  |  | C | 189 | 163.6364 | 352.6364
| Qty |  | 7 | 11 | 48 | 66 | 90 | 90 | 312 |  |  |  | D | 885 | 163.6364 | 1048.6364
Part D | Nos. |  | 18 | 18 | 18 | 18 | 23 | 5 |  |  |  |  | E | 240 | 163.6364 | 403.6364
| Qty |  | 63 | 99 | 432 | 108 | 138 | 45 | 885 |  |  |  | F | 0 | 163.6364 | 163.6364
Priority Section-2 | Nos. | 0 | 11 | 11 | 24 | 0 | 0 | 0 |  |  |  |  | G | 0 | 163.6364 | 163.6364
| Qty | 0 | 38.5 | 60.5 | 576 | 0 | 0 | 0 | 675 |  |  |  | H | 354 | 163.6364 | 517.6364
Part E | Nos. |  |  |  | 10 | [7 empty] | I | 312 | 163.6364 | 475.6364
| Qty |  | 0 | 0 | 240 | 0 | 0 | 0 | 240 |  |  |  | J | 297 | 163.6364 | 460.6364
Part F | Nos. | [11 empty] | K | 138 | 163.6364 | 301.6364
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part G | Nos.
| Qty |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Part J | Nos. |  | 9 | 9 | 9
| Qty |  | 31.5 | 49.5 | 216 | 0 | 0 | 0 | 297
Part K | Nos. |  | 2 | 2 | 5
| Qty |  | 7 | 11 | 120 | 0 | 0 | 0 | 138
Total | Nos. | 0 | 42 | 42 | 54 | 38 | 65 | 20
| Qty | 0 | 147 | 231 | 1296 | 228 | 390 | 180 | 2472
[9 empty] | Pre-cast | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 306 | 17%
[10 empty] | Week 2 (9 to 16) | 450 | 25%
[10 empty] | Week 3 (17 to 24) | 450 | 25%
[10 empty] | Week 4 (25 to 31) | 594 | 33%
[10 empty] | Total | 1800
[9 empty] | Cast-in-situ | Week-wise Planned
[10 empty] | Week 1 (1 to 8) | 420.24 | 17%
[10 empty] | Week 2 (9 to 16) | 618 | 25%
[10 empty] | Week 3 (17 to 24) | 618 | 25%
[10 empty] | Week 4 (25 to 31) | 815.76 | 33%
[10 empty] | Total | 2472
[10 empty] | Monthly Concreting Target | 4272 | cum
Erection
|  | Track beam with nose | Track beam without nose | h-section beam | U-section beam | Pre-cast Slab | Total
Priority Section-1 | Nos. | 0 | 0 | 0 | 0 | 0
| Qty | 4 | 0 | 2 | 2 | 0 | 8
Part A | Nos.
| Qty | 4 | 0 | 2 | 2 | 0 | 8
Part B | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part H | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part C | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part I | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part D | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Priority Section-2 | Nos. | 0 | 0 | 0 | 0 | 0
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part E | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part F | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part G | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part J | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Part K | Nos.
| Qty | 0 | 0 | 0 | 0 | 0 | 0
Total | Nos. | 0 | 0 | 0 | 0 | 0
| Qty | 4 | 0 | 2 | 2 | 0 | 8

## Oct-22 Plan (hidden)
|  |  | 3.5 | 25 | 6 | 5 | 11 |  |  |  |  | 12
In-Situ | SMS#4 Hot Metal Elevated Track ( In-Situ) | [8 empty] | Pre-cast | SMS#4 Hot Metal Elevated Track (Pre-cast)
| Plan for the month of October 2022 | [9 empty] | Plan for the month of October 2022
|  | Excavation | PCC | Foundation | Pier 1900 mm | Pier 1600 mm | Pier Cap | Total | Remarks |  |  | Quantity | Nos. | Remarks
Priority Section-1 | Nos. | 0 | 0 | 39 | 45 | 37 | 14 |  |  | Track beam with nose |  | 600 | 50
| Qty | 0 | 0 | 980 | 267 | 185 | 325 | 1757 |  | Track beam without nose |  | 402 | 34
Part A | Nos. |  |  | 2 | 2 |  |  |  |  | h-section beam |  | 252 | 21
| Qty |  |  | 40 | 12 |  |  | 52 |  | U-section beam |  | 219 | 18
Part B | Nos. | [8 empty] | Pre-cast Slab |  | 0 | 0
| Qty | [6 empty] | 0 |  | Total: |  | 1473 | 123
Part H | Nos. |  |  | 12 | 13
| Qty |  |  | 300 | 75 |  |  | 375 |  | All qty are in Cum
Part C | Nos. |  |  | 6 | 8
| Qty |  |  | 160 | 48 |  |  | 208
Part I | Nos. |  |  | 5 | 6 | 37 | 14
| Qty |  |  | 120 | 36 | 185 | 154 | 495
Part D | Nos. |  |  | 14 | 16
| Qty |  |  | 360 | 96 |  | 171 | 627
Priority Section-2 | Nos. | 0 | 0 | 5 | 6 | 0 | 0
| Qty | 0 | 0 | 120 | 36 | 0 | 0 | 156
Part E | Nos.
| Qty | [6 empty] | 0
Part F | Nos.
| Qty | [6 empty] | 0
Part G | Nos. |  |  | 5 | 6
| Qty |  |  | 120 | 36 |  |  | 156
Part J | Nos.
| Qty | [6 empty] | 0
Part K | Nos.
| Qty | [6 empty] | 0
Total | Nos. | 0 | 0 | 44 | 51 | 37 | 14
| Qty | 0 | 0 | 1100 | 303 | 185 | 325 | 1913
[8 empty] | Pre-cast | Week-wise Planned
[9 empty] | Week 1 (1 to 8) | 368.25
[9 empty] | Week 2 (9 to 16) | 368.25
[9 empty] | Week 3 (17 to 24) | 368.25
[9 empty] | Week 4 (25 to 31) | 368.25
[9 empty] | Total | 1473
[8 empty] | Cast-in-situ | Week-wise Planned
[9 empty] | Week 1 (1 to 8) | 478.25
[9 empty] | Week 2 (9 to 16) | 478.25
[9 empty] | Week 3 (17 to 24) | 478.25
[9 empty] | Week 4 (25 to 31) | 478.25
[9 empty] | Total | 1913
[9 empty] | Monthly Target | 3386 | cum

## Sep-22 Plan (hidden)
|  |  | 3 | 25 | 6 | 5 | 11 | [8 empty] | 11
| SMS#4 Hot Metal Elevated Track ( In-Situ) | [8 empty] | SMS#4 Hot Metal Elevated Track (Pre-cast)
| Plan for the month of September | [8 empty] | Plan for the month of September
|  | Excavation | PCC | Foundation | Pier 1900 mm | Pier 1600 mm | Pier Cap | Remark |  | S.No. | Name of Structures | Total No as Per Drawings Received | Balance | Achieved till August | Plan For September
| Part I | 12 | 12 | 12 | 16 | 16 | 7 | Subject to Clearence
| Part C | 11 | 11 | 11 | 7 | 0 |  |  |  | 1 | Track Beam with Nose | 262 | 260 | 2 | 35 | 385
| Part D | 21 | 21 | 21 | 21 | 25 | 10 | Subject to Clearence |  | 2 | Track Beam without Nose | 298 | 281 | 17 | 35 | 385
| Part H | 10 | 10 | 10 | 0 |  |  |  |  | 3 | h - Section Beam | 128 | 126 | 2 | 25 | 275
| Part G | 6 | 6 | 6 | 6 |  |  | Subject to Clearence |  | 4 | U - Section Beam | 114 | 108 | 6 | 25 | 275
| Part A | [5 empty] | 2 |  |  | 5 | Pre-cast Slab | 105 | 105 |  | 0 | 0
| Part B | [5 empty] | 6 | [8 empty] | 1320
| Part J |  |  |  |  | 10
| Part F |  |  |  |  | 9
| Total | 60 | 60 | 60 | 50 | 60 | 25
[8 empty] | Total RCC Quantity |  |  |  | Total RCC Quantity
Weekwise Planned | Week 1 (01 to 11) | 5375.76 | 83.58 | 495.52 | 59.06 | 115.71 | - | 753.87 |  | Weekwise Planned | Week 1 (01 to 11) | 418.14 | 11.9469
| Week 2 (12 to 18) | 2932.23 | 73.13 | 346.86 | 82.69 | 90 | 46.7 | 639.38 |  |  | Week 2 (12 to 18) | 365.87 | 10.4534
| Week 3 (15 to 21) | - | 20.9 | 346.86 | 82.69 | 90 | 81.72 | 622.17 |  |  | Week 3 (15 to 21) | 365.87 | 14.6348
| Week 4 (22 to 31) | - | - | 247.76 | 59.06 | 64.29 | 58.37 | 429.48 |  |  | Week 4 (22 to 31) | 261.33 | 10.4532
| Total |  | 177.61 | 1437 | 283.5 | 360 | 186.79 | 2444.9 |  |  | Total | 1411.21
Concern
Bricks in Part D needs to be shifted so that we can carry out the excavation of remaining 21 foundations as it is in Priority.
Part G excavation permit is awaited.
Scrap in Part I needs to be removed in order to excavate remaining 10 footings as it is in priority area.
|  | Excavation | PCC | Foundation | Pier 1900 mm | Pier 1600 mm | Pier Cap | Remark |  |  |  | 15% | 25% | 30% | 30%
| Part I | 12 | 36 | 300 | 96 | 80 | 77 | Subject to Clearence | 589 | 146.6667 | 735.6667 | 110.35 | 183.9167 | 220.7 | 220.7 | I | A | 25.3 | 42.1667 | 50.6 | 50.6
| Part C | 11 | 33 | 275 | 42 | 0 | 0 |  | 350 | 146.6667 | 496.6667 | 74.5 | 124.1667 | 149 | 149 | C | B | 31.9 | 53.1667 | 63.8 | 63.8
| Part D | 21 | 63 | 525 | 126 | 125 | 110 | Subject to Clearence | 949 | 146.6667 | 1095.6667 | 164.35 | 273.9167 | 328.7 | 328.7 | D | C | 74.5 | 124.1667 | 149 | 149
| Part H | 10 | 30 | 250 | 0 | 0 | 0 |  | 280 | 146.6667 | 426.6667 | 64 | 106.6667 | 128 | 128 | H | D | 164.35 | 273.9167 | 328.7 | 328.7
| Part G | 6 | 18 | 150 | 36 | 0 | 0 | Subject to Clearence | 204 | 146.6667 | 350.6667 | 52.6 | 87.6667 | 105.2 | 105.2 | G | E | 0 | 0 | 0 | 0
| Part A |  | 0 | 0 | 0 | 0 | 22 |  | 22 | 146.6667 | 168.6667 | 25.3 | 42.1667 | 50.6 | 50.6 | A | F | 28.75 | 47.9167 | 57.5 | 57.5
| Part B |  | 0 | 0 | 0 | 0 | 66 |  | 66 | 146.6667 | 212.6667 | 31.9 | 53.1667 | 63.8 | 63.8 | B | G | 52.6 | 87.6667 | 105.2 | 105.2
| Part J |  | 0 | 0 | 0 | 50 | 0 |  | 50 | 146.6667 | 196.6667 | 29.5 | 49.1667 | 59 | 59 | J | H | 64 | 106.6667 | 128 | 128
| Part F |  | 0 | 0 | 0 | 45 | 0 |  | 45 | 146.6667 | 191.6667 | 28.75 | 47.9167 | 57.5 | 57.5 | F | I | 110.35 | 183.9167 | 220.7 | 220.7
| Total | 60 | 180 | 1500 | 300 | 300 | 275 |  | 2555 | 1320 | 3875 | 581.25 | 968.75 | 1162.5 | 1162.5 |  | J | 29.5 | 49.1667 | 59 | 59
[18 empty] | 581.25 | 968.75 | 1162.5 | 1162.5

## Plan July (hidden)
Progress Details
Section | No. of piers | Actual Scope | No. of Pier as per Drawing Available | Length of piers | Clear Front (Nos.) | Excavation (Nos.) | PCC (Nos.) | PCC (Cum) | Footings (Nos.) | Footings (cum) | 1.9m dia lift (Nos.) | 1.9m dia lift (Cum) | 1.6m dia lift (Nos.) | 1.6m dia lift (Cum) | PIER Cap | Precast Segments | Plan March | Achieved March | Plan April | Achieved | Plan May | Achieved May | Plan June | Acieved | Plan July | Achieved July | Issues and concern | pcc | FOOTING | Pier | Pier | Pier Cap
A | 50 | 40 | 40 | 3mtr | 14 | 8 | 8 | 24 | 8 | 154 | 8 | 46.16 | 4 | 15.1 | [12 empty] | Site Clearance | 120 | 980 | 240 | 84 | 700
B | 33 | 28 | 28 | 3mtr | 10 | 10 | 10 | 30 | 10 | 192.5 | 10 | 57.7 | - | - | [12 empty] | Site Clearance | 84 | 686 | 168 | 58.8 | 490
H | 61 | 40 | 0 | 5.8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | [12 empty] | Issue of Drawings | 0 | 0 | 0 | 0 | 0
C | 18 | 18 | 0 | 5.8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | [12 empty] | Issue of Drawings | 0 | 0 | 0 | 0 | 0
I | 43 | 55 | 55 | 8mtrs | 23 | 6 | 3 | 9 | 0 | 0 | 0 | 0 | - | - | [12 empty] | Site Clearance | 165 | 1347.5 | 330 | 115.5 | 962.5
D | 90 | 69 | 69 | 8mtrs to 3mtrs | 33 | 33 | 33 | 99 | 31 | 596.75 | 21 | 121.17 | 11 | - | [12 empty] | Site Clearance | 207 | 1690.5 | 414 | 144.9 | 1207.5
E | 28 | 36 | 36 | 8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | [12 empty] | Issue of Drawings | 108 | 882 | 216 | 75.6 | 630
G | 45 | 33 | 0 | 5.8mtrs to 8mtrs | - | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | [12 empty] | Issue of Drawings | 0 | 0 | 0 | 0 | 0
J | 44 | 41 | 41 | 9mtrs | 41 | - | 0 | 0 | 0 | 0 | 0 | 0 | - | - | [12 empty] | Not in Priority | 123 | 1004.5 | 246 | 86.1 | 717.5
F | 122 | 108 | 30 | 11.4mtrs | 30 | 30 | 30 | 90 | 30 | 577.5 | 30 | 173.1 | 1 | 17.5 | [12 empty] | Not in Priority | 90 | 735 | 180 | 63 | 525
Total | 534 | 468 | 264 |  | 151 | 87 | 84 | 252 | 79 | 1520.75 | 69 | 398.13 | 16 | 32.6 | [13 empty] | 897 | 7325.5 | 1794 | 627.9 | 5232.5
7
Sr. No. | Activity | Scope in Nos. | Completed till date | Plan for June’22 |  | Achieved till 30th June’22 |  | Backlog | Remarks
|  |  |  | Nos. | M3 | Nos. | M3
1 | Foundation Concreting | 468 | 79 | 40 | 970 | 28 | 679 | 291 | 1.Less manpower has been deployed at site.(Current/Expected Nos.:- 30/75).
2 | Pier columns 1600mm dia | 468 | 16 | 30 | 66 | 11 | 22 | 44 | 2.Work hampered due to rain.
3 | Pier columns 1900mm dia | 468 | 69 | 30 | 173.1 | 27 | 155.79 | 17.31
Total Concreting(RCC+PCC) |  |  |  |  | 1209.1 |  | 856.79 | 352.31
Sr. No. | Activity | Scope in Nos. | Clear Front | Completed till date | July’22 Plan(Nos.) | July’22 Plan(Cum) | Remarks
1 | Civil Excavation | 468 | 151 | 87 | 40 | 6000 | 1.Plan is based on the available drawings, site front and priority.
2 | PCC for foundations | 468 | 151 | 84 | 40 | 120 | 2.Section I & J requires reinforcement drawings from MECON. (Not considered in plan)
3 | RCC for foundations | 468 | 151 | 79 | 40 | 970 | 3.Refractory bricks to be removed for enabling work front for I section.
4 | Pier columns 1900mm dia | 468 | 151 | 69 | 40 | 230.8
5 | Pier columns 1600mm dia | 468 | 151 | 1st Lift:- 16 | 60 | 126
2nd Lift:- 1
6 | Pier Capping | 468 | 151 | 0 | 10 | 120
Total Concreting(RCC) | [5 empty] | 1446.8
Precast Plan
S.No. | Name of Structures | Tentative Scope | Total No as Per Drawings Received | July’22 Plan(Nos.) | July’22 Plan(Cum.)
1 | Track Beam with Nose | 600 | 262 | 20 | 239.76 | 7192.8
2 | Track Beam without Nose | 600 | 298 | 20 | 229.6 | 6888
3 | h - Section Beam | 600 | 128 | 20 | 187 | 5610
4 | U - Section Beam | 600 | 114 | 20 | 181 | 5430
5 | Pre-cast Slab |  | 105 | 0 | 0 | 0
TOTAL |  |  |  |  | 837.36
Erection Plan
S.No. | Name of Structures | Total No as Per Drawings Received | July’22 Plan(Nos.) | July’22 Plan(Cum.)
1 | Track Beam with Nose | 262 | 4 | 47.952
2 | Track Beam without Nose | 298 | 0 | 0
3 | h - Section Beam | 128 | 2 | 18.7
4 | U - Section Beam | 114 | 2 | 18.1
5 | Pre-cast Slab | 105 | 0 | 0
TOTAL
13104
1700
14804